## General Schedule
Comments:
Days from the mobilization start date (D=0).
Total float = slack in relation to the project's critical path.
Legend - Scope column:
ETN: activities carried out by ETN and its otther contractors, except for the EPC.
EPC: activities carried out by the EPC.
ADDITIONAL: Activities which are expected to be part of the scope that may be added to the EPC, according to clause
18.1.5 of the Contract. However, this preliminary view of this scope may still be revised.
Level | Cod_aux | Activity Id | Description | Scope | Duration | Initial date (day) | Final date (day) | Total Float | Predecessors | Successors
0 | 0 | - | Angra 3 - General Schedule |  | - | Em andamento | 1950 | 0
1 | 1 | - | KEY MILESTONES |  | 1951 | 0 | 1950 | 0
2 | 1.1 | - | Special Authorizations |  | 421 | 1530 | 1950 | 0
3 | 1.1.1 | CEG9273940a | Authorization for the Use of Nuclear Material (AUMAN) | ETN | - | - | 1530 | 0 | CEGLIC0000 | CEG9273950a
3 | 1.1.2 | CEG9273950a | Authorization for Initial Operation (AOI) | ETN | - | - | 1770 | 0 | CEG9273940a | CEG9273960a
3 | 1.1.3 | CEG9273960a | Authorization for Permanent Operation (AOP) | ETN | - | - | 1950 | 0 | CEG9273950a | CEG1340000
2 | 1.2 | - | Licensing |  | 442 | 1509 | 1950 | 0
3 | 1.2.1 | CEGLIC0150 | Authorization for the Use of Nuclear Material (AUMAN) | ETN | - | 1509 | - | 245 | CEG6470000 | CEG1320000
3 | 1.2.2 | CEGLIC0200 | Authorization for Initial Operation (AOI) | ETN | - | 1766 | - | 185 | CEG1340000 | CEGLIC0250
3 | 1.2.3 | CEGLIC0250 | Operating License (LO) | ETN | - | 1920 | - | 31 | CEG1340000, CEGLIC0200 | CEGLIC0300
3 | 1.2.4 | CEGLIC0300 | Authorization for Permanent Operation (AOP) | ETN | - | - | 1950 | 0 | CEG1340000, CEGLIC0250
2 | 1.3 | - | Assembly Support Services |  | 935 | 152 | 1086 | 864
3 | 1.3.1 | CEG0916660 | Manitowoc available for Lifting and Positioning Services | ADDITIONAL | - | 152 | - | 0 | CEG1460000, CEG9273815 | CEG2590000, CEG2600000, CEG2630000, CEG0916430, CEG0916340
2 | 1.4 | - | Civil Construction |  | 570 | 0 | 569 | 354
3 | 1.4.1 | CEG6670000 | Beginning of EPCist Mobilization | EPC | - | 0 | - | 0 | CEG1341140, CEG9273980, CEG9273810, CEG9270120, CEG9270130 | CEG1520000, CEG3608000, CEG6680000, CEG6700000, CEGPA03200, CEG9273815
3 | 1.4.2 | CEG1410000 | Start of Installation of JNG Accumulators (UJA) (Package M112/ Nuclep/ 1st batch) | ADDITIONAL | - | 569 | - | 354 | CEG1390000, CEG1405000, CEG1390000PL | CEG1870000, CEG0916700, CEG1870100, CEG1870200, CEG1870300, CEG1870400, CEG1870500, CEG1870600, CEG1870700, CEG1870800, CEG1870900, CEG1870101, CEG1870110, CEG1870120, CEG1870130, CEG1870140, CEG1870150, CEG1870160, CEG1870170, CEG1870180, CEG1870190, CEG1870201, CEG1870210, CEG1870220, CEG1870230, CEG1870240, CEG1870250, CEG1870260, CEG1870270, CEG1870280, CEG1870290, CEG1870301, CEG1870310, CEG1870320, CEG1870330, CEG1870340, CEG1870350, CEG1870360, CEG1870370, CEG1870380, CEG1870390, CEG1870401, CEG1870410, CEG1870420, CEG1870430, CEG1870440, CEG1870450, CEG1870460, CEG1870470, CEG1870480, CEG1870490, CEG1870501, CEG1870510
3 | 1.4.3 | CEG4913700 | Demobilization and Installation of the Site for Civil Construction and Small Complementary Assemblies | ADDITIONAL | 120 | 967 | 1086 | 864 | CEG1030000, CEG59900011 | CEG1340000
2 | 1.5 | - | Electromechanical Erection |  | 1507 | 152 | 1658 | 124
3 | 1.5.1 | CEG1230000 | Start of SAC Ventilation Erection (UBA) | EPC | - | 152 | - | 403 | CEG6700000 | CEG3710000, CEG5720000
3 | 1.5.2 | CEG6400000 | Start of Piping Erection (UMA) | EPC | - | 152 | - | 1080 | CEG3180000, CEG6700000 | CEG1411000
3 | 1.5.3 | CEG3085000 | Completion of Mobilization for the Erection of Condensers (UMA) | EPC | - | 194 | - | 409 | CEG6700000 | CEG3080000, CEG3087000, CEG3080100
3 | 1.5.4 | CEG6410000 | Start of Electrical and Ventilation Erection (ULB) | EPC | - | 400 | - | 399 | CEG3410000, CEG6700000, CEG9271750, CEG9271780 | CEG4010000
3 | 1.5.5 | CEG6420000 | Start of Generator Busbars Erection (UMA / Ext.) | EPC | - | 524 | - | 598 | CEG4190000, CEG4180000, CEG4181000, CEG4191000 | CEG4230000
3 | 1.5.6 | CEG1426000 | Start of Erection of Polar Crane Rails SMJ01 (UJA) | ADDITIONAL | - | 622 | - | 13 | CEG1425000, CEG0916480, CEG0916480PL | CEG1430000
3 | 1.5.7 | CEG6390000 | Start of Piping Erection (UZT / PEB) | EPC | - | 712 | - | 731 | CEG3330000, CEG6700000, CEG6700000 | CEG6270000
3 | 1.5.8 | CEG1391000 | Start of Piping Erection (UJB) | EPC | - | 877 | - | 295 | CEG1140000, CEG1180000, CEG1140100 | CEG1180100
3 | 1.5.9 | CEG6350000 | Completion of Electromechanical Erection - Conventional Area | EPC | - | - | 1556 | 226 | CEG5260000, CEG6140000, CEG4850000, CEG5790000, CEG6080000, CEG4920000, CEG5330000, CEG5420000, CEG4320000, CEG3500000, CEG6270000, CEG2960000, CEG2900000, CEG4290000, CEG3717000, CEG6280000, CEG6260000, CEG3525000, CEG2980000, CEG6290000, CEG6320000, CEG6310000, CEG6300000, CEG3210000, CEG3190000, CEG3280000, CEG6360000, CEG6330000 | CEG1315000
3 | 1.5.10 | CEG6340000 | Completion of Electromechanical Erection - Nuclear Area | EPC | - | - | 1658 | 124 | CEG2315000, CEG1890000, CEG1200000, CEG2240000, CEG6240000, CEG6190000, CEG2250000, CEG1590000, CEG2320000, CEG1900000, CEG2790000, CEG6590000, CEG2730000, CEG2810000 | CEG1315000
2 | 1.6 | - | Phase A Commissioning |  | 708 | 942 | 1649 | 4
3 | 1.6.1 | CEG1262000 | Start of Commissioning of the Auxiliary Electrical System (UBA/S1) (Phase A) | EPC | - | 942 | - | 158 | CEG3640000, CEG3630000, CEG3650000, CEG3655000, CEG3660000, CEG4100000, CEG4400000, CEG3610000, CEG3670000, CEG5740000, CEG1451000, CEG7035000, CEG7035100 | CEG3745000, CEG4710000, CEG6430000, CEG1279000
3 | 1.6.2 | CEG1279000 | Connection of 138 kV Offsite Power Grid (138 kV "Switch-on") (Phase A) | EPC | - | 1062 | - | 218 | CEG4110000, CEG1520000, CEG4115000, CEG1262000, CEG4911000, CEG4911600, CEG4912200 | CEG6430000
3 | 1.6.3 | CEG6430000 | Auxiliary Electrical System ready to use (UBA / Start V-IBS) (Phase A) | EPC | - | - | 1106 | 218 | CEG1262000, CEG1279000 | CEG3525000, CEG6440000
3 | 1.6.4 | CEG6440000 | Start of Commissioning of JN / FAK (UJA) Systems (Phase A) | EPC | - | 1257 | - | 218 | CEG1880000, CEG6430000 | CEG1401000, CEG1285000
3 | 1.6.5 | CEG1285000 | Start of Primary Circuit Pressure Test (UJA) (Phase A) | EPC | - | 1580 | - | 0 | CEG1464000, CEG1474000, CEG2640000, CEG6440000, CEG0916010, CEG0916130, CEG0916250, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230 | CEG1290000, CEG1302000, CEG1310000, CEG1470000, CEG6460000
3 | 1.6.6 | CEG6460000 | Start of Secondary Circuit Pressure Test (UMA) (Phase A) | EPC | - | 1580 | - | 23 | CEG1285000, CEG1411000, CEG3100000, CEG3146000, CEG3180000, CEG3870000, CEG5350000, CEG1470000 | CEG1302000
3 | 1.6.7 | CEG1290000 | 500 kV Main Grid Connection (500 kV Switch-on) (Phase A) | EPC | - | 1580 | - | 59 | CEG4160000, CEG4220000, CEG4250000, CEG1285000, CEG4913400, CEG4912800 | CEG1310000
3 | 1.6.8 | CEG1481000 | Completion of Secondary Circuit Pressure Test(UMA) (Phase A) | EPC | - | - | 1614 | 39 | CEG1302000 | CEG1310000
3 | 1.6.9 | CEG6450000 | Start of Pressure Test of the Containment Sphere JMA (UJA) (Phase A) | EPC | - | 1615 | - | 0 | CEG1075000, CEG1110000, CEG1270000, CEG1361000, CEG2610000, CEG1420000, CEG1422000, CEG1263000, CEG0916410, CEG3870000, CEG1474000, CEG1030000, CEG0916640, CEG1470000, CEG1634000, CEG0916180 | CEG1300000
3 | 1.6.10 | CEG1471000 | Completion of Pressure Test of the Containment Sphere JMA (UJA) (Phase A) | EPC | - | - | 1649 | 0 | CEG1300000 | CEG2650000, CEG1310000
2 | 1.7 | - | Commissioning Phases B, C and D |  | 297 | 1654 | 1950 | 0
3 | 1.7.1 | CEG1310000 | Start of the First Hot Operation (Phase B) | EPC | - | 1654 | - | 0 | CEG1290000, CEG2870000, CEG3430000, CEG1150000, CEG2540000, CEG3530000, CEG3590000, CEG3250000, CEG1680000, CEG3860000, CEG1302000, CEG1470000, CEG1285000, CEG1471000, CEG1481000, CEG5915000, CEG5970000, CEG5935000, CEG5955000, CEG5990000, CEG3940000, CEG3980000, CEG3900000, CEG3970000, CEG2900000, CEG2960000, CEG3500000, CEG6260000, CEG3820000, CEG3330000, CEG2690000, CEG1431000, CEG2780000, CEG2920000, CEG4260000, CEG6050000, CEG6040000, CEG1750000, CEG1760000, CEG3745000, CEG59900001, CEG6041000, CEG6051000, CEG3981000, CEG3941000 | CEG6470000, CEG1650000, CEG1311000
3 | 1.7.2 | CEG6470000 | Start of Core Loading (Phase C) | EPC | 1 | 1753 | 1753 | 0 | CEG1310000, CEG1273000, CEG1311000, CEG1401000, CEG1590000, CEG1900000, CEG2250000, CEG2320000, CEG2730000, CEG2790000, CEG2810000, CEG2980000, CEG3190000, CEG3210000, CEG3230000, CEG3525000, CEG3717000, CEG4060000, CEG4290000, CEG6270000, CEG6280000, CEG6290000, CEG6300000, CEG6310000, CEG6320000, CEG6330000, CEG6360000, CEG1610000, CEG2650000, CEG1650000, CEG5660000, CEG5670000, CEG5680000, CEG5690000, CEG5700000, CEG5650000, CEG5500000, CEG5510000, CEG5520000, CEG5530000, CEG5610000, CEG5620000, CEG5630000, CEG5640000, CEG5540000, CEG5550000, CEG5560000, CEG5570000, CEG5580000, CEG5590000, CEG5600000, CEG5710000, CEG4370000, CEG0916240, CEG9040000, CEG6590000 | CEG1320000, CEGLIC0150
3 | 1.7.3 | CEG1315000 | Start of the Second Hot Operation (Phase C) | EPC | - | 1783 | - | 0 | CEG2180000, CEG1320000, CEG2750000, CEG3620000, CEG6340000, CEG6350000 | CEG6560000
3 | 1.7.4 | CEG1325000 | First Criticality (Phase D) | EPC | - | 1831 | - | 0 | CEG1491000, CEG1337000 | CEG1327000, CEG6490000
3 | 1.7.5 | CEG1491000 | Start of Power Tests (Start: rise 0% to 30%) (Phase D) | EPC | - | 1831 | - | 0 | CEG1330000 | CEG1325000, CEG6520000, CEG6490000
3 | 1.7.6 | CEG1327000 | Synchronization with the 500 kV Main Grid (Phase D) | EPC | - | 1841 | - | 20 | CEG1325000 | CEG1340000, CEG6520000
3 | 1.7.7 | CEG6520000 | Power Escalation (Start rise 30% to 80%) (Phase D) | EPC | - | 1861 | - | 0 | CEG1491000, CEG6490000, CEG1327000 | CEG6530000, CEG6500000
3 | 1.7.8 | CEG6530000 | Power Escalation (Finish: rise 80% to 100%) (Phase D) | EPC | - | - | 1890 | 0 | CEG6520000, CEG6500000 | CEG6510000
3 | 1.7.9 | CEG6540000 | Start of Plant Demonstration Testing (Phase D) | EPC | - | 1921 | - | 0 | CEG6510000 | CEG1335000
3 | 1.7.10 | CEG6550000 | End of Trial Operation (Phase D) | EPC | - | - | 1950 | 0 | CEG1335000 | CEG1340000
2 | 1.8 | - | Commercial Operation |  | 1 | 1950 | 1950 | 0
3 | 1.8.1 | CEG1340000 | Start of Commercial Operation | ETN | - | - | 1950 | 0 | CEG1344000, CEG1327000, CEG1337000, CEG6550000, CEG9273960a, CEG59900071, CEG59900041, CEG59900101, CEG9274520, CEG9273930, CEG9273900, CEG9273840, CEG1490000, CEG9273870, CEG9273985, CEG9274030, CEG59900011, CEG4913700, CEG2010000, CEG59900221, CEG1671000, CEG4935000 | CEGLIC0300, CEGLIC0200, CEGLIC0250
1 | 2 | - | SITE AND MAIN CONTRACTS |  | - | Em andamento | 1653 | 297
2 | 2.1 | - | Mobilizations |  | 152 | 0 | 151 | 400
3 | 2.1.1 | CEG9273815 | Mobilization and Installation of the Site for Civil Construction and Small Complementary Assemblies | ADDITIONAL | 152 | 0 | 151 | 0 | CEG9273810, CEG6670000 | CEG2590000, CEG5990000, CEG2460000, CEG2000000, CEG1990000, CEG1970000, CEG0916340, CEG1370000, CEG0916500, CEG0916660, CEG1710000, CEG3600000, CEG4913500, CEG4913600, CEG3391000, CEG3598000, CEG1370100, CEG6680000, CEG6700000, CEGPA03200, CEG1380100, CEG1970100, CEG5925000, CEG5965000, CEG5965100, CEG5925100, CEG2521000, CEG5981000, CEG1370100PL, CEG1380100PL, CEG3390010
3 | 2.1.2 | CEG6680000 | Mobilization and Installation of the EPCist Site (Nuclear Area) | EPC | 152 | 0 | 151 | 124 | CEG6670000, CEG1460000, CEG9273815 | CEG1850000, CEG5370000, CEG2290000, CEG2720000, CEG6210000, CEG1170000, CEG2210000, CEG1850000, CEG2630000, CEG2220000, CEG2720000, CEG1170000, CEG2210000, CEG2800000, CEG2710000, CEG1420000, CEG5370000, CEG2290000, CEG6210000, CEG2200000, CEG2630000, CEG2220000, CEG1860000, CEG2800000, CEG2710000, CEG1420000, CEG1160100, CEG9159000, CEG9170100, CEG5005100, CEG9210100, CEG4995000, CEG9274010, CEGPA42000, CEG9270300, CEG9270330, CEG9272160, CEG9272190, CEG9272250, CEG9272280, CEG9272340, CEG9271680, CEG9200000, CEG9273510, CEG5055000, CEG9271410, CEG4925000, CEG4955000, CEG4975000, CEG9271260, CEG9271230, CEG9271200, CEG9272580, CEG9271170, CEG9272550, CEG9270240, CEG3253400, CEG9271140, CEG9271080, CEG9271050, CEG9271020, CEG9270990, CEG9270930, CEG9270210, CEG9272430, CEG9272400, CEG9272370, CEG3725000
3 | 2.1.3 | CEGPA03200 | Mobilization and Installation of the EPCist Site (Civil Construction) | EPC | 152 | 0 | 151 | 395 | CEG6670000, CEG1460000, CEG9273815 | CEG4090000, CEG3765000, CEG3760000, CEG3570000, CEG3540000, CEG2490000, CEG3800000, CEG3250000, CEG1140000, CEG2160000, CEG3370000, CEG4000000, CEG2165000, CEG3410000, CEG2540000, CEG1680000, CEG1541000, CEG3371000, CEG4913610, CEG1720000, CEG2161000, CEG6001000, CEG2821000, CEG4171000, CEG3361000, CEG6041000, CEG6051000, CEG3341000, CEG3911000, CEG3931000, CEG3981000, CEG3941000, CEG3791000, CEG3991000, CEG4001000, CEG3511000, CEG4181000, CEG4121000, CEG4131000, CEG5970000, CEG3610000
3 | 2.1.4 | CEG6700000 | Mobilization and Installation of the EPCist Site (Conventional Area) | EPC | 152 | 0 | 151 | 400 | CEG6670000, CEG1460000, CEG9273815 | CEG5370000, CEG4960000, CEG5020000, CEG1230000, CEG4410000, CEG5750000, CEG6100000, CEG3630000, CEG5300000, CEG3200000, CEG3260000, CEG4470000, CEG4900000, CEG6410000, CEG6390000, CEG6400000, CEG3180000, CEG4400000, CEG3780000, CEG3560000, CEG3530000, CEG3590000, CEG5300000, CEG3630000, CEG3180000, CEG2890000, CEG3460000, CEG4010000, CEG4100000, CEG4230000, CEG3260000, CEG3770000, CEG3780000, CEG4070000, CEG3220000, CEG3490000, CEG3640000, CEG3650000, CEG3590000, CEG3530000, CEG3720000, CEG3705000, CEG4960000, CEG5020000, CEG6100000, CEG3200000, CEG6390000, CEG2890000, CEG3460000, CEG4010000, CEG4100000, CEG4230000, CEG3770000, CEG4070000, CEG3220000, CEG3490000, CEG3640000, CEG3650000, CEG3720000, CEG3705000, CEG3146000, CEG6640000, CEG3095000, CEG3080000, CEG4830000, CEG1240000, CEG3489000, CEG3489000, CEG3095100, CEG3080100, CEG4830100, CEG4890100, CEG3144000, CEG3085000, CEG9270960, CEG9271470, CEG5839000, CEG9271530, CEG9080100, CEG5221000, CEG4141000, CEG4151000, CEG4191000, CEG4201000, CEG4211000
2 | 2.2 | - | Hiring Design Engineering Services |  | - | Em andamento | 839 | 1111
3 | 2.2.1 | - | Hiring of Heat Exchangers (Package M101) |  | - | Em andamento | Anterior ao EPC | 998
4 | 2.2.1.1 | CEG2318000 | Fabrication of 9 Heat Exchangers KBA11/12BC001/002-KAB70BC001-JNA10a40BC001 (UJB) (M101) | ETN | - | Em andamento | Anterior ao EPC | 998 | CEG2317500 | CEG2323000
4 | 2.2.1.2 | CEG2323000 | 'CIP Delivery of 9 Heat Exchangers KBA11/12BC001/002-KAB70BC001-JNA10a40BC001 (UJB) (New Package M101) | ETN | - | - | Anterior ao EPC | 998 | CEG2318000 | CEG2324000
3 | 2.2.2 | - | Hiring Civil Works Supervision and Electromechanical Erection |  | - | Em andamento | 59 | 1891
4 | 2.2.2.1 | CEG9273840 | Civil Works and Electromechanical Erection Services Supervision | ETN | - | Em andamento | 59 | 1891 | CEG9273830, CEG9274035 | CEG1340000
3 | 2.2.3 | - | Hiring Electromechanical Design |  | - | Em andamento | Anterior ao EPC | 614
4 | 2.2.3.1 | CEG1341140 | Issuance of Documentation for Engineering Services for Electromechanical Package 3 | ETN | - | Em andamento | Anterior ao EPC | 614 | CEG1341130 | CEG6670000
3 | 2.2.4 | - | Hiring Civil Design |  | - | Em andamento | 839 | 1111
4 | 2.2.4.1 | CEG9273980 | Issuance of Documentation of the Civil Design Engineering Services | ETN | - | Em andamento | Anterior ao EPC | 614 | CEG9273970 | CEG6670000, CEG3381000, CEG3383000
4 | 2.2.4.2 | CEG9273985 | Monitoring of Civil Design Engineering Services | ETN | - | Em andamento | 839 | 1111 | CEG9273970 | CEG1340000
3 | 2.2.5 | - | Hiring Complementary Electrical Design |  | 422 | 121 | 542 | 1408
4 | 2.2.5.1 | CEG9274010 | Signing of the Engineering Services Contract for the Complementary Electrical Design | EPC | 31 | 121 | 151 | 1408 | CEG6680000 | CEG9274020
4 | 2.2.5.2 | CEG9274020 | Authorization Start of Activities of the Complementary Electrical Design Engineering Services Contract | EPC | 31 | 152 | 182 | 1408 | CEG9274010 | CEG9274030
4 | 2.2.5.3 | CEG9274030 | Issuance of Documentation for Engineering Services of the Complementary Electrical Design | EPC | 360 | 183 | 542 | 1408 | CEG9274020 | CEG1340000
3 | 2.2.6 | - | Hiring Owners – Owner Engineering |  | - | Em andamento | 72 | 1878
4 | 2.2.6.1 | CEG1490000 | Support Services (Owners) - Owner Engineering | ETN | - | Em andamento | 72 | 1878 | CEG1480000 | CEG1340000
3 | 2.2.7 | - | Hiring Inspection and Testing |  | - | Em andamento | Anterior ao EPC | 2219
4 | 2.2.7.1 | CEG9273870 | Inspection and Testing Services | ETN | - | Em andamento | Anterior ao EPC | 2219 | CEG9273860 | CEG1340000
3 | 2.2.8 | - | Hiring of Pools Erection for Fuel Elements (phases 1 and 2) |  | 439 | 90 | 528 | 184
4 | 2.2.8.1 | CEG1540000 | Mobilization for Pool Lining Erection Phase 1 | ADDITIONAL | 92 | 90 | 181 | 0 | CEG1530000 | CEG0916340
4 | 2.2.8.2 | CEG1541000 | Mobilization for Pool Lining Erection Phase 2 | EPC | 122 | 407 | 528 | 184 | CEGPA03200 | CEG59900111, CEG59900121
3 | 2.2.9 | - | Hiring of Erection of the Containment Sphere |  | 150 | 419 | 568 | 0
4 | 2.2.9.1 | CEG1510000 | Mobilization for the Containment Sphere Erection | ADDITIONAL | 150 | 419 | 568 | 0 | CEG1500000 | CEG1080000
3 | 2.2.10 | - | Hiring of Condensers Erection |  | 1 | 1 | 1 | 409
4 | 2.2.10.1 | CEG5810000 | Hiring of the Erection Services of MAG 10/20/30 | ETN | 1 | 1 | 1 | 409 | CEGLIC0000 | CEG3095100
3 | 2.2.11 | - | Hiring of Independent Technical Supervision Body - OSTI |  | - | Em andamento | Anterior ao EPC | 2003
4 | 2.2.11.1 | CEG9273900 | Continuous Service of Independent Technical Supervision - OSTI - IBQN | ETN | - | Em andamento | Anterior ao EPC | 2003 | CEG9273890 | CEG1340000
3 | 2.2.12 | - | Hiring of Manitowoc Crane Maintenance |  | - | Em andamento | 150 | 1800
4 | 2.2.12.1 | CEG59900101 | Independent Compilance or Compliance Program Services | ETN | - | Em andamento | Anterior ao EPC | 2160 | CEG59900091 | CEG1340000
4 | 2.2.12.2 | CEG9273930 | Manitowoc Crane Maintenance Services | ETN | - | Em andamento | 150 | 1800 | CEG9273920 | CEG1340000
2 | 2.3 | - | Procurement (UJA/UJB/UJE/UJF/UKA/UKH) |  | - | Em andamento | 1653 | 207
3 | 2.3.1 | - | Procurement of Equipment and Materials |  | - | Em andamento | 1356 | 504
4 | 2.3.1.1 | - | 0024 REFUELING MACHINE MECH.PA |  | - | Anterior ao EPC | Anterior ao EPC | 1052
5 | 2.3.1.1.1 | CEG1636000 | FOB FRAMATOME Delivery - Refuelling Machine FCB (UJA) (FRAMATOME/1561/SUP024) | ETN | - | - | Anterior ao EPC | 1052 | CEG1348000 | CEG1640000
4 | 2.3.1.2 | - | 0565 FOOT PLATES TO BE WELDED |  | 1 | 814 | 814 | 184
5 | 2.3.1.2.1 | CEG1631000 | Delivery FOB FRAMATOME - Supercompact Racks Fuel Storage FAB (Z1) (UJA) (FRAMATOME/1574/SUP565, 565A and 642) | ETN | - | - | 814 | 184 | CEG1348000 | CEG1632000
4 | 2.3.1.3 | - | E024 Electroacoustic Alarm System |  | 240 | 582 | 821 | 158
5 | 2.3.1.3.1 | CEG7035100 | Renegotiation of the Electroacoustic Alarm System [E024] | ETN | 240 | 582 | 821 | 158 | CEGLIC0000 | CEG1262000, CEG4710000
4 | 2.3.1.4 | - | E040 Cathodic Protection |  | - | Em andamento | 391 | 692
5 | 2.3.1.4.1 | CEG6085000 | Negotiation for Return of Cathodic Protection Services [E040] | ETN | - | Em andamento | 102 | 692 | CEGLIC0000 | CEG6095000
5 | 2.3.1.4.2 | CEG6095000 | Cathodic Protection Fabrication [E040] | ETN | 290 | 102 | 391 | 692 | CEG6085000 | CEG6096000
5 | 2.3.1.4.3 | CEG6096000 | 'CIP Delivery of Cathodic Protection [E040] | ETN | - | - | 391 | 692 | CEG6095000 | CEG3330000
4 | 2.3.1.5 | - | GR001 Fan |  | - | Em andamento | 320 | 872
5 | 2.3.1.5.1 | CEG6005000 | Negotiation for Return of Fan Services [GR001] | ETN | - | Em andamento | Anterior ao EPC | 872 | CEGLIC0000 | CEG6015000
5 | 2.3.1.5.2 | CEG6015000 | Fan Fabrication [GR001] | ETN | - | Anterior ao EPC | 320 | 872 | CEG6005000 | CEG6016000
5 | 2.3.1.5.3 | CEG6016000 | 'CIP Delivery of Fans [GR001] | ETN | - | - | 320 | 872 | CEG6015000 | CEG3740000
4 | 2.3.1.6 | - | GR008 Dampers Adjustment |  | - | Anterior ao EPC | 320 | 872
5 | 2.3.1.6.1 | CEG6025000 | Negotiation for Return of Louver Damper Services [GR008] | ETN | - | Anterior ao EPC | Anterior ao EPC | 872 | CEGLIC0000 | CEG6035000
5 | 2.3.1.6.2 | CEG6035000 | Fabrication of Louver Dampers [GR008] | ETN | - | Anterior ao EPC | 320 | 872 | CEG6025000 | CEG6036000
5 | 2.3.1.6.3 | CEG6036000 | CIP Delivery of Louver Dampers [GR008] | ETN | - | - | 320 | 872 | CEG6035000 | CEG3740000
4 | 2.3.1.7 | - | GR022 Quick Closing Dampers |  | 510 | 457 | 966 | 295
5 | 2.3.1.7.1 | CEG7045000 | Finalize Fabrication of Quick Closing Dampers [GR022] | ETN | 510 | 457 | 966 | 295 | CEGLIC0000 | CEG7046000
5 | 2.3.1.7.2 | CEG7046000 | 'CIP Delivery of Quick Closing Dampers [GR022] | ETN | - | - | 966 | 295 | CEG7045000 | CEG1180520
4 | 2.3.1.8 | - | M100 Heat Exchangers - GR1 |  | - | Em andamento | 441 | 470
5 | 2.3.1.8.1 | CEG9260000 | Negotiation Return Services Heat Exchangers PGD01a03BC001-KAA10a40BC001-PJD10a40BC001/002 (UJB) (PCT M100) | ETN | - | Em andamento | Anterior ao EPC | 470 | CEGLIC0000 | CEG9270000
5 | 2.3.1.8.2 | CEG9270000 | Fabrication of Heat Exchangers PGD01a03BC001-KAA10a40BC001-PJD10a40BC001/002 (UJB) (PCT M100) | ETN | - | Anterior ao EPC | 441 | 470 | CEG9260000 | CEG2322000
5 | 2.3.1.8.3 | CEG2322000 | 'CIP Delivery of 15 Heat Exchangers PGD01a03BC001-KAA10a40BC001-PJD10a40BC001/002 (UJB) (PCT M100) | ETN | - | - | 441 | 470 | CEG9270000 | CEG2324000
4 | 2.3.1.9 | - | M112 Accumulators |  | 120 | 329 | 448 | 354
5 | 2.3.1.9.1 | CEG6065000 | Finalize Fabrication of Accumulators [M112] | ETN | 120 | 329 | 448 | 354 | CEGLIC0000 | CEG1405000
4 | 2.3.1.10 | - | M114 Tanks - GR5 |  | - | Em andamento | 876 | 295
5 | 2.3.1.10.1 | CEG5005000 | Negotiation of the Termination of GR5/GR6 Tank Services [M114_M115] | ETN | - | Em andamento | 276 | 295 | CEGLIC0000 | CEG5005100
5 | 2.3.1.10.2 | CEG5005100 | Mobilization of GR5/GR6 Tank Assembler [M114_M115] | EPC | 1 | 277 | 277 | 295 | CEG6680000, CEG5005000 | CEG5015000
5 | 2.3.1.10.3 | CEG5015000 | Fabrication of GR5/GR6 Tanks [M114_M115] | EPC | 600 | 277 | 876 | 295 | CEG5005100 | CEG5016000
5 | 2.3.1.10.4 | CEG5016000 | 'CIP Delivery of GR5/GR6 Tanks [M114_M115] | EPC | - | - | 876 | 295 | CEG5015000 | CEG1180100
4 | 2.3.1.11 | - | M117 Plastic Tanks |  | - | Anterior ao EPC | 221 | 691
5 | 2.3.1.11.1 | CEG5025000 | Negotiation for Return of Tank Services [M117_M155A_M155B_M161A_M175_M602_E045B] | ETN | - | Anterior ao EPC | 71 | 691 | CEGLIC0000 | CEG5035000
5 | 2.3.1.11.2 | CEG5035000 | Tanks Fabrication [M117_M155A_M155B_M161A_M175_M602_E045B] | ETN | 150 | 72 | 221 | 691 | CEG5025000 | CEG5036000
5 | 2.3.1.11.3 | CEG5036000 | 'CIP Delivery of Tanks [M117_M155A_M155B_M161A_M175_M602_E045B] | ETN | - | - | 221 | 691 | CEG5035000 | CEG4910800
4 | 2.3.1.12 | - | M178A Special Ports |  | 535 | 259 | 793 | 449
5 | 2.3.1.12.1 | CEG4995000 | Fabrication of Special Doors, Shielding Door, Decontamination Room Coating [M178A_M372_M340_M311B] | EPC | 535 | 259 | 793 | 449 | CEG4985000, CEG6680000 | CEG4996000
5 | 2.3.1.12.2 | CEG4996000 | CIP Delivery of Special Doors, Shielding Door, Decontamination Room Coating [M178A_M372_M340_M311B] | EPC | - | - | 793 | 449 | CEG4995000 | CEG6220000, CEG2220140
4 | 2.3.1.13 | - | M207 Horizontal Centrifugal Pumps |  | - | Anterior ao EPC | 221 | 601
5 | 2.3.1.13.1 | CEG5085000 | Negotiation for Return of Horizontal Centrifugal Pumps Services [M207] | ETN | - | Anterior ao EPC | Anterior ao EPC | 601 | CEGLIC0000 | CEG5095000
5 | 2.3.1.13.2 | CEG5095000 | Fabrication of Horizontal Centrifugal Pumps [M207] | ETN | - | Anterior ao EPC | 221 | 601 | CEG5085000 | CEG5096000
5 | 2.3.1.13.3 | CEG5096000 | 'CIP Delivery of Horizontal Centrifugal Pumps [M207] | ETN | - | - | 221 | 601 | CEG5095000 | CEG4910400
4 | 2.3.1.14 | - | M210 Nuclear Centrifugal Pumps |  | - | Em andamento | 756 | 124
5 | 2.3.1.14.1 | CEG5065000 | Negotiation for Return of Nuclear Centrifugal Pump Services [M210] | ETN | - | Em andamento | 156 | 124 | CEGLIC0000 | CEG5075000
5 | 2.3.1.14.2 | CEG5075000 | Fabrication of Nuclear Centrifugal Pumps [M210] | ETN | 600 | 157 | 756 | 124 | CEG5065000 | CEG5076000
5 | 2.3.1.14.3 | CEG5076000 | 'CIP Delivery of Nuclear Centrifugal Pumps [M210] | ETN | - | - | 756 | 124 | CEG5075000 | CEG1180400
4 | 2.3.1.15 | - | M214 Horizontal Centifugal Pumps |  | - | Anterior ao EPC | 421 | 641
5 | 2.3.1.15.1 | CEG6045000 | Negotiation for Return of Services of Horizontal Centrifugal Pumps [M214] | ETN | - | Anterior ao EPC | 61 | 641 | CEGLIC0000 | CEG6055000
5 | 2.3.1.15.2 | CEG6055000 | Fabrication of Horizontal Centrifugal Pumps [M214] | ETN | 360 | 62 | 421 | 641 | CEG6045000 | CEG6056000
5 | 2.3.1.15.3 | CEG6056000 | 'CIP Delivery of Horizontal Centrifugal Pumps [M214] | ETN | - | - | 421 | 641 | CEG6055000 | CEG2220900
4 | 2.3.1.16 | - | M302 Locks Sealing Walls |  | 549 | 429 | 977 | 175
5 | 2.3.1.16.1 | CEG4975000 | Fabrication of Locks Sealing Wall, Stand Rods, Guide Rods, Rad. Sample Holder, ... [M302_M318_M334b_M336] | EPC | 549 | 429 | 977 | 175 | CEG4965000, CEG6680000 | CEG4976000
5 | 2.3.1.16.2 | CEG4976000 | CIP delivery of Locks Sealing Wall, Stand Rods, Guide Rods, Rad. Sample Holder, ... [M302_M318_M334b_M336] | EPC | - | - | 977 | 175 | CEG4975000 | CEG1870401, CEG1075000
4 | 2.3.1.17 | - | M307 Wall Crane *UJA* |  | 520 | 292 | 811 | 461
5 | 2.3.1.17.1 | CEG4955000 | Fabrication of H3 Bridges, Cranes, Overhead Cranes and Hoists [M307_M308_M309_M316_M317_M341_M351] | EPC | 520 | 292 | 811 | 461 | CEG4945000, CEG6680000 | CEG4956000
5 | 2.3.1.17.2 | CEG4956000 | 'CIP Delivery of H3 Bridges, Cranes, Overhead Cranes and Hoists [M307_M308_M309_M316_M317_M341_M351] | EPC | - | - | 811 | 461 | CEG4955000 | CEG2220140
4 | 2.3.1.18 | - | M324 Support of Heavy Components |  | - | Anterior ao EPC | 310 | 322
5 | 2.3.1.18.1 | CEG9050000 | Negotiation for Return of Fabrication of Primary Circuit Component Supports (UJA) (Package M324/ Bardella) | ETN | - | Anterior ao EPC | Anterior ao EPC | 322 | CEGLIC0000 | CEG9055000
5 | 2.3.1.18.2 | CEG9055000 | Fabrication of Primary Circuit Component Supports (UJA) (Package M324/ Bardella) | ETN | - | Anterior ao EPC | 310 | 322 | CEG9050000 | CEG9060000
5 | 2.3.1.18.3 | CEG9060000 | CIP Delivery Primary Circuit Component Supports (UJA) (Package M324/ Bardella) | ETN | - | - | 310 | 322 | CEG9055000 | CEG2630000
4 | 2.3.1.19 | - | M325 Reactor Pressure Vessel Support |  | 300 | 251 | 550 | 322
5 | 2.3.1.19.1 | CEG9159000 | Mobilization of the RPV Support Erection Company (UJA) (Package M325) | EPC | 300 | 251 | 550 | 322 | CEGLIC0000, CEG6680000 | CEG2600000
4 | 2.3.1.20 | - | M326 RPV Insulation - Bottom + Nozzles |  | 450 | 480 | 929 | 0
5 | 2.3.1.20.1 | CEG7055000 | Negotiation and Finalize Insulation Fabrication and RPV Sealing Ring [M326_M327_M323] | ETN | 450 | 480 | 929 | 0 | CEGLIC0000 | CEG7056000
5 | 2.3.1.20.2 | CEG7056000 | CIP delivery of Insulation and RPV Sealing Ring [M326_M327_M323] | ETN | - | - | 929 | 0 | CEG7055000 | CEG0916750
4 | 2.3.1.21 | - | M330 Supercompact Racks |  | - | Anterior ao EPC | Anterior ao EPC | 1701
5 | 2.3.1.21.1 | CEG1633000 | Delivery FOB FRAMATOME - Supercompact Racks Fuel Storage FAB (Z2) (UJA) (FRAMATOME/1575/SUP642A and 643) | ETN | - | - | Anterior ao EPC | 1701 | CEG1348000 | CEG1634000
4 | 2.3.1.22 | - | M335 Pressure Equalizer Structure |  | 575 | 595 | 1169 | 691
5 | 2.3.1.22.1 | CEG4925000 | Fabrication of Circuit Pressure Equalising Structures - Overflow Cover - JMJ10 [M335] | EPC | 575 | 595 | 1169 | 691 | CEG4915000, CEG6680000 | CEG4926000
5 | 2.3.1.22.2 | CEG4926000 | CIP delivery of Circuit Pressure Equalising Structures - Overflow Cover - JMJ10 [M335] | EPC | - | - | 1169 | 691 | CEG4925000 | CEG4935000
4 | 2.3.1.23 | - | M337 Lifting Beam for RPV Cover |  | 470 | 887 | 1356 | 0
5 | 2.3.1.23.1 | CEG9100000 | Negotiation for Return of Services - Lifting Beam and RPV Cover Rod (UJA) (Package M337/M378 Bardella) | ETN | 240 | 887 | 1126 | 0 | CEGLIC0000 | CEG9110000
5 | 2.3.1.23.2 | CEG9110000 | Procurement and Fabrication of RPV Lifting Beam and Cover Rod (UJA) (Package M337/M378 Bardella) | ETN | 230 | 1127 | 1356 | 0 | CEG9100000 | CEG9120000
5 | 2.3.1.23.3 | CEG9120000 | CIP Delivery Lifting Beam and RPV Cover Rod (UJA) (Package M337/M378 Bardella) | ETN | - | - | 1356 | 0 | CEG9110000 | CEG9130000
4 | 2.3.1.24 | - | M354 Lifts |  | 390 | 231 | 620 | 872
5 | 2.3.1.24.1 | CEG5055000 | Lifts Fabrication [M354] | EPC | 390 | 231 | 620 | 872 | CEG5045000, CEG6680000 | CEG5056000
5 | 2.3.1.24.2 | CEG5056000 | CIP Delivery of Lifts [M354] | EPC | - | - | 620 | 872 | CEG5055000 | CEG3740000
4 | 2.3.1.25 | - | M493 Special Supports |  | 600 | 99 | 698 | 274
5 | 2.3.1.25.1 | CEG6075000 | Negotiation and Finalize Fabrication of Supports [M493_M494_M335 parts] | ETN | 600 | 99 | 698 | 274 | CEGLIC0000 | CEG6076000
5 | 2.3.1.25.2 | CEG6076000 | 'CIP Delivery of Supports [M493_M494_M335 parts] | ETN | - | - | 698 | 274 | CEG6075000 | CEG1870000, CEG2300000, CEG4935000
3 | 2.3.2 | - | Civil Dependent Equipment Procurement |  | - | Em andamento | 691 | 606
4 | 2.3.2.1 | - | M112 Accumulators |  | 1 | 448 | 448 | 354
5 | 2.3.2.1.1 | CEG1405000 | CIP Delivery JNG Accumulators (UJA) (Package M112/ Nuclep) | ETN | - | - | 448 | 354 | CEG6065000 | CEG1410000, CEG0916700
4 | 2.3.2.2 | - | M130 KBF Degassing Column |  | - | Em andamento | 691 | 606
5 | 2.3.2.2.1 | CEG9170000 | Negotiation for Termination of Services - Degassing Column KBG10BY001 (UKA) (Package M130/131/140) | ETN | - | Em andamento | 151 | 606 | CEGLIC0000 | CEG9170100
5 | 2.3.2.2.2 | CEG9170100 | Mobilization of the Component Assembler - Degassing Column KBG10BY001 (UKA) (Package M130/131/140) | EPC | 1 | 152 | 152 | 606 | CEG9170000, CEG6680000 | CEG9180000
5 | 2.3.2.2.3 | CEG9180000 | Fabrication of Degassing Column KBG10BY001 (UKA) (Package M130/131/140) | EPC | 540 | 152 | 691 | 606 | CEG9170100 | CEG2016000
5 | 2.3.2.2.4 | CEG2016000 | CIP Delivery Degassing Column KBG10BY001 (UKA) (Package M130/131/140) | EPC | - | - | 691 | 606 | CEG9180000 | CEG2115000, CEG2125000, CEG2130000, CEG2140000
4 | 2.3.2.3 | - | M603 Hybrid Bed Filters |  | 150 | 392 | 541 | 309
5 | 2.3.2.3.1 | CEG9200000 | Fabrication - Hybrid Bed Filters GDF01/ 11BT001 (UKA) (Package M603) (2nd Stage) | EPC | 150 | 392 | 541 | 309 | CEG9190000, CEG6680000 | CEG2014000
5 | 2.3.2.3.2 | CEG2014000 | CIP Delivery Hybrid Bed Filters GDF01/ 11BT001 (UKA) (Package M603) (2nd Stage) | EPC | - | - | 541 | 309 | CEG9200000 | CEG2090000
3 | 2.3.3 | - | Procurement of Fuel Elements |  | 1241 | 413 | 1653 | 0
4 | 2.3.3.1 | CEG9274100 | Signing of the Contract for the Fabrication of Fuel Elements | EPC | - | - | 413 | 0 | CEGLIC0000 | CEG9274200
4 | 2.3.3.2 | CEG9274200 | Production of Uranium Concentrate | ETN | 600 | 414 | 1013 | 0 | CEG9274100 | CEG9274300
4 | 2.3.3.3 | CEG9274300 | Conversion of Uranium Concentrate to Uranium Hexafluoride | ETN | 390 | 1014 | 1403 | 0 | CEG9274200 | CEG9274400
4 | 2.3.3.4 | CEG9274400 | Isotopic Enrichment | ETN | 210 | 1404 | 1613 | 0 | CEG9274300 | CEG9274500
4 | 2.3.3.5 | CEG9274500 | Nuclear Fuel Fabrication | ETN | 40 | 1614 | 1653 | 0 | CEG9274400 | CEG1650000
2 | 2.4 | - | Procurement (UBA / UBP / ULB / Transformers) |  | - | Anterior ao EPC | 501 | 951
3 | 2.4.1 | - | Procurement of Equipment and Materials |  | - | Anterior ao EPC | 501 | 951
4 | 2.4.1.1 | CEG4390000 | CIP Delivery Power Socket Boxes (UBA) (Package E038) | ETN | - | - | Anterior ao EPC | 924 | CEGLIC0000 | CEG4400000, CEG3600000
4 | 2.4.1.2 | CEG4350000 | Delivery FOB FRAMATOME - Reactor Prot (TXS) Cabinets (UBA) (CF: L/M1/M2/L-UBA/N) (FRAMATOME/1850/Lot5/SUP813) | ETN | - | - | Anterior ao EPC | 1994 | CEG1348000 | CEG4370000, CEG5710000
4 | 2.4.1.3 | CEG5480000 | Delivery FOB FRAMATOME - SPPA Cabinets (UBA) (CF: B) (FRAMATOME/8000/Lot4/SUP753B) | ETN | - | - | Anterior ao EPC | 2037 | CEG1348000 | CEG5600000
4 | 2.4.1.4 | CEG3685000 | Delivery FOB FRAMATOME - Main Control Room CW/ Safety Panel (UBA) (FRAMATOME/8000/SUP218) | ETN | - | - | Anterior ao EPC | 901 | CEG1348000 | CEG1441000
4 | 2.4.1.5 | CEG5730000 | Delivery FOB FRAMATOME - SPPA Cabinets (UBA) (CF: V) (FRAMATOME/8000/Lot1/SUP750) | ETN | - | - | Anterior ao EPC | 988 | CEG1348000 | CEG5740000
4 | 2.4.1.6 | CEG5490000 | Delivery FOB FRAMATOME - SPPA Cabinets (UBA) (CF: K3) (FRAMATOME/8000/Lot2/SUP757A) | ETN | - | - | Anterior ao EPC | 1550 | CEG1348000 | CEG5530000
4 | 2.4.1.7 | CEG5470000 | Delivery FOB FRAMATOME - SPPA Cabinets (UBA) (CF: L) (FRAMATOME/8000/Lot4/SUP753A) | ETN | - | - | Anterior ao EPC | 1259 | CEG1348000 | CEG4360000
4 | 2.4.1.8 | CEG3596100 | Negotiation and Delivery of CIP Lots - Power Cables and Accessories (UBA) (Package E012/ Prysmian/ Other Lots) | ETN | 195 | 77 | 271 | 158 | CEGLIC0000 | CEG3610000
4 | 2.4.1.9 | CEG3598000 | CIP Delivery Cable Trays and Accessories (UBA) (Package E013/ Assembler/ 1. lot) | EPC | - | - | 151 | 158 | CEG1343000, CEG1460000, CEG9273815 | CEG1240000, CEG3600000
4 | 2.4.1.10 | CEG4410000 | CIP Delivery Lamps and Luminaires of the Lighting Sys.(UBA) (Package E010/ Assembler) | EPC | - | - | 151 | 583 | CEG1343000, CEG6700000 | CEG4400000
4 | 2.4.1.11 | CEG3705000 | CIP Delivery Ducts/ Ventilation Supports SAC (UBA) (Package M628/ Assembler/ 1. lot) | EPC | - | 152 | - | 438 | CEG1343000, CEG6700000, CEG6700000 | CEG3710000
4 | 2.4.1.12 | CEG5750000 | Delivery to the Construction Site of the Fire Network Pipes (UBA) supplied by the Assembler | EPC | - | - | 201 | 418 | CEG1343000, CEG6700000 | CEG5760000
4 | 2.4.1.13 | CEG2880000 | Delivery FOB FRAMATOME - Emergency Diesel Generators 1/2/3/4XJ (UBP) (FRAMATOME/7350/SUP196) | ETN | - | - | 304 | 490 | CEG1348000 | CEG2890000
4 | 2.4.1.14 | CEG3616000 | Delivery FOB FRAMATOME - Emergency Feeding Pumps A and D (FRAMATOME/4600/SUP147A+D) (ULB) | ETN | - | - | 381 | 342 | CEG1348000 | CEG3490000, CEG3489000
4 | 2.4.1.15 | CEG2940000 | Delivery FOB FRAMATOME - QKA Cold Water System Components (UBP) (FRAMATOME/5670/SUP184B+705) | ETN | - | - | 475 | 196 | CEG1348000 | CEG2950000
4 | 2.4.1.16 | - | M612A Fire Protection System |  | 350 | 152 | 501 | 418
5 | 2.4.1.16.1 | CEG3725000 | Fabrication of Pipes for the Fire Protection Sys. (Pac. M612A) (UBA) | EPC | 350 | 152 | 501 | 418 | CEG3715000, CEG6680000 | CEG3735000
5 | 2.4.1.16.2 | CEG3735000 | CIP Delivery Pipes of the Fire Protection Sys. (Pac. M612A) (UBA) | EPC | - | - | 501 | 418 | CEG3725000 | CEG5760000
2 | 2.5 | - | Procurement (UMA and Other Buildings) |  | - | Em andamento | 1533 | 39
3 | 2.5.1 | - | Procurement of Equipment and Materials |  | - | Em andamento | 1533 | 39
4 | 2.5.1.1 | CEG4295000 | Finalize Fabrication of the MAG 10 Condenser (UMA) (Package M105 / Nuclep / 3. batch) | ETN | - | Em andamento | Anterior ao EPC | 1095 | CEGLIC0000 | CEG4300000, CEG4310000
4 | 2.5.1.2 | CEG9240000 | Negotiation for Return of Services - Moisture Separators LBJ61/ 62 (UMA) (PCT M106/Delp) | ETN | - | Em andamento | 156 | 441 | CEGLIC0000 | CEG9250000
4 | 2.5.1.3 | CEG4300000 | CIP Delivery MAG 10 Condensers (UMA) (Package M105 / Nuclep / 3. lot) | ETN | - | - | Anterior ao EPC | 1095 | CEG4295000 | CEG3087000
4 | 2.5.1.4 | CEG9250000 | Fabrication - Moisture Separators LBJ61/ 62 (UMA) (PCT M106/Delp) | ETN | 750 | 157 | 906 | 441 | CEG9240000 | CEG9250100
4 | 2.5.1.5 | CEG9210000 | Negotiation for Termination of Services - Tanks and Pressure Vessels (Package M116/M119) | EPC | 1 | 172 | 172 | 400 | CEGLIC0000 | CEG9210100
4 | 2.5.1.6 | CEG5070000 | CIP Delivery Materials for Electromechanical Erection (ULD) | EPC | - | - | 181 | 877 | CEG5050000 | CEG3780000
4 | 2.5.1.7 | CEG5210000 | CIP Delivery UZT Materials and Pipe Galleries | EPC | - | - | 402 | 540 | CEG5120000 | CEG5240000
4 | 2.5.1.8 | CEG4310000 | Delivery remaining Components MAG Condensers required after concreting TG Set foundation (UMA) | ETN | - | - | 551 | 409 | CEG3105000, CEG4295000 | CEG3100000
4 | 2.5.1.9 | CEG5110000 | CIP Delivery Materials for Electromechanical Erection (UPC/ UQB) | EPC | - | - | 721 | 159 | CEG5080000 | CEG3260000
4 | 2.5.1.10 | CEG9250100 | CIP Delivery Moisture Separators LBJ61/ 62 (UMA) (PCT M106/Delp) | ETN | - | - | 906 | 441 | CEG9250000 | CEG3120000
4 | 2.5.1.11 | CEG3115000 | Termination of Installation and Approval of Hydrostatic Test of Moisture Separators LBJ61/ 62 (UMA) (PCT M106/Delp) | ETN | - | - | 1116 | 441 | CEG3120000 | CEG4930000
4 | 2.5.1.12 | - | C001 Shielding Doors |  | 519 | 423 | 941 | 158
5 | 2.5.1.12.1 | CEG9270300 | Fabrication C001 - Shielding Doors | EPC | 519 | 423 | 941 | 158 | CEG9270290, CEG6680000 | CEG9270310
5 | 2.5.1.12.2 | CEG9270310 | CIP Delivery C001 - Shielding Doors | EPC | - | - | 941 | 158 | CEG9270300 | CEG4710000
4 | 2.5.1.13 | - | C002 Common Steel Doors |  | 519 | 423 | 941 | 158
5 | 2.5.1.13.1 | CEG9270330 | Fabrication C002 - Common Steel Doors | EPC | 519 | 423 | 941 | 158 | CEG9270320, CEG6680000 | CEG9270340
5 | 2.5.1.13.2 | CEG9270340 | Delivery CIP C002 - Common Steel Doors | EPC | - | - | 941 | 158 | CEG9270330 | CEG4710000
4 | 2.5.1.14 | - | C003 Roulette Type Doors |  | 759 | 63 | 821 | 158
5 | 2.5.1.14.1 | CEG9270350 | Bidding and Hiring C003 - Roulette Type Doors | ETN | 240 | 63 | 302 | 158 | CEG1424010 | CEG9270360
5 | 2.5.1.14.2 | CEG9270360 | Fabrication C003 - Roulette Type Doors | ETN | 519 | 303 | 821 | 158 | CEG9270350 | CEG9270370
5 | 2.5.1.14.3 | CEG9270370 | CIP C003 Delivery - Roulette Type Doors | ETN | - | - | 821 | 158 | CEG9270360 | CEG4710000
4 | 2.5.1.15 | - | E011 Telephone System |  | 150 | 122 | 271 | 583
5 | 2.5.1.15.1 | CEG9271950 | Fabrication E011 - Telephone System Equipment | EPC | 150 | 122 | 271 | 583 | CEG9271940 | CEG9271960
5 | 2.5.1.15.2 | CEG9271960 | CIP Delivery E011 - Telephone System Equipment | EPC | - | - | 271 | 583 | CEG9271950 | CEG4400000
4 | 2.5.1.16 | - | E015 Grounding Material |  | 366 | 346 | 711 | 158
5 | 2.5.1.16.1 | CEG9271970 | Bidding and Hiring E015 - Grounding Material | EPC | 216 | 346 | 561 | 158 | CEG1424010 | CEG9271980
5 | 2.5.1.16.2 | CEG9271980 | Fabrication E015 - Grounding Material | EPC | 150 | 562 | 711 | 158 | CEG9271970 | CEG9271990
5 | 2.5.1.16.3 | CEG9271990 | Delivery CIP E015 - Grounding Material | EPC | - | - | 711 | 158 | CEG9271980 | CEG3600000
4 | 2.5.1.17 | - | E025 Search System - Person |  | 390 | 432 | 821 | 158
5 | 2.5.1.17.1 | CEG9270380 | Bidding and Hiring E025 - Person Search System (GIF.G ACQUISITION) | ETN | 240 | 432 | 671 | 158 | CEG1424010 | CEG9270390
5 | 2.5.1.17.2 | CEG9270390 | Fabrication E025 - Person Search System (GIF.G ACQUISITION) | ETN | 150 | 672 | 821 | 158 | CEG9270380 | CEG9270400
5 | 2.5.1.17.3 | CEG9270400 | CIP Delivery E025 - Person Search System (GIF.G ACQUISITION) | ETN | - | - | 821 | 158 | CEG9270390 | CEG4710000
4 | 2.5.1.18 | - | E026 Radio System |  | 390 | 432 | 821 | 158
5 | 2.5.1.18.1 | CEG9270410 | Bidding and Hiring E026 - Radio System | EPC | 240 | 432 | 671 | 158 | CEG1424010 | CEG9270420
5 | 2.5.1.18.2 | CEG9270420 | Fabrication E026 - Radio System | EPC | 150 | 672 | 821 | 158 | CEG9270410 | CEG9270430
5 | 2.5.1.18.3 | CEG9270430 | CIP Delivery E026 - Radio System | EPC | - | - | 821 | 158 | CEG9270420 | CEG4710000
4 | 2.5.1.19 | - | E028 Distribution Boxes for the Communication System |  | 390 | 432 | 821 | 158
5 | 2.5.1.19.1 | CEG9272000 | Bidding and Hiring E028 - Communication Distribution Boxes and Radio System | EPC | 240 | 432 | 671 | 158 | CEG1424010 | CEG9272010
5 | 2.5.1.19.2 | CEG9272010 | Fabrication E028 - Communication Distribution Boxes and Radio System | EPC | 150 | 672 | 821 | 158 | CEG9272000 | CEG9272020
5 | 2.5.1.19.3 | CEG9272020 | CIP Delivery E028 - Communication Distribution Boxes and Radio System | EPC | - | - | 821 | 158 | CEG9272010 | CEG4710000
4 | 2.5.1.20 | - | E029 Sealing Materials |  | 390 | 322 | 711 | 158
5 | 2.5.1.20.1 | CEG9272030 | Bidding and Hiring E029 - Sealing Materials and Fireproof Gloves | EPC | 240 | 322 | 561 | 158 | CEG1424010 | CEG9272040
5 | 2.5.1.20.2 | CEG9272040 | Fabrication E029 - Sealing Materials and Fireproof Gloves | EPC | 150 | 562 | 711 | 158 | CEG9272030 | CEG9272050
5 | 2.5.1.20.3 | CEG9272050 | CIP Delivery E029 - Sealing Materials and Fireproof Gloves | EPC | - | - | 711 | 158 | CEG9272040 | CEG3600000
4 | 2.5.1.21 | - | E032 Communication Cables |  | 390 | 322 | 711 | 158
5 | 2.5.1.21.1 | CEG9272060 | Bidding and Hiring E032 - Communication Cables | EPC | 240 | 322 | 561 | 158 | CEG1424010 | CEG9272070
5 | 2.5.1.21.2 | CEG9272070 | Fabrication E032 - Communication Cables | EPC | 150 | 562 | 711 | 158 | CEG9272060 | CEG9272080
5 | 2.5.1.21.3 | CEG9272080 | CIP Delivery E032 - Communication Cables | EPC | - | - | 711 | 158 | CEG9272070 | CEG3600000
4 | 2.5.1.22 | - | E034 Installation Materials |  | 390 | 322 | 711 | 158
5 | 2.5.1.22.1 | CEG9272090 | Bidding and Hiring E034 - Installation Materials | EPC | 240 | 322 | 561 | 158 | CEG1424010 | CEG9272100
5 | 2.5.1.22.2 | CEG9272100 | Fabrication E034 - Installation Materials | EPC | 150 | 562 | 711 | 158 | CEG9272090 | CEG9272110
5 | 2.5.1.22.3 | CEG9272110 | CIP Delivery E034 - Installation Materials | EPC | - | - | 711 | 158 | CEG9272100 | CEG3600000
4 | 2.5.1.23 | - | E039B Luminaires and Accessories for External Lighting System |  | 150 | 122 | 271 | 583
5 | 2.5.1.23.1 | CEG9272130 | Fabrication E039B- Accessories for External Lighting System | EPC | 150 | 122 | 271 | 583 | CEG9272120 | CEG9272140
5 | 2.5.1.23.2 | CEG9272140 | CIP Delivery E039B- Accessories for External Lighting System | EPC | - | - | 271 | 583 | CEG9272130 | CEG4400000
4 | 2.5.1.24 | - | E052 Engine Test Bench |  | 390 | 2 | 391 | 692
5 | 2.5.1.24.1 | CEG9270190 | Bidding and Hiring E052 - Engine Test Bench | ETN | 240 | 2 | 241 | 692 | CEG1424010 | CEG9270180
5 | 2.5.1.24.2 | CEG9270180 | Fabrication E052 - Engine Test Bench | ETN | 150 | 242 | 391 | 692 | CEG9270190 | CEG9270170
5 | 2.5.1.24.3 | CEG9270170 | CIP Delivery E052 - Engine Test Bench | ETN | - | - | 391 | 692 | CEG9270180 | CEG3330000
4 | 2.5.1.25 | - | E060 Greenhouses, benches, etc. |  | 390 | 2 | 391 | 692
5 | 2.5.1.25.1 | CEG9270440 | Bidding and Hiring E060 - Greenhouses, Benches | ETN | 240 | 2 | 241 | 692 | CEG1424010 | CEG9270450
5 | 2.5.1.25.2 | CEG9270450 | Fabrication E060 - Greenhouses, Benches | ETN | 150 | 242 | 391 | 692 | CEG9270440 | CEG9270460
5 | 2.5.1.25.3 | CEG9270460 | CIP Delivery E060 - Greenhouses, Benches | ETN | - | - | 391 | 692 | CEG9270450 | CEG3330000
4 | 2.5.1.26 | - | E065 Remote Transmission Unit |  | 390 | 432 | 821 | 158
5 | 2.5.1.26.1 | CEG9270470 | Bidding and Hiring E065 - Remote Terminal Unit | ETN | 240 | 432 | 671 | 158 | CEG1424010 | CEG9270480
5 | 2.5.1.26.2 | CEG9270480 | Fabrication E065 - Remote Terminal Unit | ETN | 150 | 672 | 821 | 158 | CEG9270470 | CEG9270490
5 | 2.5.1.26.3 | CEG9270490 | CIP Delivery E065- Remote Terminal Unit | ETN | - | - | 821 | 158 | CEG9270480 | CEG4710000
4 | 2.5.1.27 | - | E070 CCTV for JEB and Radiological Protection |  | 390 | 2 | 391 | 692
5 | 2.5.1.27.1 | CEG9270500 | Bidding and Hiring E070/ E049- CCTV for JEB and Radiological Protection | EPC | 240 | 2 | 241 | 692 | CEG1424010 | CEG9270510
5 | 2.5.1.27.2 | CEG9270510 | Manufacture E070/ E049- CCTV for JEB and Radiological Protection | EPC | 150 | 242 | 391 | 692 | CEG9270500 | CEG9270520
5 | 2.5.1.27.3 | CEG9270520 | CIP Delivery E070/ E049- CCTV for JEB and Radiological Protection | EPC | - | - | 391 | 692 | CEG9270510 | CEG3330000
4 | 2.5.1.28 | - | E104 Line + Equipment for Connection to 138 kV network |  | 390 | 137 | 526 | 278
5 | 2.5.1.28.1 | CEG9270530 | Bidding and Hiring E104/ E105- Line + Equipment for connection to 138 kV and 500 kV networks | EPC | 240 | 137 | 376 | 278 | CEG1424010 | CEG9270540
5 | 2.5.1.28.2 | CEG9270540 | Manufacture E104/ E105- Line + Equipment for connection to 138 kV and 500 kV networks | EPC | 150 | 377 | 526 | 278 | CEG9270530 | CEG9270550
5 | 2.5.1.28.3 | CEG9270550 | CIP Delivery E104/ E105- Line + Equipment for connection to 138 kV and 500 kV networks | EPC | - | - | 526 | 278 | CEG9270540 | CEG4910801
4 | 2.5.1.29 | - | E106 Oscillograph |  | 390 | 432 | 821 | 158
5 | 2.5.1.29.1 | CEG9270560 | Bidding and Hiring E106 - Oscillograph | ETN | 240 | 432 | 671 | 158 | CEG1424010 | CEG9270570
5 | 2.5.1.29.2 | CEG9270570 | Fabrication E106 - Oscillograph | ETN | 150 | 672 | 821 | 158 | CEG9270560 | CEG9270580
5 | 2.5.1.29.3 | CEG9270580 | CIP Delivery E106 - Oscillograph | ETN | - | - | 821 | 158 | CEG9270570 | CEG4710000
4 | 2.5.1.30 | - | GR011 Protective Shutters |  | 150 | 332 | 481 | 331
5 | 2.5.1.30.1 | CEG9272160 | Fabrication GR011 - Protection Shutters | EPC | 150 | 332 | 481 | 331 | CEG9272150, CEG6680000 | CEG9272170
5 | 2.5.1.30.2 | CEG9272170 | CIP Delivery GR011 - Protection Shutters | EPC | - | - | 481 | 331 | CEG9272160 | CEG4050000
4 | 2.5.1.31 | - | GR013B Electric Air Humidifier |  | 150 | 185 | 334 | 516
5 | 2.5.1.31.1 | CEG9272190 | Fabrication GR013B - Air Humidifier | EPC | 150 | 185 | 334 | 516 | CEG9272180, CEG6680000 | CEG9272200
5 | 2.5.1.31.2 | CEG9272200 | CIP Delivery GR013B - Air Humidifier | EPC | - | - | 334 | 516 | CEG9272190 | CEG2710000
4 | 2.5.1.32 | - | GR019 Block Valves |  | 150 | 185 | 334 | 516
5 | 2.5.1.32.1 | CEG9272220 | Fabrication GR019 - Insulation Valves | EPC | 150 | 185 | 334 | 516 | CEG9272210 | CEG9272230
5 | 2.5.1.32.2 | CEG9272230 | CIP Delivery GR019 - Insulation Valves | EPC | - | - | 334 | 516 | CEG9272220 | CEG2710000
4 | 2.5.1.33 | - | GR028A Air Handling Unit - AHU |  | 150 | 185 | 334 | 516
5 | 2.5.1.33.1 | CEG9272250 | Fabrication GR028A - Air Conditioning Unit - AHU | EPC | 150 | 185 | 334 | 516 | CEG9272240, CEG6680000 | CEG9272260
5 | 2.5.1.33.2 | CEG9272260 | CIP Delivery GR028A - Air Conditioning Unit - AHU | EPC | - | - | 334 | 516 | CEG9272250 | CEG2710000
4 | 2.5.1.34 | - | GR028B Air Handling Unit - AHU |  | 150 | 185 | 334 | 516
5 | 2.5.1.34.1 | CEG9272280 | Fabrication GR028B - Structures for AHU's copies | EPC | 150 | 185 | 334 | 516 | CEG9272270, CEG6680000 | CEG9272290
5 | 2.5.1.34.2 | CEG9272290 | CIP Delivery GR028B - Structures for AHU's copies | EPC | - | - | 334 | 516 | CEG9272280 | CEG2710000
4 | 2.5.1.35 | - | GR046 Remote actuation cables for Dampers |  | - | Anterior ao EPC | 334 | 516
5 | 2.5.1.35.1 | CEG9272300 | Biddingr and Hiring GR046 - Remote actuation cables for Dampers [Cancelled] | ETN | - | Anterior ao EPC | 184 | 516 | CEG1424010 | CEG9272310
5 | 2.5.1.35.2 | CEG9272310 | Fabrication GR046 - Remote actuation cables for Dampers | EPC | 150 | 185 | 334 | 516 | CEG9272300 | CEG9272320
5 | 2.5.1.35.3 | CEG9272320 | CIP Delivery GR046 - Remote actuation cables for Dampers | EPC | - | - | 334 | 516 | CEG9272310 | CEG2710000
4 | 2.5.1.36 | - | GR047 Compact Air Conditioner GR47 |  | - | Anterior ao EPC | 334 | 516
5 | 2.5.1.36.1 | CEG9272330 | Bidding and Hiring GR047 - Cooling Units (Self-Contained) | ETN | - | Anterior ao EPC | 184 | 516 | CEG1424010 | CEG9272340
5 | 2.5.1.36.2 | CEG9272340 | Fabrication GR047 - Cooling Units (Self-Contained) | ETN | 150 | 185 | 334 | 516 | CEG9272330, CEG6680000 | CEG9272350
5 | 2.5.1.36.3 | CEG9272350 | CIP Delivery GR047 - Cooling Units (Self-Contained) | ETN | - | - | 334 | 516 | CEG9272340 | CEG2710000
4 | 2.5.1.37 | - | GR200 Temporary Ventilation System ULB |  | 150 | 217 | 366 | 403
5 | 2.5.1.37.1 | CEG9272370 | Fabrication GR200 - Temporary Air Conditioning System - ULB | EPC | 150 | 217 | 366 | 403 | CEG9272360, CEG6680000 | CEG9272380
5 | 2.5.1.37.2 | CEG9272380 | CIP Delivery GR200 - Temporary Air Conditioning System - ULB | EPC | - | - | 366 | 403 | CEG9272370 | CEG5720000
4 | 2.5.1.38 | - | GR201 Temporary Ventilation System UJA/UJB/UKA |  | 150 | 185 | 334 | 516
5 | 2.5.1.38.1 | CEG9272400 | Fabrication GR201 - Temporary Ventilation System (UJA/UJB/UKA) | EPC | 150 | 185 | 334 | 516 | CEG9272390, CEG6680000 | CEG9272410
5 | 2.5.1.38.2 | CEG9272410 | CIP Delivery GR201 - Temporary Ventilation System (UJA/UJB/UKA) | EPC | - | - | 334 | 516 | CEG9272400 | CEG2710000
4 | 2.5.1.39 | - | GR202 Temporary UBA System (FANCOILS, PUMPS...) |  | 150 | 217 | 366 | 403
5 | 2.5.1.39.1 | CEG9272430 | Fabrication GR202 - Temporary Air Conditioning System - UBA | EPC | 150 | 217 | 366 | 403 | CEG9272420, CEG6680000 | CEG9272440
5 | 2.5.1.39.2 | CEG9272440 | CIP Delivery GR202 - Temporary Air Conditioning System - UBA | EPC | - | - | 366 | 403 | CEG9272430 | CEG5720000
4 | 2.5.1.40 | - | I001 Electronic Transmitters |  | 332 | 551 | 882 | 536
5 | 2.5.1.40.1 | CEG9270590 | Bidding and Hiring I001 - Electronic Transmitters (GN System) | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270600
5 | 2.5.1.40.2 | CEG9270600 | Fabrication I001 - Electronic Transmitters (GN System) | EPC | 92 | 791 | 882 | 536 | CEG9270590 | CEG9270610
5 | 2.5.1.40.3 | CEG9270610 | CIP Delivery I001 - Electronic Transmitters (GN System) | EPC | - | - | 882 | 536 | CEG9270600 | CEG3210000
4 | 2.5.1.41 | - | I002 Pressure gauges |  | 332 | 551 | 882 | 536
5 | 2.5.1.41.1 | CEG9270620 | Bidding and Hiring I002 - Pressure gauges (GN System) | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270630
5 | 2.5.1.41.2 | CEG9270630 | Fabrication I002 - Pressure gauges (GN System) | EPC | 92 | 791 | 882 | 536 | CEG9270620 | CEG9270640
5 | 2.5.1.41.3 | CEG9270640 | CIP Delivery I002 - Pressure gauges (GN System) | EPC | - | - | 882 | 536 | CEG9270630 | CEG3210000
4 | 2.5.1.42 | - | I006 Control System (PLC) |  | 423 | 460 | 882 | 536
5 | 2.5.1.42.1 | CEG9270680 | Bidding and Hiring I006 - Control System (PLC) (GN System) | EPC | 240 | 460 | 699 | 536 | CEG1424010 | CEG9270690
5 | 2.5.1.42.2 | CEG9270690 | Fabrication I006 - Control System (PLC) (GN System) | EPC | 183 | 700 | 882 | 536 | CEG9270680 | CEG9270700
5 | 2.5.1.42.3 | CEG9270700 | CIP Delivery I006 - Control System (PLC) (GN System) | EPC | - | - | 882 | 536 | CEG9270690 | CEG3210000
4 | 2.5.1.43 | - | I007 Signal Distribution Module |  | 332 | 551 | 882 | 536
5 | 2.5.1.43.1 | CEG9270710 | Bidding and Hiring I007 - Signal Distribution Module (GN System) | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270720
5 | 2.5.1.43.2 | CEG9270720 | Fabrication I007 - Signal Distribution Module (GN System) | EPC | 92 | 791 | 882 | 536 | CEG9270710 | CEG9270730
5 | 2.5.1.43.3 | CEG9270730 | CIP Delivery I007 - Signal Distribution Module (GN System) | EPC | - | - | 882 | 536 | CEG9270720 | CEG3210000
4 | 2.5.1.44 | - | I009 Electro-electronic Equipment for Commissioning and I&C Cold Workshop |  | 332 | 551 | 882 | 536
5 | 2.5.1.44.1 | CEG9270740 | Bidding and Hiring I009A- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270750
5 | 2.5.1.44.2 | CEG9270770 | Bidding and Hiring I009B- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270780
5 | 2.5.1.44.3 | CEG9270800 | Bidding and Hiring I009C- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270810
5 | 2.5.1.44.4 | CEG9270750 | Fabrication I009A- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | 92 | 791 | 882 | 536 | CEG9270740 | CEG9270760
5 | 2.5.1.44.5 | CEG9270780 | Fabrication I009B- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | 92 | 791 | 882 | 536 | CEG9270770 | CEG9270790
5 | 2.5.1.44.6 | CEG9270810 | Fabrication I009C- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | 92 | 791 | 882 | 536 | CEG9270800 | CEG9270820
5 | 2.5.1.44.7 | CEG9270760 | CIP Delivery I009A- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | - | - | 882 | 536 | CEG9270750 | CEG3210000
5 | 2.5.1.44.8 | CEG9270790 | CIP Delivery I009B - Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | - | - | 882 | 536 | CEG9270780 | CEG3210000
5 | 2.5.1.44.9 | CEG9270820 | CIP Delivery I009C- Electro-electronic Equipment for Commissioning and I&C Cold Workshop | EPC | - | - | 882 | 536 | CEG9270810 | CEG3210000
4 | 2.5.1.45 | - | I003 Orifice Plates |  | 362 | 521 | 882 | 536
5 | 2.5.1.45.1 | CEG9270650 | Bidding and Hiring I003 - Orifice Plates (GN System) | EPC | 240 | 521 | 760 | 536 | CEG1424010 | CEG9270660
5 | 2.5.1.45.2 | CEG9270660 | Fabrication I003 - Orifice Plates (GN System) | EPC | 122 | 761 | 882 | 536 | CEG9270650 | CEG9270670
5 | 2.5.1.45.3 | CEG9270670 | CIP Delivery I003 - Orifice Plates (GN System) | EPC | - | - | 882 | 536 | CEG9270660 | CEG3210000
4 | 2.5.1.46 | - | I010 Pressure Measuring Equipment for Commissioning and I&C Cold Workshop (New Code Value) |  | 332 | 551 | 882 | 536
5 | 2.5.1.46.1 | CEG9270830 | Bidding and Hiring I010 - Pressure Measuring Equipment for Commissioning and I&C Cold Workshop | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270840
5 | 2.5.1.46.2 | CEG9270840 | Fabrication I010 - Pressure Measuring Equipment for Commissioning and I&C Cold Workshop | EPC | 92 | 791 | 882 | 536 | CEG9270830 | CEG9270850
5 | 2.5.1.46.3 | CEG9270850 | CIP Delivery I010 - Pressure Measuring Equipment for Commissioning and I&C Cold Workshop | EPC | - | - | 882 | 536 | CEG9270840 | CEG3210000
4 | 2.5.1.47 | - | I011 Tools for Commissioning and I&C Cold Workshop |  | 362 | 521 | 882 | 536
5 | 2.5.1.47.1 | CEG9270860 | Bidding and Hiring I011 - Tools for Commissioning and I&C Cold Workshop | EPC | 240 | 521 | 760 | 536 | CEG1424010 | CEG9270870
5 | 2.5.1.47.2 | CEG9270870 | Fabrication I011 - Tools for Commissioning and I&C Cold Workshop | EPC | 122 | 761 | 882 | 536 | CEG9270860 | CEG9270880
5 | 2.5.1.47.3 | CEG9270880 | CIP Delivery I011 - Tools for Commissioning and I&C Cold Workshop | EPC | - | - | 882 | 536 | CEG9270870 | CEG3210000
4 | 2.5.1.48 | - | I012 Workbenches for Commissioning and I&C Cold Workshop |  | 332 | 551 | 882 | 536
5 | 2.5.1.48.1 | CEG9270890 | Bidding and Hiring I012 - Workbenches for Commissioning and I&C Cold Workshop | EPC | 240 | 551 | 790 | 536 | CEG1424010 | CEG9270900
5 | 2.5.1.48.2 | CEG9270900 | Fabrication I012 - Workbenches for Commissioning and I&C Cold Workshop | EPC | 92 | 791 | 882 | 536 | CEG9270890 | CEG9270910
5 | 2.5.1.48.3 | CEG9270910 | CIP Delivery I012 - Workbenches for Commissioning and I&C Cold Workshop | EPC | - | - | 882 | 536 | CEG9270900 | CEG3210000
4 | 2.5.1.49 | - | I015 Automation of the Modernization of the Demineralization System |  | 390 | 373 | 762 | 536
5 | 2.5.1.49.1 | CEG9270260 | Bidding and Hiring I015 - Automation of the Modernization of the Demineralization System | EPC | 240 | 373 | 612 | 536 | CEG1424010 | CEG9270270
5 | 2.5.1.49.2 | CEG9270270 | Fabrication I015 - Automation of the Modernization of the Demineralization System | EPC | 150 | 613 | 762 | 536 | CEG9270260 | CEG9270280
5 | 2.5.1.49.3 | CEG9270280 | CIP Delivery I015 - Automation of the Modernization of the Demineralization System | EPC | - | - | 762 | 536 | CEG9270270 | CEG3210000
4 | 2.5.1.50 | - | M102 Heat Exchangers - GR3 |  | 690 | 162 | 851 | 409
5 | 2.5.1.50.1 | CEG9080100 | Mobilization of Services Assembler - Low Pressure Preheaters (A1/A2) LAD51/52BB001 (UMA) (PCT M102) | EPC | 1 | 162 | 162 | 409 | CEG9080000, CEG6700000 | CEG9090000
5 | 2.5.1.50.2 | CEG9090000 | Supply and Fabrication of Low Pressure Preheaters (A1/A2) LAD51/52BB001 (UMA) (PCT M102) | EPC | 690 | 162 | 851 | 409 | CEG9080100 | CEG4330000
5 | 2.5.1.50.3 | CEG4330000 | CIP Delivery Low Pressure Preheaters (A1/A2) LAD51/52BB001 (UMA) (PCT M102) | EPC | - | - | 851 | 409 | CEG9090000 | CEG3100000
4 | 2.5.1.51 | - | M113 Feeding Water Tank |  | 1 | 152 | 152 | 400
5 | 2.5.1.51.1 | CEG3144000 | Mobilization of the Feeding Water Tank Assembler LAA10BB001 (UMA) (Package M113) | EPC | 1 | 152 | 152 | 400 | CEG6700000 | CEG3146000
4 | 2.5.1.52 | - | M116 Sample Collection Tank |  | 240 | 172 | 411 | 400
5 | 2.5.1.52.1 | CEG9210100 | Mobilization of Tank and Pressure Vessel Assembler (Package M116/M119) | EPC | 1 | 172 | 172 | 400 | CEG9210000, CEG6680000 | CEG9220000
5 | 2.5.1.52.2 | CEG9220000 | Fabrication Tanks and Pressure Vessels (Package M116/M119) | EPC | 240 | 172 | 411 | 400 | CEG9210100 | CEG9230000
5 | 2.5.1.52.3 | CEG9230000 | CIP Delivery Tanks and Pressure Vessels (Package M116/M119) | EPC | - | - | 411 | 400 | CEG9220000 | CEG2260000, CEG3180000, CEG2324000, CEG4910600
4 | 2.5.1.53 | - | M161B Waste Transfer Station |  | 150 | 762 | 911 | 541
5 | 2.5.1.53.1 | CEG9270210 | Fabrication M161B _M322_ M333_M334A - Waste Transfer Station/RPV Cover Discs | EPC | 150 | 762 | 911 | 541 | CEG9270200, CEG6680000 | CEG9270220
5 | 2.5.1.53.2 | CEG9270220 | CIP Delivery M161B _M322_ M333_M334A - Waste Transfer Station/RPV Cover Discs | EPC | - | - | 911 | 541 | CEG9270210 | CEG2250000
4 | 2.5.1.54 | - | M174 Water Separator |  | 180 | 732 | 911 | 541
5 | 2.5.1.54.1 | CEG9270930 | Fabrication M174 - Water Separator | EPC | 180 | 732 | 911 | 541 | CEG9270920, CEG6680000 | CEG9270940
5 | 2.5.1.54.2 | CEG9270940 | CIP Delivery M174 - Water Separator | EPC | - | - | 911 | 541 | CEG9270930 | CEG2250000
4 | 2.5.1.55 | - | M176 Decontamination Basins with Agitator |  | 397 | 635 | 1031 | 541
5 | 2.5.1.55.1 | CEG9270960 | Fabrication M176 - Decontamination Basins with Agitator | EPC | 397 | 635 | 1031 | 541 | CEG9270950, CEG6700000 | CEG9270970
5 | 2.5.1.55.2 | CEG9270970 | CIP Delivery M176 - Decontamination Basins with Agitator | EPC | - | - | 1031 | 541 | CEG9270960 | CEG2250000
4 | 2.5.1.56 | - | M181 Tube Covers |  | 150 | 762 | 911 | 541
5 | 2.5.1.56.1 | CEG9272460 | Fabrication M181 - Caps for Tubes | EPC | 150 | 762 | 911 | 541 | CEG9272450 | CEG9272470
5 | 2.5.1.56.2 | CEG9272470 | CIP Delivery M181 - Caps for Tubes | EPC | - | - | 911 | 541 | CEG9272460 | CEG2250000
4 | 2.5.1.57 | - | M191 Hot Laundry |  | 214 | 818 | 1031 | 541
5 | 2.5.1.57.1 | CEG9270990 | Fabrication M191 - Hot Laundry | EPC | 214 | 818 | 1031 | 541 | CEG9270980, CEG6680000 | CEG9271000
5 | 2.5.1.57.2 | CEG9271000 | CIP Delivery M191 - Hot Laundry | EPC | - | - | 1031 | 541 | CEG9270990 | CEG2250000
4 | 2.5.1.58 | - | M192 Cold Workshop |  | 305 | 607 | 911 | 541
5 | 2.5.1.58.1 | CEG9271020 | Fabrication M192 - Cold Workshop | EPC | 305 | 607 | 911 | 541 | CEG9271010, CEG6680000 | CEG9271030
5 | 2.5.1.58.2 | CEG9271030 | CIP Delivery M192 - Cold Workshop | EPC | - | - | 911 | 541 | CEG9271020 | CEG2250000
4 | 2.5.1.59 | - | M193 Hot Workshop |  | 214 | 698 | 911 | 541
5 | 2.5.1.59.1 | CEG9271050 | Fabrication M193 - Hot Workshop | EPC | 214 | 698 | 911 | 541 | CEG9271040, CEG6680000 | CEG9271060
5 | 2.5.1.59.2 | CEG9271060 | CIP Delivery M193 - Hot Workshop | EPC | - | - | 911 | 541 | CEG9271050 | CEG2250000
4 | 2.5.1.60 | - | M194 Commissioning Tools |  | 270 | 292 | 561 | 470
5 | 2.5.1.60.1 | CEG9272480 | Bidding and Hiring M194 - Commissioning Tools | ETN | 240 | 292 | 531 | 470 | CEG1424010 | CEG9272490
5 | 2.5.1.60.2 | CEG9272490 | M194 Fabrication - Commissioning Tools | ETN | 30 | 532 | 561 | 470 | CEG9272480 | CEG9272500
5 | 2.5.1.60.3 | CEG9272500 | CIP Delivery M194 - Commissioning Tools | ETN | - | - | 561 | 470 | CEG9272490 | CEG2324000
4 | 2.5.1.61 | - | M195 Lubricant Warehouse in Use - 4 USU |  | 330 | 582 | 911 | 541
5 | 2.5.1.61.1 | CEG9272510 | Bidding and Hiring M195 - Lubricant Warehouse in Use - 4 USU | ETN | 240 | 582 | 821 | 541 | CEG1424010 | CEG9272520
5 | 2.5.1.61.2 | CEG9272520 | Fabrication M195 - Lubricant Warehouse in Use - 4 USU | ETN | 90 | 822 | 911 | 541 | CEG9272510 | CEG9272530
5 | 2.5.1.61.3 | CEG9272530 | CIP Delivery M195 - Lubricant Warehouse in Use - 4 USU | ETN | - | - | 911 | 541 | CEG9272520 | CEG2250000
4 | 2.5.1.62 | - | M196 Injectors and Sprinklers GN |  | 275 | 637 | 911 | 541
5 | 2.5.1.62.1 | CEG9271080 | Fabrication M196 - GN Injectors and Sprinklers | EPC | 275 | 637 | 911 | 541 | CEG9271070, CEG6680000 | CEG9271090
5 | 2.5.1.62.2 | CEG9271090 | CIP Delivery M196 - GN Injectors and Sprinklers | EPC | - | - | 911 | 541 | CEG9271080 | CEG2250000
4 | 2.5.1.63 | - | M197 Mud Filter GN |  | 515 | 397 | 911 | 541
5 | 2.5.1.63.1 | CEG9271100 | Bidding and Hiring M197 - GN Mud Filter | ETN | 240 | 397 | 636 | 541 | CEG1424010 | CEG9271110
5 | 2.5.1.63.2 | CEG9271110 | Fabrication M197 - GN Mud Filter | ETN | 275 | 637 | 911 | 541 | CEG9271100 | CEG9271120
5 | 2.5.1.63.3 | CEG9271120 | CIP Delivery M197 - GN Mud Filter | ETN | - | - | 911 | 541 | CEG9271110 | CEG2250000
4 | 2.5.1.64 | - | M198 Electrolytic Cell Bank |  | 244 | 668 | 911 | 541
5 | 2.5.1.64.1 | CEG9271140 | Fabrication M198 - Electrolytic Cell Bank | EPC | 244 | 668 | 911 | 541 | CEG9271130, CEG6680000 | CEG9271150
5 | 2.5.1.64.2 | CEG9271150 | CIP Delivery M198 - Electrolytic Cell Bank | EPC | - | - | 911 | 541 | CEG9271140 | CEG2250000
4 | 2.5.1.65 | - | M203 Air Compressors |  | 420 | 612 | 1031 | 541
5 | 2.5.1.65.1 | CEG9270240 | Fabrication M203 - Air Compressors | EPC | 420 | 612 | 1031 | 541 | CEG9270230, CEG6680000 | CEG9270250
5 | 2.5.1.65.2 | CEG9270250 | CIP Delivery M203 - Air Compressors | EPC | - | - | 1031 | 541 | CEG9270240 | CEG2250000
4 | 2.5.1.66 | - | M215 Control Air Compressor |  | 150 | 562 | 711 | 400
5 | 2.5.1.66.1 | CEG9272550 | Fabrication M215 - Control Air Compressors | EPC | 150 | 562 | 711 | 400 | CEG9272540, CEG6680000 | CEG9272560
5 | 2.5.1.66.2 | CEG9272560 | CIP Delivery M215 - Control Air Compressors | EPC | - | - | 711 | 400 | CEG9272550 | CEG1411000
4 | 2.5.1.67 | - | M219 Air Blowers |  | 244 | 788 | 1031 | 541
5 | 2.5.1.67.1 | CEG9271170 | Fabrication M219 - Air Blowers | EPC | 244 | 788 | 1031 | 541 | CEG9271160, CEG6680000 | CEG9271180
5 | 2.5.1.67.2 | CEG9271180 | CIP Delivery M219 - Air Blowers | EPC | - | - | 1031 | 541 | CEG9271170 | CEG2250000
4 | 2.5.1.68 | - | M224 Bitumen Charging Pump |  | 150 | 642 | 791 | 541
5 | 2.5.1.68.1 | CEG9272580 | Fabrication M224 - Bitumen Charging Pump | EPC | 150 | 642 | 791 | 541 | CEG9272570, CEG6680000 | CEG9272590
5 | 2.5.1.68.2 | CEG9272590 | CIP Delivery M224 - Bitumen Charging Pump | EPC | - | - | 791 | 541 | CEG9272580 | CEG6200000
4 | 2.5.1.69 | - | M225 Drainage Pump |  | 390 | 402 | 791 | 541
5 | 2.5.1.69.1 | CEG9272600 | Bidding and Hiring M225 - PEC Drainage Pump | ETN | 240 | 402 | 641 | 541 | CEG1424010 | CEG9272610
5 | 2.5.1.69.2 | CEG9272610 | Fabrication M225 - PEC Drainage Pump | ETN | 150 | 642 | 791 | 541 | CEG9272600 | CEG9272620
5 | 2.5.1.69.3 | CEG9272620 | CIP Delivery M225 - PEC Drainage Pump | ETN | - | - | 791 | 541 | CEG9272610 | CEG6200000
4 | 2.5.1.70 | - | M226 Plastic Pumps GN |  | 275 | 757 | 1031 | 541
5 | 2.5.1.70.1 | CEG9271200 | Fabrication M226 - GN Plastic Pumps | EPC | 275 | 757 | 1031 | 541 | CEG9271190, CEG6680000 | CEG9271210
5 | 2.5.1.70.2 | CEG9271210 | CIP Delivery M226 - GN Plastic Pumps | EPC | - | - | 1031 | 541 | CEG9271200 | CEG2250000
4 | 2.5.1.71 | - | M227 Circulation Pumps GN |  | 275 | 757 | 1031 | 541
5 | 2.5.1.71.1 | CEG9271230 | Fabrication M227 - GN Circulation Pumps | EPC | 275 | 757 | 1031 | 541 | CEG9271220, CEG6680000 | CEG9271240
5 | 2.5.1.71.2 | CEG9271240 | CIP Delivery M227 - NG Circulation Pumps | EPC | - | - | 1031 | 541 | CEG9271230 | CEG2250000
4 | 2.5.1.72 | - | M228 Dosing PumpsGN |  | 275 | 757 | 1031 | 541
5 | 2.5.1.72.1 | CEG9271260 | Fabrication M228 - GN Dosing Pumps | EPC | 275 | 757 | 1031 | 541 | CEG9271250, CEG6680000 | CEG9271270
5 | 2.5.1.72.2 | CEG9271270 | CIP Delivery M228 - GN Dosing Pumps | EPC | - | - | 1031 | 541 | CEG9271260 | CEG2250000
4 | 2.5.1.73 | - | M229 Agitator for the Flocculant Preparation Tank |  | 454 | 108 | 561 | 470
5 | 2.5.1.73.1 | CEG9271280 | Bidding and Hiring M229 - Flocculant Preparation Tank Agitator | ETN | 240 | 108 | 347 | 470 | CEG1424010 | CEG9271290
5 | 2.5.1.73.2 | CEG9271290 | Fabrication M229 - Flocculant Preparation Tank Agitator | ETN | 214 | 348 | 561 | 470 | CEG9271280 | CEG9271300
5 | 2.5.1.73.3 | CEG9271300 | CIP Delivery M229 - Flocculant Preparation Tank Agitator | ETN | - | - | 561 | 470 | CEG9271290 | CEG2324000
4 | 2.5.1.74 | - | M326A Access Doors to the Reactor shaft |  | 390 | 172 | 561 | 470
5 | 2.5.1.74.1 | CEG9272630 | Bidding and Hiring M326A - Access doors to the reactor shaft | ETN | 240 | 172 | 411 | 470 | CEG1424010 | CEG9272640
5 | 2.5.1.74.2 | CEG9272640 | Fabrication M326A - Reactor shaft access doors | ETN | 150 | 412 | 561 | 470 | CEG9272630 | CEG9272650
5 | 2.5.1.74.3 | CEG9272650 | CIP Delivery M326A - Reactor shaft access doors | ETN | - | - | 561 | 470 | CEG9272640 | CEG2324000
4 | 2.5.1.75 | - | M342 Radiation Sample Holder |  | 244 | 626 | 869 | 182
5 | 2.5.1.75.1 | CEG9271410 | Fabrication M342 - Radiation Sample Holder | EPC | 244 | 626 | 869 | 182 | CEG9271400, CEG6680000 | CEG9271420
5 | 2.5.1.75.2 | CEG9271420 | CIP Delivery M342 - Radiation Sample Holder | EPC | - | - | 869 | 182 | CEG9271410 | CEG1760000
4 | 2.5.1.76 | - | M360 Hoists / Trolleys |  | 789 | 745 | 1533 | 4
5 | 2.5.1.76.1 | CEG9271430 | Bidding and Hiring M360 - Hoists / Trolleys | ETN | 240 | 745 | 984 | 4 | CEG1424010 | CEG9271440
5 | 2.5.1.76.2 | CEG9271440 | M360 Fabrication - Hoists / Trolleys | ETN | 549 | 985 | 1533 | 4 | CEG9271430 | CEG9271450
5 | 2.5.1.76.3 | CEG9271450 | CIP Delivery M360 - Hoists / Trolleys | ETN | - | - | 1533 | 4 | CEG9271440 | CEG1311000
4 | 2.5.1.77 | - | M380 Component/Pipe Identification System |  | 150 | 92 | 241 | 124
5 | 2.5.1.77.1 | CEG9272670 | Fabrication M380 - Components/Pipe Identification System | EPC | 150 | 92 | 241 | 124 | CEG9272660 | CEG9272680
5 | 2.5.1.77.2 | CEG9272680 | CIP Delivery M380 - Components/Pipe Identification System | EPC | - | - | 241 | 124 | CEG9272670 | CEG1860000
4 | 2.5.1.78 | - | M383 Metal Covers - Agitators |  | 390 | 257 | 646 | 606
5 | 2.5.1.78.1 | CEG9272690 | Bidding and Hiring M383 - Metal Covers - Agitators | ETN | 240 | 257 | 496 | 606 | CEG1424010 | CEG9272700
5 | 2.5.1.78.2 | CEG9272700 | Fabrication M383 - Metal Covers - Agitators | ETN | 150 | 497 | 646 | 606 | CEG9272690 | CEG9272710
5 | 2.5.1.78.3 | CEG9272710 | Delivery CIP M383 - Metal Covers - Agitators | ETN | - | - | 646 | 606 | CEG9272700 | CEG5390000
4 | 2.5.1.79 | - | M400 Drainage Boxes / Drains |  | 150 | 301 | 450 | 395
5 | 2.5.1.79.1 | CEG9273690 | Fabrication M400 - Polypropylene Drainage Boxes - Embedded Parts 1st Stage (UJA/UJB/UKA) | EPC | 150 | 301 | 450 | 395 | CEG9273680 | CEG9273700
5 | 2.5.1.79.2 | CEG9273700 | CIP Delivery M400 - Polypropylene Draiagen Boxes - Embedded Parts 1st Stage (UJA/UJB/UKA) | EPC | - | - | 450 | 395 | CEG9273690 | CEG2821000
4 | 2.5.1.80 | - | M401 Rectangular Ferritic Lugs |  | 150 | 283 | 432 | 540
5 | 2.5.1.80.1 | CEG9271470 | Fabrication M401/420B – Ferritic Lugs and Special Parts | EPC | 150 | 283 | 432 | 540 | CEG9271460, CEG6700000 | CEG9271480
5 | 2.5.1.80.2 | CEG9271480 | CIP Delivery M401 / 420B - Ferritic Lugs and Special Parts | EPC | - | - | 432 | 540 | CEG9271470 | CEG5230000
4 | 2.5.1.81 | - | M403 Containment Discs in FRP |  | 120 | 193 | 312 | 540
5 | 2.5.1.81.1 | CEG9272730 | Fabrication M403 - FRP Containment Discs | EPC | 120 | 193 | 312 | 540 | CEG9272720 | CEG9272740
5 | 2.5.1.81.2 | CEG9272740 | CIP Delivery M403 - FRP Containment Discs | EPC | - | - | 312 | 540 | CEG9272730 | CEG5230000
4 | 2.5.1.82 | - | M404 Galvanized Piping |  | 150 | 2 | 151 | 403
5 | 2.5.1.82.1 | CEG9271800 | Fabrication M404 - Galvanized Piping | EPC | 150 | 2 | 151 | 403 | CEG9271790 | CEG9271810
5 | 2.5.1.82.2 | CEG9271810 | CIP Delivery M404 - Galvanized Piping | EPC | - | - | 151 | 403 | CEG9271800 | CEG5720000
4 | 2.5.1.83 | - | M405 Cast Iron Piping |  | 150 | 2 | 151 | 403
5 | 2.5.1.83.1 | CEG9271500 | Fabrication M405 - Cast Iron Piping | EPC | 150 | 2 | 151 | 403 | CEG9271490 | CEG9271510
5 | 2.5.1.83.2 | CEG9271510 | CIP Delivery M405 - Cast Iron Piping | EPC | - | - | 151 | 403 | CEG9271500 | CEG5720000
4 | 2.5.1.84 | - | M413 Miscellaneous (Miscellaneous Materials) |  | 270 | 72 | 341 | 441
5 | 2.5.1.84.1 | CEG9272760 | Fabrication M413 - Miscellaneous Materials | EPC | 270 | 72 | 341 | 441 | CEG9272750 | CEG9272770
5 | 2.5.1.84.2 | CEG9272770 | CIP Delivery M413 - MiscellaneousMaterials | EPC | - | - | 341 | 441 | CEG9272760 | CEG4910000
4 | 2.5.1.85 | - | M420A Welded Piping - ESPES |  | 400 | 272 | 671 | 441
5 | 2.5.1.85.1 | CEG5839000 | Fabrication of PAB-UMA-Fuzi-Tec Pipings (Package M420A / M497) | EPC | 400 | 272 | 671 | 441 | CEGLIC0000, CEG6700000 | CEG5840000
5 | 2.5.1.85.2 | CEG5840000 | CIP Delivery PAB-UMA-Fuzi-Tec Pipings (Package M420A / M497) | EPC | - | - | 671 | 441 | CEGLIC0000, CEG5839000 | CEG4900000
4 | 2.5.1.86 | - | M432A Screws, Nuts and Bolts on RCD5 |  | 31 | 121 | 151 | 403
5 | 2.5.1.86.1 | CEG9272790 | Fabrication M432A - Screws, Nuts and Bolts in RCD5 | EPC | 31 | 121 | 151 | 403 | CEG9272780 | CEG9272800
5 | 2.5.1.86.2 | CEG9272800 | CIP Delivery M432A - Screws, Nuts and Bolts on RCD5 | EPC | - | - | 151 | 403 | CEG9272790 | CEG5720000
4 | 2.5.1.87 | - | M434B Piping in PVC + GRP |  | 150 | 2 | 151 | 403
5 | 2.5.1.87.1 | CEG9272820 | Fabrication M434B - RPVC Piping (PVC+PRFV) | EPC | 150 | 2 | 151 | 403 | CEG9272810 | CEG9272830
5 | 2.5.1.87.2 | CEG9272830 | CIP Delivery M434B - RPVC piping (PVC+PRFV) | EPC | - | - | 151 | 403 | CEG9272820 | CEG5720000
4 | 2.5.1.88 | - | M434C PRFC piping |  | 150 | 2 | 151 | 403
5 | 2.5.1.88.1 | CEG9272850 | Fabrication M434C - GRP Piping | EPC | 150 | 2 | 151 | 403 | CEG9272840 | CEG9272860
5 | 2.5.1.88.2 | CEG9272860 | CIP Delivery M434C - GRP Piping | EPC | - | - | 151 | 403 | CEG9272850 | CEG5720000
4 | 2.5.1.89 | - | M436 Polyethylene Piping |  | 150 | 2 | 151 | 403
5 | 2.5.1.89.1 | CEG9272910 | Fabrication M436 - Polyethylene Piping | EPC | 150 | 2 | 151 | 403 | CEG9272900 | CEG9272920
5 | 2.5.1.89.2 | CEG9272920 | CIP Delivery M436 - Polyethylene Piping | EPC | - | - | 151 | 403 | CEG9272910 | CEG5720000
4 | 2.5.1.90 | - | M437 PVC piping |  | 150 | 2 | 151 | 403
5 | 2.5.1.90.1 | CEG9271830 | Fabrication M437 - PVC Piping | EPC | 150 | 2 | 151 | 403 | CEG9271820 | CEG9271840
5 | 2.5.1.90.2 | CEG9271840 | CIP Delivery M437 - PVC Piping | EPC | - | - | 151 | 403 | CEG9271830 | CEG5720000
4 | 2.5.1.91 | - | M438 Copper Tubing |  | 120 | 222 | 341 | 441
5 | 2.5.1.91.1 | CEG9272880 | Fabrication M438 - Copper Piping | EPC | 120 | 222 | 341 | 441 | CEG9272870 | CEG9272890
5 | 2.5.1.91.2 | CEG9272890 | CIP Delivery M438 - Copper Piping | EPC | - | - | 341 | 441 | CEG9272880 | CEG4910000
4 | 2.5.1.92 | - | M440Embedded Parts for PAB/UMA |  | 150 | 2 | 151 | 124
5 | 2.5.1.92.1 | CEG9273720 | Fabrication M440 - Embedded Parts for PAB/UMA | EPC | 150 | 2 | 151 | 124 | CEG9273710 | CEG9273730
5 | 2.5.1.92.2 | CEG9273730 | CIP Delivery M440 - Embedded Parts for PAB/UMA | EPC | - | - | 151 | 124 | CEG9273720 | CEG4913600
4 | 2.5.1.93 | - | M441 Embedded Parts for PAB/UPC |  | 270 | 362 | 631 | 124
5 | 2.5.1.93.1 | CEG9273750 | Fabrication M441 - Embedded Parts for PAB/UPC | EPC | 270 | 362 | 631 | 124 | CEG9273740 | CEG9273760
5 | 2.5.1.93.2 | CEG9273760 | CIP Delivery M441 - Embedded Parts for PAB/UPC | EPC | - | - | 631 | 124 | CEG9273750 | CEG4913610
4 | 2.5.1.94 | - | M480C Fireproof Gloves |  | 181 | 201 | 381 | 418
5 | 2.5.1.94.1 | CEG9272940 | Fabrication M480C - Fireproof Gloves | EPC | 181 | 201 | 381 | 418 | CEG9272930 | CEG9272950
5 | 2.5.1.94.2 | CEG9272950 | CIP Delivery M480C - Fireproof Gloves | EPC | - | - | 381 | 418 | CEG9272940 | CEG5770000
4 | 2.5.1.95 | - | M491A Special Foundations |  | 125 | 217 | 341 | 441
5 | 2.5.1.95.1 | CEG9272970 | Fabrication M491A - Special Foundations for Cold Lines and PVC/FRP | EPC | 125 | 217 | 341 | 441 | CEG9272960 | CEG9272980
5 | 2.5.1.95.2 | CEG9272980 | CIP Delivery M491A - Special Foundations for Cold Lines and PVC/FRP | EPC | - | - | 341 | 441 | CEG9272970 | CEG4910000
4 | 2.5.1.96 | - | M492 CPT Fixed Points |  | 150 | 419 | 568 | 682
5 | 2.5.1.96.1 | CEG9271530 | Fabrication M492 - Fixed Points of Containment Penetrations | EPC | 150 | 419 | 568 | 682 | CEG9271520, CEG6700000 | CEG9271540
5 | 2.5.1.96.2 | CEG9271540 | CIP Delivery M492 - Fixed Points of Containment Penetrations | EPC | - | - | 568 | 682 | CEG9271530 | CEG1420000
4 | 2.5.1.97 | - | M495 Miscellaneous Supports |  | 150 | 192 | 341 | 441
5 | 2.5.1.97.1 | CEG9273000 | Fabrication M495 - Miscellaneous Supports | EPC | 150 | 192 | 341 | 441 | CEG9272990 | CEG9273010
5 | 2.5.1.97.2 | CEG9273010 | Delivery CIP M495 - Miscellaneous Supports | EPC | - | - | 341 | 441 | CEG9273000 | CEG4910000
4 | 2.5.1.98 | - | M502 External Hydrants |  | 150 | 292 | 441 | 418
5 | 2.5.1.98.1 | CEG9273030 | Fabrication M502 - External Fire Valves | EPC | 150 | 292 | 441 | 418 | CEG9273020 | CEG9273040
5 | 2.5.1.98.2 | CEG9273040 | CIP Delivery M502 - External Fire Valves | EPC | - | - | 441 | 418 | CEG9273030 | CEG1016140
4 | 2.5.1.99 | - | M503 Type 164 Flow Displays |  | 150 | 292 | 441 | 418
5 | 2.5.1.99.1 | CEG9273060 | Fabrication M503 - Type 164 Flow Displays | EPC | 150 | 292 | 441 | 418 | CEG9273050 | CEG9273070
5 | 2.5.1.99.2 | CEG9273070 | CIP Delivery M503 - Type 164 Flow Displays | EPC | - | - | 441 | 418 | CEG9273060 | CEG1016140
4 | 2.5.1.100 | - | M505 Filters Type 193 |  | 150 | 292 | 441 | 418
5 | 2.5.1.100.1 | CEG9273090 | Fabrication M505 - Type 193 Filters | EPC | 150 | 292 | 441 | 418 | CEG9273080 | CEG9273100
5 | 2.5.1.100.2 | CEG9273100 | CIP Delivery M505 - Type 193 Filters | EPC | - | - | 441 | 418 | CEG9273090 | CEG1016140
4 | 2.5.1.101 | - | M506 RC5 Globe Valves |  | 150 | 292 | 441 | 418
5 | 2.5.1.101.1 | CEG9273120 | Fabrication M506 - Globe and Check Valves - RC5 | EPC | 150 | 292 | 441 | 418 | CEG9273110 | CEG9273130
5 | 2.5.1.101.2 | CEG9273130 | CIP Delivery M506 - Globe and Check Valves - RC5 | EPC | - | - | 441 | 418 | CEG9273120 | CEG1016140
4 | 2.5.1.102 | - | M507 Internal Hydrants |  | 150 | 232 | 381 | 418
5 | 2.5.1.102.1 | CEG9273150 | Fabrication M507 - Internal Fire Valves | EPC | 150 | 232 | 381 | 418 | CEG9273140 | CEG9273160
5 | 2.5.1.102.2 | CEG9273160 | CIP Delivery M507 - Internal Fire Valves | EPC | - | - | 381 | 418 | CEG9273150 | CEG5770000
4 | 2.5.1.103 | - | M508A Diaphragm Valves |  | 150 | 292 | 441 | 418
5 | 2.5.1.103.1 | CEG9273180 | Fabrication M508A - Diaphragm Valves | EPC | 150 | 292 | 441 | 418 | CEG9273170 | CEG9273190
5 | 2.5.1.103.2 | CEG9273190 | CIP Delivery M508A - Diaphragm Valves | EPC | - | - | 441 | 418 | CEG9273180 | CEG1016140
4 | 2.5.1.104 | - | M508B Ball Valves |  | 150 | 292 | 441 | 418
5 | 2.5.1.104.1 | CEG9273210 | Fabrication M508B - Ball Valves | EPC | 150 | 292 | 441 | 418 | CEG9273200 | CEG9273220
5 | 2.5.1.104.2 | CEG9273220 | CIP Delivery M508B - Ball Valves | EPC | - | - | 441 | 418 | CEG9273210 | CEG1016140
4 | 2.5.1.105 | - | M514B Hoses |  | 150 | 292 | 441 | 418
5 | 2.5.1.105.1 | CEG9273240 | Fabrication M514B - Hoses | EPC | 150 | 292 | 441 | 418 | CEG9273230 | CEG9273250
5 | 2.5.1.105.2 | CEG9273250 | CIP Delivery M514B - Hoses | EPC | - | - | 441 | 418 | CEG9273240 | CEG1016140
4 | 2.5.1.106 | - | M514C Flexible Metal Pipes |  | 150 | 192 | 341 | 441
5 | 2.5.1.106.1 | CEG9273270 | Fabrication M514C - Flexible Metal Pipes | EPC | 150 | 192 | 341 | 441 | CEG9273260 | CEG9273280
5 | 2.5.1.106.2 | CEG9273280 | CIP Delivery M514C - Flexible Metal Pipes | EPC | - | - | 341 | 441 | CEG9273270 | CEG4910000
4 | 2.5.1.107 | - | M514D Couplings |  | 150 | 171 | 320 | 872
5 | 2.5.1.107.1 | CEG9273300 | M514D Fabrication - Couplings | EPC | 150 | 171 | 320 | 872 | CEG9273290 | CEG9273310
5 | 2.5.1.107.2 | CEG9273310 | CIP Delivery M514D - Couplings | EPC | - | - | 320 | 872 | CEG9273300 | CEG3740000
4 | 2.5.1.108 | - | M514E Ball Valves |  | 150 | 171 | 320 | 872
5 | 2.5.1.108.1 | CEG9273330 | Fabrication M514E - Ball Valves for Compressed Air | EPC | 150 | 171 | 320 | 872 | CEG9273320 | CEG9273340
5 | 2.5.1.108.2 | CEG9273340 | CIP Delivery M514E - Ball Valves for Compressed Air | EPC | - | - | 320 | 872 | CEG9273330 | CEG3740000
4 | 2.5.1.109 | - | M514F Transition Parts and Coupling. |  | 150 | 171 | 320 | 872
5 | 2.5.1.109.1 | CEG9273360 | Fabrication M514F - Transition Parts for Couplings | EPC | 150 | 171 | 320 | 872 | CEG9273350 | CEG9273370
5 | 2.5.1.109.2 | CEG9273370 | CIP Delivery M514F - Transition Parts for Couplings | EPC | - | - | 320 | 872 | CEG9273360 | CEG3740000
4 | 2.5.1.110 | - | M514H PVC Y Filters |  | 150 | 171 | 320 | 872
5 | 2.5.1.110.1 | CEG9273390 | Fabrication M514H - PVC Y Filters for QUP System | EPC | 150 | 171 | 320 | 872 | CEG9273380 | CEG9273400
5 | 2.5.1.110.2 | CEG9273400 | CIP Delivery M514H - PVC Y Filters for QUP System | EPC | - | - | 320 | 872 | CEG9273390 | CEG3740000
4 | 2.5.1.111 | - | M515 Type 356 Diaphragm Valves |  | 150 | 171 | 320 | 872
5 | 2.5.1.111.1 | CEG9273420 | Fabrication M515 - Type 356 Diaphragm Valves | EPC | 150 | 171 | 320 | 872 | CEG9273410 | CEG9273430
5 | 2.5.1.111.2 | CEG9273430 | CIP Delivery M515 - Type 356 Diaphragm Valves | EPC | - | - | 320 | 872 | CEG9273420 | CEG3740000
4 | 2.5.1.112 | - | M516 Vertical Check Valves |  | 150 | 171 | 320 | 872
5 | 2.5.1.112.1 | CEG9273450 | Fabrication M516 - Vertical Check Valves | EPC | 150 | 171 | 320 | 872 | CEG9273440 | CEG9273460
5 | 2.5.1.112.2 | CEG9273460 | CIP Delivery M516 - Vertical Check Valves | EPC | - | - | 320 | 872 | CEG9273450 | CEG3740000
4 | 2.5.1.113 | - | M517 Solenoid Valves |  | 150 | 171 | 320 | 872
5 | 2.5.1.113.1 | CEG9273480 | Fabrication M517 - Solenoid Valves in Box | EPC | 150 | 171 | 320 | 872 | CEG9273470 | CEG9273490
5 | 2.5.1.113.2 | CEG9273490 | CIP Delivery M517 - Solenoid Valves in Box | EPC | - | - | 320 | 872 | CEG9273480 | CEG3740000
4 | 2.5.1.114 | - | M518A Electric Heaters |  | 150 | 171 | 320 | 872
5 | 2.5.1.114.1 | CEG9273510 | Fabrication M518A - Electric Heaters - Boilers | EPC | 150 | 171 | 320 | 872 | CEG9273500, CEG6680000 | CEG9273520
5 | 2.5.1.114.2 | CEG9273520 | CIP Delivery M518A - Electric Heaters - Boilers | EPC | - | - | 320 | 872 | CEG9273510 | CEG3740000
4 | 2.5.1.115 | - | M518B Building/ Globe Valves |  | 150 | 171 | 320 | 872
5 | 2.5.1.115.1 | CEG9273540 | Fabrication M518B - Globe and Gate Building Valves | EPC | 150 | 171 | 320 | 872 | CEG9273530 | CEG9273550
5 | 2.5.1.115.2 | CEG9273550 | CIP Delivery M518B - Globe and Gate Building Valves | EPC | - | - | 320 | 872 | CEG9273540 | CEG3740000
4 | 2.5.1.116 | - | M519 Vacuum Breaker Valves |  | 150 | 171 | 320 | 872
5 | 2.5.1.116.1 | CEG9273570 | Fabrication M519 - Vacuum Breaker Valves | EPC | 150 | 171 | 320 | 872 | CEG9273560 | CEG9273580
5 | 2.5.1.116.2 | CEG9273580 | CIP Delivery M519 - Vacuum Breaker Valves | EPC | - | - | 320 | 872 | CEG9273570 | CEG3740000
4 | 2.5.1.117 | - | M521 Type 288 Flow Restrictor |  | 150 | 171 | 320 | 872
5 | 2.5.1.117.1 | CEG9273600 | Fabrication M521 - Type 288 Flow Restrictor | EPC | 150 | 171 | 320 | 872 | CEG9273590 | CEG9273610
5 | 2.5.1.117.2 | CEG9273610 | CIP Delivery M521 - Type 288 Flow Restrictor | EPC | - | - | 320 | 872 | CEG9273600 | CEG3740000
4 | 2.5.1.118 | - | M607A Interconnection Ducts between UKA and UKH |  | 336 | 456 | 791 | 541
5 | 2.5.1.118.1 | CEG9271560 | Fabrication M607A - Interconnection Ducts between UKA and UKH | EPC | 336 | 456 | 791 | 541 | CEG9271550 | CEG9271570
5 | 2.5.1.118.2 | CEG9271570 | CIP Delivery M607A - Interconnection Ducts between UKA and UKH | EPC | - | - | 791 | 541 | CEG9271560 | CEG6200000
4 | 2.5.1.119 | - | M607B Gratings and Diffusers for Nuclear Buildings |  | 197 | 145 | 341 | 441
5 | 2.5.1.119.1 | CEG9271860 | Fabrication M607B - Gratings and Diffusers for Nuclear Buildings | EPC | 197 | 145 | 341 | 441 | CEG9271850 | CEG9271870
5 | 2.5.1.119.2 | CEG9271870 | Delivery CIP M607B - Gratings and Diffusers for Nuclear Buildings | EPC | - | - | 341 | 441 | CEG9271860 | CEG4910000
4 | 2.5.1.120 | - | M607C Metal profiles and sheets for component fixing structure |  | 150 | 192 | 341 | 441
5 | 2.5.1.120.1 | CEG9271920 | Fabrication M607C - Metal profiles and sheets for component fixing structure | EPC | 150 | 192 | 341 | 441 | CEG9271910 | CEG9271930
5 | 2.5.1.120.2 | CEG9271930 | CIP Delivery M607C - Metal profiles and sheets for Component fixing structure | EPC | - | - | 341 | 441 | CEG9271920 | CEG4910000
4 | 2.5.1.121 | - | M608A Gratings and Diffusers for Conventional Buildings (except UBA) |  | 150 | 72 | 221 | 441
5 | 2.5.1.121.1 | CEG9271890 | Fabrication M608A - UBA Gratings and Diffusers | EPC | 150 | 72 | 221 | 441 | CEG9271880 | CEG9271900
5 | 2.5.1.121.2 | CEG9271900 | CIP Delivery M608A - UBA Gratings and Diffusers | EPC | - | - | 221 | 441 | CEG9271890 | CEG4910000
4 | 2.5.1.122 | - | M608B UBA Building Gratings and Diffusers |  | 150 | 192 | 341 | 441
5 | 2.5.1.122.1 | CEG9273630 | Fabrication M608B - UBA Building Gratings and Diffusers | EPC | 150 | 192 | 341 | 441 | CEG9273620 | CEG9273640
5 | 2.5.1.122.2 | CEG9273640 | CIP Delivery M608B - UBA Building Gratings and Diffusers | EPC | - | - | 341 | 441 | CEG9273630 | CEG4910000
4 | 2.5.1.123 | - | M613 Manual Fire Extinguishers |  | 367 | 195 | 561 | 418
5 | 2.5.1.123.1 | CEG9271590 | Fabrication M613 - Manual Fire Extinguishers | EPC | 367 | 195 | 561 | 418 | CEG9271580 | CEG9271600
5 | 2.5.1.123.2 | CEG9271600 | CIP Delivery M613 - Manual Fire Extinguishers | EPC | - | - | 561 | 418 | CEG9271590 | CEG1016140
4 | 2.5.1.124 | - | M617A Cold Laboratory Furniture |  | 423 | 849 | 1271 | 158
5 | 2.5.1.124.1 | CEG9271610 | Bidding and Hiring M617A - Cold Laboratory Furniture | ETN | 240 | 849 | 1088 | 158 | CEG1424010 | CEG9271620
5 | 2.5.1.124.2 | CEG9271620 | Fabrication M617A - Cold Laboratory Furniture | ETN | 183 | 1089 | 1271 | 158 | CEG9271610 | CEG9271630
5 | 2.5.1.124.3 | CEG9271630 | CIP Delivery M617A - Cold Laboratory Furniture | ETN | - | - | 1271 | 158 | CEG9271620 | CEG4710000
4 | 2.5.1.125 | - | M617C Reagents and Glassware |  | 393 | 879 | 1271 | 158
5 | 2.5.1.125.1 | CEG9271640 | Bidding and Hiring M617C - Reagents and Glassware | ETN | 240 | 879 | 1118 | 158 | CEG1424010 | CEG9271650
5 | 2.5.1.125.2 | CEG9271650 | Fabrication M617C - Reagents and Glassware | ETN | 153 | 1119 | 1271 | 158 | CEG9271640 | CEG9271660
5 | 2.5.1.125.3 | CEG9271660 | CIP Delivery M617C - Reagents and Glassware | ETN | - | - | 1271 | 158 | CEG9271650 | CEG4710000
4 | 2.5.1.126 | - | M620 Oil Separator |  | 184 | 566 | 749 | 182
5 | 2.5.1.126.1 | CEG9271680 | Fabrication M620 - Oil Separator | EPC | 184 | 566 | 749 | 182 | CEG9271670, CEG6680000 | CEG9271690
5 | 2.5.1.126.2 | CEG9271690 | CIP Delivery M620 - Oil Separator | EPC | - | - | 749 | 182 | CEG9271680 | CEG1760000
4 | 2.5.1.127 | - | M626 Embedded Parts 1st. Stage |  | 2 | 151 | 152 | 0
5 | 2.5.1.127.1 | CEG9273790 | CIP Delivery M626 - Embedded Parts 1st Stage Ventilation (UJA/UJB/UKA) | EPC | - | - | 151 | 0 | CEG9273780 | CEG1370000, CEG1370100, CEG1370100PL
5 | 2.5.1.127.2 | CEG9273780 | Fabrication M626 - Embedded Parts 1st Stage Ventilation (UJA/UJB/UKA) | EPC | 1 | 152 | 152 | 0 | CEG9273770 | CEG9273790
4 | 2.5.1.128 | - | M627 Ducts, Supports, Insulation/Nuclear Area |  | 150 | 10 | 159 | 322
5 | 2.5.1.128.1 | CEG9273660 | Fabrication M627 /M628 - Plates, Profiles and Tubes, Threaded Bar, Seals, Accessories for Ducts and Supports | EPC | 150 | 10 | 159 | 322 | CEGLIC0000 | CEG9273670
5 | 2.5.1.128.2 | CEG9273670 | CIP Delivery M627 /M628 - Plates, Profiles and Tubes, Threaded Bar, Seals, Duct Accessories and Supports | EPC | - | - | 159 | 322 | CEG9273660 | CEG2590000
4 | 2.5.1.129 | - | M701 Consumables for Commissioning |  | 393 | 879 | 1271 | 158
5 | 2.5.1.129.1 | CEG9271700 | Bidding and Hiring M701 - Consumables for Commissioning | ETN | 240 | 879 | 1118 | 158 | CEG1424010 | CEG9271710
5 | 2.5.1.129.2 | CEG9271710 | Fabrication M701 - Consumables for Commissioning | ETN | 153 | 1119 | 1271 | 158 | CEG9271700 | CEG9271720
5 | 2.5.1.129.3 | CEG9271720 | CIP Delivery M701 - Consumables for Commissioning | ETN | - | - | 1271 | 158 | CEG9271710 | CEG4710000
4 | 2.5.1.130 | - | V37 UST Ventilation System |  | - | Anterior ao EPC | 279 | 399
5 | 2.5.1.130.1 | CEG9271730 | Bidding and Hiring V37 - Ventilation System (UST) | ETN | - | Anterior ao EPC | 218 | 399 | CEG1424010 | CEG9271740
5 | 2.5.1.130.2 | CEG9271740 | Fabrication V37 - Ventilation System (UST) | ETN | 61 | 219 | 279 | 399 | CEG9271730 | CEG9271750
5 | 2.5.1.130.3 | CEG9271750 | CIP Delivery V37 - Ventilation System (UST) | ETN | - | - | 279 | 399 | CEG9271740 | CEG6410000
4 | 2.5.1.131 | - | V38 UYA + UYF Ventilation System |  | - | Anterior ao EPC | 279 | 399
5 | 2.5.1.131.1 | CEG9271760 | Bidding and Hiring V38 - Ventilation System (UYA/UYF) | ETN | - | Anterior ao EPC | 218 | 399 | CEG1424010 | CEG9271770
5 | 2.5.1.131.2 | CEG9271770 | Fabrication V38 - Ventilation System (UYA/UYF) | ETN | 61 | 219 | 279 | 399 | CEG9271760 | CEG9271780
5 | 2.5.1.131.3 | CEG9271780 | CIP Delivery V38 - Ventilation System (UYA/UYF) | ETN | - | - | 279 | 399 | CEG9271770 | CEG6410000
2 | 2.6 | - | EPCist Contracting Services |  | - | Em andamento | Anterior ao EPC | 0
3 | 2.6.1 | - | Preparation of Due Diligence and Advisory Studies |  | - | Em andamento | Anterior ao EPC | 0
4 | 2.6.1.1 | CEG9270030 | BNDES - Preparation of Due Diligence and Advisory Studies - Service A (Internal Approval - Accepted - A6) | ETN | - | Em andamento | Anterior ao EPC | 76 | CEG9270010 | CEG9270050, CEG9270060
4 | 2.6.1.2 | CEG9270032 | BNDES - Preparation of Due Diligence and Advisory Studies - Service B | ETN | - | Em andamento | Anterior ao EPC | 0 | CEG9270012 | CEG9270050, CEG9270060
4 | 2.6.1.3 | CEG9270034 | BNDES - Preparation of Due Diligence and Advisory Studies - Service C | ETN | - | Em andamento | Anterior ao EPC | 112 | CEG9270014 | CEG9270050, CEG9270060
3 | 2.6.2 | - | Auction Preparation |  | - | Em andamento | Anterior ao EPC | 10
4 | 2.6.2.1 | CEG9270040 | BNDES - Implementation - Governance for Approvals | ETN | - | Em andamento | Anterior ao EPC | 10 | CEG9270020 | CEG9270050
4 | 2.6.2.2 | CEG9270060 | BNDES - Implementation - First Delivery, Final and Accepted Version | ETN | - | Anterior ao EPC | Anterior ao EPC | 0 | CEG9270020, CEG9270030, CEG9270032, CEG9270034 | CEG9270120
3 | 2.6.3 | - | Auction |  | - | Anterior ao EPC | Anterior ao EPC | 10
4 | 2.6.3.1 | CEG9270050 | BNDES - Implementation - Publication of Notice | ETN | - | Anterior ao EPC | Anterior ao EPC | 10 | CEG9270030, CEG9270032, CEG9270034, CEG9270040 | CEG9270110
4 | 2.6.3.2 | CEG9270110 | BNDES - Implementation - Submission of Qualification, Qualification, Homologation and Hiring | ETN | - | Anterior ao EPC | Anterior ao EPC | 10 | CEG9270050 | CEG9270130
3 | 2.6.4 | - | Hiring of the EPCist |  | - | Anterior ao EPC | Anterior ao EPC | 0
4 | 2.6.4.1 | CEG9270120 | BNDES - Implementation - Roadshow and Contracts Financing | ETN | - | Anterior ao EPC | Anterior ao EPC | 0 | CEG9270060 | CEG6670000
4 | 2.6.4.2 | CEG9270130 | BNDES - Implementation - Final Tariff Approval by MME/CNPE | ETN | - | Anterior ao EPC | Anterior ao EPC | 10 | CEG9270110 | CEG6670000
1 | 3 | - | NUCLEAR AREA (UJA/ UJB/ UJE/ UJF / UKA/ UKH ) |  | - | Anterior ao EPC | 1752 | 198
2 | 3.1 | - | Civil Construction |  | - | Anterior ao EPC | 1234 | 716
3 | 3.1.1 | - | Construction of the Reactor Building (UJA) |  | 1084 | 151 | 1234 | 419
4 | 3.1.1.1 | - | Concrete Structure (UJA) |  | 470 | 152 | 621 | 13
5 | 3.1.1.1.1 | CEG1370100 | Concrete Structure between elev. +11.15m and +17.15m (UJA) | ADDITIONAL | 249 | 152 | 400 | 0 | CEG1460000, CEG9273790, CEG9273815 | CEG1740000, CEG2620000, CEG2590000, CEG1380100, CEG1380100
5 | 3.1.1.1.2 | CEG1380100 | Concrete Structure between elev. +17.15m and +26.65m (UJA) | ADDITIONAL | 359 | 152 | 510 | 0 | CEG1460000, CEG1370100, CEG1370100, CEG9273815 | CEG1390000, CEG1740000, CEG2600000, CEG0916440, CEG4913500, CEG1671000, CEG1390000, CEG59900111, CEG59900121, CEG59900131, CEG59900141, CEG59900151, CEG59900161
5 | 3.1.1.1.3 | CEG1390000 | Concrete Structure between elev. +26.65m and +34.43m (UJA) | ADDITIONAL | 345 | 224 | 568 | 0 | CEG1380100, CEG1380100 | CEG1410000, CEG1750000, CEG5915000, CEG1080000, CEG1120000, CEG1078000, CEG0916700, CEG0916480
5 | 3.1.1.1.4 | CEG0916480 | Concrete Structure between elev. +34.43m and +42.07m (UJA) | ADDITIONAL | 68 | 538 | 605 | 29 | CEG1390000 | CEG1120000, CEG1090000, CEG1426000
5 | 3.1.1.1.5 | - | Concrete Structure (UJA) w/ Pool Lining Interface |  | 388 | 234 | 621 | 13
6 | 3.1.1.1.5.1 | CEG1370100PL | Concrete Structure between elev. +11.15m and +17.15m (UJA) Pool Lining | ADDITIONAL | 197 | 234 | 430 | 15 | CEG9273790, CEG0916360, CEG9273815 | CEG1740000, CEG2620000, CEG2590000, CEG1380100PL, CEG1380100PL
6 | 3.1.1.1.5.2 | CEG1380100PL | Concrete Structure between elev. +17.15m and +26.65m (UJA) Pool Lining | ADDITIONAL | 265 | 249 | 513 | 15 | CEG1460000, CEG1370100PL, CEG1370100PL, CEG9273815 | CEG1740000, CEG2600000, CEG0916440, CEG4913500, CEG1671000, CEG59900111, CEG59900121, CEG59900131, CEG59900141, CEG59900151, CEG59900161, CEG1390000PL, CEG1390000PL
6 | 3.1.1.1.5.3 | CEG1390000PL | Concrete Structure between elev. +26.65m and +34.43m (UJA) Pool Lining | ADDITIONAL | 90 | 479 | 568 | 0 | CEG0916420, CEG1380100PL, CEG1380100PL | CEG1410000, CEG1750000, CEG5915000, CEG1080000, CEG1120000, CEG1078000, CEG0916700, CEG0916480PL
6 | 3.1.1.1.5.4 | CEG0916480PL | Concrete Structure between elev. +34.43m and +42.07m (UJA) Pool Lining | ADDITIONAL | 44 | 578 | 621 | 13 | CEG1390000PL | CEG1120000, CEG1090000, CEG1426000
4 | 3.1.1.2 | - | Civil Dependent (UJA) |  | 433 | 151 | 583 | 354
5 | 3.1.1.2.1 | CEG1400100 | Repositioning Oil Supply Tanks JEB40BB050 (UJA/ FRAMATOME/1410/delivered) | ADDITIONAL | - | - | 151 | 0 | CEG1350000 | CEG1870000, CEG1870100, CEG1870200, CEG1870300, CEG1870400, CEG1870500, CEG1870600, CEG1870700, CEG1870800, CEG1870900, CEG1870101, CEG1870110, CEG1870120, CEG1870130, CEG1870140, CEG1870150, CEG1870160, CEG1870170, CEG1870180, CEG1870190, CEG1870201, CEG1870210, CEG1870220, CEG1870230, CEG1870240, CEG1870250, CEG1870260, CEG1870270, CEG1870280, CEG1870290, CEG1870301, CEG1870310, CEG1870320, CEG1870330, CEG1870340, CEG1870350, CEG1870360, CEG1870370, CEG1870380, CEG1870390, CEG1870401, CEG1870410, CEG1870420, CEG1870430, CEG1870440, CEG1870450, CEG1870460, CEG1870470, CEG1870480, CEG1870490, CEG1870501, CEG1870510, CEG0916340
5 | 3.1.1.2.2 | CEG0916700 | Installation of JNG Accumulators (UJA) (Package M112/ Nuclep/ 1st batch) | ADDITIONAL | 15 | 569 | 583 | 354 | CEG1390000, CEG1405000, CEG1410000, CEG1390000PL | CEG1870000, CEG1870100, CEG1870200, CEG1870300, CEG1870400, CEG1870500, CEG1870600, CEG1870700, CEG1870800, CEG1870900, CEG1870101, CEG1870110, CEG1870120, CEG1870130, CEG1870140, CEG1870150, CEG1870160, CEG1870170, CEG1870180, CEG1870190, CEG1870201, CEG1870210, CEG1870220, CEG1870230, CEG1870240, CEG1870250, CEG1870260, CEG1870270, CEG1870280, CEG1870290, CEG1870301, CEG1870310, CEG1870320, CEG1870330, CEG1870340, CEG1870350, CEG1870360, CEG1870370, CEG1870380, CEG1870390, CEG1870401, CEG1870410, CEG1870420, CEG1870430, CEG1870440, CEG1870450, CEG1870460, CEG1870470, CEG1870480, CEG1870490, CEG1870501, CEG1870510, CEG1440000
4 | 3.1.1.3 | - | Finishing (UJA) |  | 801 | 434 | 1234 | 182
5 | 3.1.1.3.1 | CEG1740000 | Civil Finishing Service phase 1/ Release Rooms (EU) for erection up to elev. +21.55m (UJA) | ADDITIONAL | 110 | 434 | 543 | 216 | CEG1730000, CEG1380000, CEG1370000, CEG1370100, CEG1380100, CEG1370100PL, CEG1380100PL | CEG1750000
5 | 3.1.1.3.2 | CEG1750000 | Civil Finishing Services Phase 1 other Areas (UJA) | ADDITIONAL | 301 | 569 | 869 | 182 | CEG1390000, CEG1740000, CEG1390000PL | CEG1870000, CEG1310000, CEG1760000, CEG1870100, CEG1870200, CEG1870300, CEG1870400, CEG1870500, CEG1870600, CEG1870700, CEG1870800, CEG1870900, CEG1870101, CEG1870110, CEG1870120, CEG1870130, CEG1870140, CEG1870150, CEG1870160, CEG1870170, CEG1870180, CEG1870190, CEG1870201, CEG1870210, CEG1870220, CEG1870230, CEG1870240, CEG1870250, CEG1870260, CEG1870270, CEG1870280, CEG1870290, CEG1870301, CEG1870310, CEG1870320, CEG1870330, CEG1870340, CEG1870350, CEG1870360, CEG1870370, CEG1870380, CEG1870390, CEG1870401, CEG1870410, CEG1870420, CEG1870430, CEG1870440, CEG1870450, CEG1870460, CEG1870470, CEG1870480, CEG1870490, CEG1870501, CEG1870510
5 | 3.1.1.3.3 | CEG1760000 | Final Civil Finishing Services (UJA) | EPC | 365 | 870 | 1234 | 182 | CEG1750000, CEG9271420, CEG9271690 | CEG1310000, CEG2610000
4 | 3.1.1.4 | - | Steel Structure (UJA) |  | 671 | 236 | 906 | 747
5 | 3.1.1.4.1 | CEG0916680 | Fabrication and Erection of Laydown Area Deck Gradings elev. +11.75m (UJA) | ADDITIONAL | 550 | 236 | 785 | 179 | CEGLIC0000 | CEG0916430
5 | 3.1.1.4.2 | CEG5890000 | Release of the Steel Structure Design up to elev. +26.65m (UJA) | ETN | - | - | 478 | 747 | CEG1346000, CEGPA01500 | CEG5905100
5 | 3.1.1.4.3 | CEG5905100 | Erection of Steel Structures up to elev. +26.65m (UJA) | ADDITIONAL | 373 | 479 | 851 | 747 | CEG5890000 | CEG5915000
5 | 3.1.1.4.4 | CEG5915000 | Erection of Steel Structures up to elev. +34.43m (UJA) | ADDITIONAL | 66 | 841 | 906 | 747 | CEG1390000, CEG5905000, CEG1390000PL, CEG5905100 | CEG1310000
3 | 3.1.2 | - | Construction of the Reactor Building (Annulus) (UJB) |  | 993 | 123 | 1115 | 538
4 | 3.1.2.1 | - | Concrete Structure (UJB) |  | 935 | 152 | 1086 | 528
5 | 3.1.2.1.1 | CEG0916500 | Complementation of the Concrete Structure in the elevation +21.05m | ADDITIONAL | 30 | 152 | 181 | 370 | CEG1460000, CEG9273815 | CEG0916520, CEG1140100
5 | 3.1.2.1.2 | CEG0916520 | Complementation of the Structure in the elevation +23.70m (UJB) | ADDITIONAL | 74 | 182 | 255 | 689 | CEG0916500 | CEG0916540
5 | 3.1.2.1.3 | CEG0916540 | Concrete Structure between the elevations +26.55 and +28.15m (UJB) | ADDITIONAL | 71 | 270 | 340 | 689 | CEG0916520 | CEG1030000, CEG1710000
5 | 3.1.2.1.4 | CEG1030000 | Concrete Structure of the Dome (Dome/ UJB) | ADDITIONAL | 368 | 719 | 1086 | 528 | CEG1120000, CEG0916540, CEG0916620 | CEG2500000, CEG1150000, CEG6450000, CEG4913700
4 | 3.1.2.2 | - | Finishing (UJB) |  | 905 | 182 | 1086 | 567
5 | 3.1.2.2.1 | CEG1140100 | Civil Finishing Services phase 1/ Release Rooms (EU) for erection up to elev. +26.65m (UJB) | ADDITIONAL | 500 | 182 | 681 | 370 | CEG0916500 | CEG1145000, CEG1180000, CEG2324000, CEG2720000, CEG1391000
5 | 3.1.2.2.2 | CEG1145000 | Civil Finishing Services Phase 1 other Areas (UJB) | EPC | 123 | 559 | 681 | 611 | CEG1140000, CEG1140100 | CEG1150000
5 | 3.1.2.2.3 | CEG1150000 | Civil Finishing Services Final Phase (UJB) | EPC | 361 | 726 | 1086 | 567 | CEG1145000, CEG1030000 | CEG1310000
4 | 3.1.2.3 | - | Steel Structure (UJB) |  | 993 | 123 | 1115 | 538
5 | 3.1.2.3.1 | CEG5930000 | Release of the Steel Structure Design above elevation +14.15m (UJB) | ETN | - | - | 123 | 538 | CEG1020000, CEG1346000, CEGPA01500 | CEG5970000, CEG5965100
5 | 3.1.2.3.2 | CEG5965100 | Erection of Steel Structures up to elev. +14.15m (UJB) | ADDITIONAL | 361 | 152 | 512 | 750 | CEG5930000, CEG1460000, CEG9273815 | CEG5970000
5 | 3.1.2.3.3 | CEG5970000 | Erection of Steel Structures up to elev. +28.15m (UJB) | EPC | 752 | 364 | 1115 | 538 | CEG1020000, CEG5930000, CEG5920000, CEG5965000, CEG5965100, CEGPA03200 | CEG1310000
3 | 3.1.3 | - | Construction of the Reactor Auxiliary Building (UKA) |  | 1026 | 152 | 1177 | 773
4 | 3.1.3.1 | - | Concrete Structure (UKA) |  | 734 | 152 | 885 | 1065
5 | 3.1.3.1.1 | CEG1970100 | Walls and Slabs up to elevation. +17.15m (UKA) | ADDITIONAL | 120 | 152 | 271 | 309 | CEG1960000, CEG1460000, CEG9273815 | CEG1990000, CEG2100000, CEG2115000, CEG2090000, CEG2165000, CEG5935000, CEG2165000, CEG1990000, CEG1990100
5 | 3.1.3.1.2 | CEG1990100 | Walls and Slabs up to elevation. +21.65m (UKA) | ADDITIONAL | 180 | 272 | 451 | 514 | CEG1975000, CEG1970100 | CEG2000000, CEG2120000, CEG2125000, CEG2170000, CEG2165000
5 | 3.1.3.1.3 | CEG1975000 | Positioning of the Personnel Lock External Chamber - JMF | ADDITIONAL | - | - | 451 | 399 | CEGLIC0000 | CEG1990000, CEG1990100
5 | 3.1.3.1.4 | CEG2000000 | Walls and Slabs up to elevation +25.95m (UKA) | ADDITIONAL | 180 | 452 | 631 | 514 | CEG1460000, CEG1990100, CEG9273815 | CEG2010000, CEG2130000, CEG2140000, CEG2490000
5 | 3.1.3.1.5 | CEG1975500 | Positioning of the Personnel Lock Internal Chamber - JMF | ADDITIONAL | - | 569 | - | 0 | CEGLIC0000 | CEG1080000
5 | 3.1.3.1.6 | CEG2010000 | Walls and Slabs +25.95m to the Coverage(UKA) | ADDITIONAL | 83 | 632 | 714 | 1236 | CEG2000000 | CEG1340000
5 | 3.1.3.1.7 | CEG2070000 | Concreting of Slabs after erection of Civil Dependents (UKA) | EPC | 120 | 766 | 885 | 867 | CEG2125000, CEG2130000, CEG2140000 | CEG2180000
4 | 3.1.3.2 | - | Civil Dependent (UKA) |  | 226 | 542 | 767 | 822
5 | 3.1.3.2.1 | CEG2090000 | Positioning of Hybrid Bed Filters GDF01/11BT001/ Superior Slab +14.15m (UKA) (Package M603) (2nd Stage) | EPC | - | 542 | - | 309 | CEG1970000, CEG2014000, CEG1970100 | CEG2260000
5 | 3.1.3.2.2 | CEG2140000 | Positioning of Liquid Waste Evap. Columns KPF11/12/ Slab Sup Cob. (UKA) (Pac M130/131/140) | EPC | - | 692 | - | 606 | CEG2000000, CEG2016000 | CEG2070000, CEG5410000
5 | 3.1.3.2.3 | CEG2125000 | Positioning of Degassing Column KBF40BY001/ Top Slab +21.65m (UKA) (Pac M130/131/140) | EPC | - | 692 | - | 897 | CEG2016000, CEG1990100 | CEG2070000
5 | 3.1.3.2.4 | CEG2130000 | Positioning of Coolant Evapor. KBF20/ Top Slab Coverage +25.95m (UKA) (Pac M130/131/140) | EPC | - | 722 | - | 867 | CEG2000000, CEG2016000 | CEG2070000
5 | 3.1.3.2.5 | CEG2115000 | Positioning of Degassing Column KBG10BY001/ Top Slab +17.15m (UKA) (Pac M130/131/140) | EPC | - | 767 | - | 606 | CEG2016000, CEG1970100 | CEG5390000
4 | 3.1.3.3 | - | Finishing (UKA) |  | 1026 | 152 | 1177 | 605
5 | 3.1.3.3.1 | CEG2161000 | Finishing Service of Civil phase 1/ Release Rooms (EU) for erection up to elev. +11.15m (UKA) | EPC | 335 | 152 | 486 | 506 | CEG2150000, CEG1960000, CEG1940000, CEG1950000, CEGPA03200 | CEG2220000
5 | 3.1.3.3.2 | CEG2165000 | Finishing Service of Civil phase 1/ Release Rooms (EU) for erection up to elev. +21.65m (UKA) | EPC | 362 | 272 | 633 | 379 | CEG1970000, CEG1970000, CEG1990000, CEGPA03200, CEG1990100, CEG1970100, CEG1970100 | CEG2180000, CEG2260000, CEG2170000
5 | 3.1.3.3.3 | CEG2170000 | Civil Finishing Services Phase 1 other Areas (UKA) | EPC | 364 | 542 | 905 | 605 | CEG1990000, CEG2165000, CEG1990100 | CEG2180000
5 | 3.1.3.3.4 | CEG2180000 | Civil Finishing Services Final Phase (UKA/UKH) | EPC | 366 | 812 | 1177 | 605 | CEG2170000, CEG2165000, CEG2070000 | CEG1315000
4 | 3.1.3.4 | - | Steel Structure (UKA) |  | 368 | 152 | 519 | 1134
5 | 3.1.3.4.1 | CEG5925100 | Erection of Steel Structures up to elev. +11.15m (UKA) | ADDITIONAL | 338 | 152 | 489 | 1134 | CEG1960000, CEG5900000, CEG1460000, CEG9273815 | CEG5935000
5 | 3.1.3.4.2 | CEG5935000 | Erection of Steel Structures up to elev. +33.30m (UKA) | ADDITIONAL | 138 | 382 | 519 | 1134 | CEG1970000, CEG5925000, CEG1970100, CEG5925100 | CEG1310000
3 | 3.1.4 | - | Construction of the Gas Discharge Chimney (UKH) |  | - | Anterior ao EPC | 1187 | 514
4 | 3.1.4.1 | - | Concrete Structure (UKH) |  | 550 | 548 | 1097 | 514
5 | 3.1.4.1.1 | CEG2490000 | Concrete Structure between elev. +5.60m and +26.35m (UKH) | EPC | 93 | 548 | 640 | 514 | CEG2000000, CEG2480000, CEGPA03200 | CEG2500000, CEG2750000
5 | 3.1.4.1.2 | CEG2500000 | Concrete Structure between elev. +26.35m and +155.00m (UKH) | EPC | 468 | 630 | 1097 | 514 | CEG1030000, CEG2490000 | CEG2750000
4 | 3.1.4.2 | - | Finishing (UKH) |  | - | Anterior ao EPC | 1187 | 514
5 | 3.1.4.2.1 | CEG2740000 | Release of the Civil Finishing Design up to elev. +29.92m (UKH) | ETN | - | - | Anterior ao EPC | 1473 | CEG1346000, CEGPA01500 | CEG2750000
5 | 3.1.4.2.2 | CEG2750000 | Civil Finishing Services Phase 1 (UKH) | EPC | 90 | 1098 | 1187 | 514 | CEG2740000, CEG2490000, CEG2500000 | CEG5945000, CEG1315000
4 | 3.1.4.3 | - | Steel Structure (UKH) |  | - | Anterior ao EPC | 1139 | 514
5 | 3.1.4.3.1 | CEG5910000 | Release of the Steel Structure Design up to elev. +29.92m (UKH) | ETN | - | - | Anterior ao EPC | 1473 | CEG1346000, CEGPA01500 | CEG5945000
5 | 3.1.4.3.2 | CEG5945000 | Erection of Steel Structures up to elev. +29.92m (UKH) | EPC | 8 | 1098 | 1105 | 514 | CEG5910000, CEG2750000 | CEG5955000
5 | 3.1.4.3.3 | CEG5955000 | Erection of Steel Structures up to elev. +155.00m (UKH) | EPC | 34 | 1106 | 1139 | 514 | CEG5945000 | CEG1310000
3 | 3.1.5 | - | Construction of the Main Steam and Feedwater Valve Compartment (UJE) |  | 333 | 342 | 674 | 689
4 | 3.1.5.1 | - | Concrete Structure (UJE) |  | 273 | 342 | 614 | 689
5 | 3.1.5.1.1 | CEG1710000 | Concrete Structure up to elevation. +36.15m (UJE) | ADDITIONAL | 273 | 342 | 614 | 689 | CEG1070000, CEG1700000, CEG1700000, CEG0916540, CEG1460000, CEG9273815 | CEG1720000, CEG6070000
4 | 3.1.5.2 | - | Finishing (UJE) |  | 183 | 492 | 674 | 689
5 | 3.1.5.2.1 | CEG1720000 | Civil Finishing Phase 1 (UJE) | EPC | 183 | 492 | 674 | 689 | CEG1710000, CEGPA03200 | CEG2300000, CEG2300100, CEG2300200, CEG2300300, CEG2300400
4 | 3.1.5.3 | - | Steel Structure (UJE) |  | 180 | 492 | 671 | 689
5 | 3.1.5.3.1 | CEG6070000 | Erection of Steel Structures (UJE) | ADDITIONAL | 180 | 492 | 671 | 689 | CEG1710000 | CEG2300000, CEG2300100, CEG2300200, CEG2300300, CEG2300400
3 | 3.1.6 | - | Construction of the Equipment Lock Structure and Gantry (UJF) |  | 679 | 521 | 1199 | 751
4 | 3.1.6.1 | - | Concrete Structure (UJF) |  | 188 | 521 | 708 | 26
5 | 3.1.6.1.1 | CEG4913500 | Concrete Structure Columns / Beams up to elevation +40.40m (UJF) | ADDITIONAL | 188 | 521 | 708 | 26 | CEG1660000, CEG1460000, CEG1380000, CEG1380100, CEG1380100PL, CEG9273815 | CEG1670000, CEG1680000, CEG6060000, CEG1680000
4 | 3.1.6.2 | - | Civil Dependent (UJF) |  | 491 | 709 | 1199 | 751
5 | 3.1.6.2.1 | CEG1670000 | Erection and Commissioning of SMJ05 Overhead Crane for Entry of Components/ Semi-Gantry (UJF) | ADDITIONAL | 280 | 709 | 988 | 26 | CEG1080000, CEG5820000, CEG4913500 | CEG0916760, CEG0916740, CEG0916320, CEG0916800
5 | 3.1.6.2.2 | CEG1671000 | Erection of the UJF Erection Platform | EPC | 30 | 914 | 943 | 1007 | CEG1260000, CEG1380000, CEG1380100, CEG1380100PL | CEG1340000
5 | 3.1.6.2.3 | CEG1672000 | Disassembling of the UJF Platform | EPC | 15 | 1185 | 1199 | 325 | CEGLIC0000 | CEG1263000
4 | 3.1.6.3 | - | Finishing (UJF) |  | 85 | 709 | 793 | 860
5 | 3.1.6.3.1 | CEG1680000 | Civil Finishing (UJF) | EPC | 85 | 709 | 793 | 860 | CEG4913500, CEG4913500, CEGPA03200 | CEG1310000
4 | 3.1.6.4 | - | Steel Structure (UJF) |  | 85 | 709 | 793 | 449
5 | 3.1.6.4.1 | CEG6060000 | Erection of Steel Structures (UJF) | ADDITIONAL | 85 | 709 | 793 | 449 | CEG4913500 | CEG6220000
2 | 3.2 | - | Erection of the Steel Envelope of the Containment Sphere and Locks (UJA) |  | 721 | 569 | 1289 | 325
3 | 3.2.1 | CEG1078000 | Civil Release elev. +35.55m UJA for erection of Zone 8 (UJA) | ADDITIONAL | - | 569 | - | 0 | CEG1390000, CEG1390000PL | CEG1080000, CEG1420000
3 | 3.2.2 | CEG1080000 | Erection of Zone 8 of the JMA Containment Sphere (UJA) | ADDITIONAL | 81 | 569 | 649 | 0 | CEG1070000, CEG1078000, CEG1390000, CEG1510000, CEG1975500, CEG1390000PL | CEG1670000, CEG1120000, CEG1075000
3 | 3.2.3 | CEG1120000 | Erection of Zone 9 of the JMA Containment Sphere (UJA) | ADDITIONAL | 69 | 650 | 718 | 0 | CEG1080000, CEG1390000, CEG0916480, CEG1390000PL, CEG0916480PL | CEG1090000, CEG1030000, CEG0916560
3 | 3.2.4 | CEG0916560 | Erection of Zone 10 Spider Scaffolding Structure (UJA) | ADDITIONAL | 15 | 719 | 733 | 0 | CEG1120000, CEG1430000 | CEG1090000
3 | 3.2.5 | CEG1090000 | Erection of Zone 10 of the JMA Containment Sphere (UJA) | ADDITIONAL | 52 | 734 | 785 | 0 | CEG1120000, CEG0916480, CEG0916560, CEG1430000, CEG0916480PL | CEG1260000, CEG0916580, CEG0916430
3 | 3.2.6 | CEG1260000 | Welding of Sealing Bars, Drilling, Oxy-cutting and Erection Gate Removal (UJA) | ADDITIONAL | 150 | 764 | 913 | 547 | CEG1090000 | CEG1270000, CEG1110000, CEG1075000, CEG1671000
3 | 3.2.7 | CEG0916580 | Erection of Zone 11 of the JMA Containment Sphere (UJA) | ADDITIONAL | 43 | 786 | 828 | 0 | CEG1090000 | CEG0916600
3 | 3.2.8 | CEG1110000 | Erection of the JME Equipment Lock (UJA) | EPC | 150 | 787 | 936 | 678 | CEG1260000 | CEG1300000, CEG1361000, CEG6450000
3 | 3.2.9 | CEG1075000 | Erection of the JMF Personnel Lock (UJA) | EPC | 186 | 792 | 977 | 547 | CEG1641000, CEG1080000, CEG1260000, CEG4976000 | CEG1300000, CEG6450000, CEG1263000
3 | 3.2.10 | CEG1270000 | Erection of the JMG Emergency Lock (UJA) | EPC | 150 | 803 | 952 | 662 | CEG1260000 | CEG1300000, CEG6450000
3 | 3.2.11 | CEG0916600 | Erection of Zone 12 of the JMA Containment Sphere (UJA) | ADDITIONAL | 32 | 829 | 860 | 0 | CEG0916580 | CEG0916620
3 | 3.2.12 | CEG0916620 | Erection of Zone 13 of the JMA Containment Sphere (UJA) | ADDITIONAL | 17 | 861 | 877 | 0 | CEG0916600 | CEG1030000, CEG0916640
3 | 3.2.13 | CEG0916640 | Zone 10 Spider Dismantling (UJA) | ADDITIONAL | 60 | 878 | 937 | 0 | CEG0916620 | CEG6450000, CEG1440000
3 | 3.2.14 | CEG1361000 | Completion of the Erection of the Containment Sphere (UJA) | ADDITIONAL | - | - | 936 | 678 | CEG1110000 | CEG1300000, CEG6450000
3 | 3.2.15 | CEG1263000 | Erection Gate Closing (UJA) | EPC | 90 | 1200 | 1289 | 325 | CEG1075000, CEG0916320, CEG1672000 | CEG6450000
2 | 3.3 | - | Electromechanical Erection in Buildings (UJA/UJB/UJE/UJF/UKA/UKH) |  | - | Anterior ao EPC | 1713 | 237
3 | 3.3.1 | - | Erection in the Reactor Building (UJA) |  | - | Anterior ao EPC | 1713 | 237
4 | 3.3.1.1 | - | Erection of the Polar Bridge (Crane) (UJA) |  | 370 | 623 | 992 | 0
5 | 3.3.1.1.1 | CEG1430000 | Erection of the Railway, Girders and Trolley of the Polar Bridge | ADDITIONAL | 83 | 623 | 705 | 13 | CEG1426000 | CEG1090000, CEG0916560, CEG1440000
5 | 3.3.1.1.2 | CEG1440000 | Final Erection, Functional Testing and Commissioning | ADDITIONAL | 55 | 938 | 992 | 0 | CEG1430000, CEG0916640, CEG0916700 | CEG1261000
5 | 3.3.1.1.3 | CEG1261000 | SMJ01 ready-to-use Polar Bridge (UJA) | ADDITIONAL | - | - | 992 | 0 | CEG1440000 | CEG0916760, CEG0916740, CEG0916260, CEG0916320, CEG0916720, CEG0916800, CEG4910390, CEG0916300
4 | 3.3.1.2 | - | Coating of Fuel Pools and Supercompact Racks (UJA) |  | 1279 | 152 | 1430 | 520
5 | 3.3.1.2.1 | - | Pools - Phase 1 |  | 327 | 152 | 478 | 0
6 | 3.3.1.2.1.1 | CEG0916340 | Form Works and Embedded Parts of the Cask Pool Walls - Phase 1 (UJA) | ADDITIONAL | 120 | 152 | 271 | 0 | CEG1620000, CEG1540000, CEG1400100, CEG0916660, CEG9273815 | CEG0916360
6 | 3.3.1.2.1.2 | CEG0916360 | Form Works and Embedded Parts of the Fuel Pool Walls - Phase 1 (UJA) | ADDITIONAL | 120 | 172 | 291 | 0 | CEG0916340 | CEG0916380, CEG1370100PL
6 | 3.3.1.2.1.3 | CEG0916380 | Form Works and Embedded Parts - Phase 1 (UJA) | ADDITIONAL | 60 | 229 | 288 | 0 | CEG0916360 | CEG0916400
6 | 3.3.1.2.1.4 | CEG0916400 | Form Works and Embedded Parts of the Reactor Room Walls - Phase 1 (UJA) | ADDITIONAL | 80 | 269 | 348 | 0 | CEG0916380 | CEG0916420
6 | 3.3.1.2.1.5 | CEG0916420 | Erection of Lining Pool Panels - Phase 1 (UJA) | ADDITIONAL | 200 | 279 | 478 | 0 | CEG0916400 | CEG0916440, CEG59900111, CEG59900121, CEG59900131, CEG59900141, CEG59900151, CEG59900161, CEG1390000PL
5 | 3.3.1.2.2 | - | Pools - Preparation for Phase 2 |  | 150 | 514 | 663 | 184
6 | 3.3.1.2.2.1 | CEG0916440 | Pool Construction and Coating Services - Stocret Coating (UJA) | ADDITIONAL | 150 | 514 | 663 | 184 | CEG0916420, CEG1380000, CEG1380100, CEG1380100PL | CEG0916760, CEG0916740, CEG0916320, CEG0916800, CEG4910390, CEG59900151
5 | 3.3.1.2.3 | - | Pools - Phase 2 |  | 902 | 529 | 1430 | 520
6 | 3.3.1.2.3.1 | CEG59900111 | Erection of Gratings botton Setdown | EPC | 28 | 529 | 556 | 184 | CEG0916420, CEG1380100, CEG1541000, CEG1380100PL | CEG59900121
6 | 3.3.1.2.3.2 | CEG59900121 | Erection of Fuel Pool Bottom Gratings | EPC | 41 | 529 | 569 | 184 | CEG0916420, CEG1380000, CEG1380100, CEG1541000, CEG59900111, CEG1380100PL | CEG59900131
6 | 3.3.1.2.3.3 | CEG59900131 | Concreting of the FP/SD Bottom + Mortar - EPCist | EPC | 29 | 561 | 589 | 184 | CEG0916420, CEG1380000, CEG1380100, CEG59900121, CEG1380100PL | CEG59900141
6 | 3.3.1.2.3.4 | CEG59900141 | Scaffolding Erection - Clean FP/CP | EPC | 29 | 590 | 618 | 184 | CEG0916420, CEG1380000, CEG1380100, CEG59900131, CEG1380100PL | CEG59900151
6 | 3.3.1.2.3.5 | CEG59900151 | Cask Pool Wall Lining | EPC | 138 | 604 | 741 | 184 | CEG0916420, CEG1380000, CEG1380100, CEG59900141, CEG0916440, CEG1380100PL | CEG59900161
6 | 3.3.1.2.3.6 | CEG59900161 | Fuel Pool Wall Lining | EPC | 182 | 604 | 785 | 184 | CEG0916420, CEG1380000, CEG1380100, CEG59900151, CEG1380100PL | CEG59900171
6 | 3.3.1.2.3.7 | CEG59900171 | Erection of Sill and niche for the separating damper - EPCist | EPC | 72 | 869 | 940 | 184 | CEG59900161, CEG2600000 | CEG1632000, CEG59900181
6 | 3.3.1.2.3.8 | CEG59900181 | Concreting of Sill and separation damper niche | EPC | 39 | 941 | 979 | 184 | CEG59900171 | CEG1632000, CEG59900191
6 | 3.3.1.2.3.9 | CEG59900191 | Scaffolding Erection - Clean - SD/RR - EPCist | EPC | 15 | 980 | 994 | 184 | CEG59900181 | CEG1632000, CEG59900201
6 | 3.3.1.2.3.10 | CEG59900201 | SD/RR Wall Coating | EPC | 90 | 995 | 1084 | 184 | CEG59900191 | CEG1632000, CEG59900211
6 | 3.3.1.2.3.11 | CEG59900211 | SD Floor Coating | EPC | 59 | 1026 | 1084 | 837 | CEG59900201 | CEG59900221
6 | 3.3.1.2.3.12 | CEG59900221 | Erection of RR/SD stairs and accessories | EPC | 29 | 1085 | 1113 | 837 | CEG59900211 | CEG1340000
6 | 3.3.1.2.3.13 | CEG1632000 | Pool Lining - Erection of Supercompact Racks of Fuel storage (Zone1) (UJA) | EPC | 173 | 1085 | 1257 | 184 | CEG1631000, CEG59900171, CEG59900181, CEG59900191, CEG59900201 | CEG1634000, CEG1650000
6 | 3.3.1.2.3.14 | CEG1634000 | Pool Lining - Erection of Supercompact Racks of Fuel storage (Zone2) (UJA) | EPC | 173 | 1258 | 1430 | 184 | CEG1632000, CEG1633000 | CEG1650000, CEG6450000
4 | 3.3.1.3 | - | Fuel Refilling Device (UJA) |  | 240 | 1230 | 1469 | 67
5 | 3.3.1.3.1 | CEG1640000 | Erection of the Refuelling Machine FCB (UJA) | EPC | 240 | 1230 | 1469 | 67 | CEG1636000, CEG0916760, CEG0916320 | CEG1650000, CEG3840000
5 | 3.3.1.3.2 | CEG3840000 | Installation of Components and Devices for Fuel Transfer to the RPV (UJA) | EPC | 73 | 1397 | 1469 | 67 | CEG1640000 | CEG3860000, CEG1610000
4 | 3.3.1.4 | - | Nuclear Fuel Storage and Handling (UJA) |  | 210 | 1350 | 1559 | 193
5 | 3.3.1.4.1 | CEG1610000 | Storage and Handling of Nuclear Fuel (UJA) | EPC | 210 | 1350 | 1559 | 193 | CEG3860000, CEG3840000 | CEG6470000
4 | 3.3.1.5 | - | Reactor Protection System (UJA) |  | 120 | 547 | 666 | 987
5 | 3.3.1.5.1 | CEG4530000 | Erection of the Reactor Protection System - Periphery (CF: L) (UJA/UJB/UJE) | EPC | 120 | 547 | 666 | 987 | CEG4360000 | CEG1431000
5 | 3.3.1.5.2 | CEG1431000 | Completion of Reactor Protection System Erection (JR) (UJA) | EPC | - | - | 666 | 987 | CEG4360000, CEG4530000 | CEG1310000
4 | 3.3.1.6 | - | Containment Penetrations (UJA) |  | 364 | 569 | 932 | 682
5 | 3.3.1.6.1 | CEG1420000 | Nuclear Fuel of LAB/LBA Mechanical Penetrations in the JMA Containment Sphere (UJA) | EPC | 364 | 569 | 932 | 682 | CEG1070000, CEG5830000, CEG1078000, CEG6680000, CEG6680000, CEG9271540 | CEG1422000, CEG1422000, CEG6450000
5 | 3.3.1.6.2 | CEG1422000 | Nuclear Fuel of JML Electrical Penetrations in the JMA Containment Sphere (UJA) | EPC | 120 | 813 | 932 | 682 | CEG1420000, CEG1420000, CEG5830000 | CEG2670000, CEG6450000
4 | 3.3.1.7 | - | Erection of Supports and Isolation of the Reactor Pressure Vessel (UJA) |  | 1165 | 160 | 1324 | 182
5 | 3.3.1.7.1 | CEG2590000 | Placement of the Insulation Embedded Parts and RPV Support (JAA) /+14.15m (UJA) | ADDITIONAL | 182 | 160 | 341 | 322 | CEG1350000, CEG1460000, CEG0916660, CEG1370000, CEG9273670, CEG1370100, CEG1370100PL, CEG9273815 | CEG2600000, CEG2600000, CEG2620000
5 | 3.3.1.7.2 | CEG2600000 | Erection of RPV Phase 1 Supports (JAA) (UJA) | EPC | 180 | 551 | 730 | 322 | CEG1380000, CEG2590000, CEG2590000, CEG2630000, CEG0916660, CEG9160000, CEG9159000, CEG1380100, CEG1380100PL | CEG2640000, CEG0916320, CEG2610000, CEG59900171
5 | 3.3.1.7.3 | CEG2610000 | Erection of RPV Phase 2 Supports (JAA) (UJA) | EPC | 90 | 1235 | 1324 | 182 | CEG1760000, CEG2600000 | CEG6450000, CEG3810000
4 | 3.3.1.8 | - | Erection of Primary Circuit Supports (UJA) |  | 1493 | 221 | 1713 | 39
5 | 3.3.1.8.1 | CEG2620000 | Primary Circuit Supports - Embedded Parts (elev. +11.15m / +17.15m) (UJA) | ADDITIONAL | 210 | 221 | 430 | 322 | CEG1350000, CEG2590000, CEG1370000, CEG1370100, CEG1370100PL | CEG2630000
5 | 3.3.1.8.2 | CEG2630000 | Primary Circuit Supports - Phase 1 Lifting (UJA) | EPC | 125 | 431 | 555 | 322 | CEG6680000, CEG6680000, CEG2620000, CEG0916660, CEG9060000 | CEG2640000, CEG0916760, CEG2600000, CEG0916740, CEG0916320, CEG0916800, CEG4910390
5 | 3.3.1.8.3 | CEG2640000 | Primary Circuit Supports - Continuation phase 1/2 (UJA) | EPC | 304 | 686 | 989 | 590 | CEG2600000, CEG2630000 | CEG2650000, CEG1285000
5 | 3.3.1.8.4 | CEG2650000 | Primary Circuit Supports - phase 3 (UJA) | EPC | 60 | 1654 | 1713 | 39 | CEG1471000, CEG1311000, CEG2640000 | CEG6470000
4 | 3.3.1.9 | - | Erection of Primary Circuit Components (UJA) |  | 727 | 933 | 1659 | 291
5 | 3.3.1.9.1 | CEG0916300 | Installation o f Erection Platform / Bearing Path for Heavy Components | EPC | 60 | 933 | 992 | 2 | CEG1261000 | CEG4910390
5 | 3.3.1.9.2 | CEG4910390 | Lifting and Installation of the JEF10BB001 Pressurizer (JEF System) (UJA) | EPC | 20 | 995 | 1014 | 0 | CEG2630000, CEG1261000, CEG0916440, CEG0916430, CEG0916300 | CEG0916260, CEG0916800, CEG0916260
5 | 3.3.1.9.3 | CEG0916800 | Lifting and Installation of Pressure Relief Tank JEG10BB001 (UJA) | EPC | 20 | 1015 | 1034 | 0 | CEG1670000, CEG2630000, CEG1261000, CEG0916440, CEG4910390 | CEG0916010, CEG0916130, CEG0916740, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230
5 | 3.3.1.9.4 | CEG0916740 | Lifting and Erection of the Coolant Pump Housings of the JEB10-40AP001 Reactor (UJA) | EPC | 30 | 1035 | 1064 | 0 | CEG1670000, CEG2630000, CEG1261000, CEG0916440, CEG0916800 | CEG0916130, CEG0916010, CEG0916760, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230, CEG0916750
5 | 3.3.1.9.5 | CEG0916750 | Erection of the Reactor Pressure Vessel Insulation (UJA) | EPC | 60 | 1050 | 1109 | 0 | CEG0916430, CEG0916740, CEG7056000 | CEG0916760
5 | 3.3.1.9.6 | CEG0916760 | Lifting and Installation of Steam Generators JEA10-40BC001(UJA) | EPC | 60 | 1110 | 1169 | 0 | CEG1670000, CEG2630000, CEG1261000, CEG0916440, CEG0916740, CEG0916750 | CEG0916010, CEG0916130, CEG1640000, CEG0916320, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230, CEG0916280, CEG4935000
5 | 3.3.1.9.7 | CEG0916320 | Lifting and Installation of the JAA10BB001 Reactor Pressure Vessel (UJA) | EPC | 30 | 1170 | 1199 | 0 | CEG1670000, CEG2630000, CEG1261000, CEG2600000, CEG0916440, CEG0916760 | CEG1640000, CEG0916010, CEG0916130, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230, CEG0916260, CEG0916280, CEG1263000
5 | 3.3.1.9.8 | CEG4935000 | Erection of Circuit Pressure Equalizers structures - Overflow Cover - JMJ10 | EPC | 90 | 1170 | 1259 | 691 | CEG0916760, CEG4926000, CEG6076000 | CEG1340000
5 | 3.3.1.9.9 | CEG0916280 | Erection of Steam Generators (JEA10-40 System) | EPC | 125 | 1200 | 1324 | 255 | CEG0916760, CEG0916320 | CEG1470000
5 | 3.3.1.9.10 | CEG0916260 | Erection of the Pressurization System (JEF System) | EPC | 195 | 1200 | 1394 | 185 | CEG1261000, CEG0916320, CEG4910390, CEG4910390 | CEG1470000
5 | 3.3.1.9.11 | CEG3170000 | Establish "Clean Conditions" and Access Control for Erection of RPV Internals (UJA) | EPC | 30 | 1370 | 1399 | 17 | CEG3480000, CEG1464000 | CEG3810000
5 | 3.3.1.9.12 | CEG1464000 | Erection of the JEF Pressurizer Valve Station (UJA) | EPC | 30 | 1370 | 1399 | 17 | CEG1462000, CEG0916010, CEG0916130, CEG0916250, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230 | CEG1474000, CEG1285000, CEG3170000
5 | 3.3.1.9.13 | CEG3480000 | Installation of Devices for Erection of RPV Internals (JAA) (UJA) | EPC | 20 | 1397 | 1416 | 0 | CEG0916250 | CEG3810000, CEG3170000
5 | 3.3.1.9.14 | CEG0916410 | Erection of the Removable Part and RCP Electric Motors (JEB System) | EPC | 58 | 1397 | 1454 | 160 | CEG0916250 | CEG1300000, CEG6450000
5 | 3.3.1.9.15 | CEG3810000 | Installation and Erection of RPV including Internals (JAA) (UJA) | EPC | 120 | 1417 | 1536 | 0 | CEG3480000, CEG2610000, CEG3170000 | CEG0916470, CEG3860000
5 | 3.3.1.9.16 | CEG9130000 | Erection of the Lifting Beam and RPV Cover Rod (UJA) | EPC | 60 | 1477 | 1536 | 0 | CEG9120000 | CEG3860000
5 | 3.3.1.9.17 | CEG3860000 | Installation of RPV Reactor Pressure Vessel Cover (JAA) (UJA) | EPC | 23 | 1537 | 1559 | 0 | CEG3840000, CEG9130000, CEG3810000 | CEG1310000, CEG1610000, CEG1474000
5 | 3.3.1.9.18 | CEG1474000 | Primary Circuit Cleanliness (UJA) | EPC | 30 | 1550 | 1579 | 0 | CEG1464000, CEG0916010, CEG0916130, CEG0916250, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230, CEG4710000, CEG3860000 | CEG1285000, CEG0916180, CEG6450000
5 | 3.3.1.9.19 | CEG0916470 | Inspection of Reactor Pressure Vessel Internals | EPC | 45 | 1615 | 1659 | 94 | CEG3810000, CEG0916220 | CEG1320000
4 | 3.3.1.10 | - | Erection of Primary Circuit Piping (UJA) |  | 614 | 786 | 1399 | 17
5 | 3.3.1.10.1 | CEG0916430 | Transport and Lay-down of Primary Circuit Spools | EPC | 30 | 786 | 815 | 179 | CEG0916680, CEG1090000, CEG0916660 | CEG0916720, CEG0916750, CEG4910390
5 | 3.3.1.10.2 | CEG0916720 | Preliminary Arrangement of Main Coolant Piping Units (JEC System) | EPC | 22 | 998 | 1019 | 180 | CEG1261000, CEG0916430 | CEG0916010, CEG0916130, CEG0916030, CEG0916150, CEG0916040, CEG0916050, CEG0916060, CEG0916070, CEG0916170, CEG0916190, CEG0916210, CEG0916230
5 | 3.3.1.10.3 | - | Loop 1 |  | 145 | 1200 | 1344 | 72
6 | 3.3.1.10.3.1 | CEG0916010 | Installation and Welding of 1st Loop - Hot Leg | EPC | 140 | 1200 | 1339 | 0 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320 | CEG1464000, CEG1474000, CEG1285000, CEG0916030, CEG0916050
6 | 3.3.1.10.3.2 | CEG0916030 | Installation and Welding of 1st Loop - Cold Leg | EPC | 130 | 1210 | 1339 | 72 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916010 | CEG1464000, CEG1474000, CEG1285000, CEG0916040
6 | 3.3.1.10.3.3 | CEG0916040 | Installation and Welding of 1st Loop - Cross Over Leg | EPC | 120 | 1225 | 1344 | 72 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916030 | CEG1464000, CEG1474000, CEG1285000
5 | 3.3.1.10.4 | - | Loop 2 |  | 135 | 1210 | 1344 | 72
6 | 3.3.1.10.4.1 | CEG0916050 | Installation and Welding of 2nd Loop - Hot Leg | EPC | 120 | 1210 | 1329 | 0 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916010 | CEG1464000, CEG1474000, CEG1285000, CEG0916060, CEG0916130
6 | 3.3.1.10.4.2 | CEG0916060 | Installation and Welding of 2nd Loop - Cold Leg | EPC | 90 | 1240 | 1329 | 72 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916050 | CEG1464000, CEG1474000, CEG1285000, CEG0916070
6 | 3.3.1.10.4.3 | CEG0916070 | Installation and Welding of 2nd Loop - Cross Over Leg | EPC | 90 | 1255 | 1344 | 72 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916060 | CEG1464000, CEG1474000, CEG1285000
5 | 3.3.1.10.5 | - | Loop 3 |  | 120 | 1260 | 1379 | 37
6 | 3.3.1.10.5.1 | CEG0916130 | Installation and Welding of 3rd Loop - Hot Leg | EPC | 120 | 1260 | 1379 | 0 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916050 | CEG1464000, CEG1474000, CEG1285000, CEG0916150, CEG0916190
6 | 3.3.1.10.5.2 | CEG0916150 | Installation and Welding of 3rd Loop - Cold Leg | EPC | 100 | 1275 | 1374 | 37 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916130 | CEG1464000, CEG1474000, CEG1285000, CEG0916170
6 | 3.3.1.10.5.3 | CEG0916170 | Installation and Welding of 3rd Loop - Cross Over Leg | EPC | 90 | 1290 | 1379 | 37 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916150 | CEG1464000, CEG1474000, CEG1285000
5 | 3.3.1.10.6 | - | Loop 4 |  | 120 | 1280 | 1399 | 0
6 | 3.3.1.10.6.1 | CEG0916190 | Installation and Welding of 4th Loop - Hot Leg | EPC | 120 | 1280 | 1399 | 0 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916130 | CEG1464000, CEG1474000, CEG1285000, CEG0916210
6 | 3.3.1.10.6.2 | CEG0916210 | Installation and Welding of 4th Loop - Cold Leg | EPC | 90 | 1300 | 1389 | 0 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916190 | CEG1464000, CEG1474000, CEG1285000, CEG0916230
6 | 3.3.1.10.6.3 | CEG0916230 | Installation and Welding of 4th Loop - Cross Over Leg | EPC | 90 | 1300 | 1389 | 0 | CEG0916760, CEG0916740, CEG0916720, CEG0916800, CEG0916320, CEG0916210 | CEG1464000, CEG1474000, CEG1285000, CEG0916250
5 | 3.3.1.10.7 | - | Surge Line |  | 75 | 1322 | 1396 | 0
6 | 3.3.1.10.7.1 | CEG0916250 | Installation and Welding of Surge Line Pipings | EPC | 75 | 1322 | 1396 | 0 | CEG0916230 | CEG1464000, CEG1474000, CEG1285000, CEG3480000, CEG0916410
4 | 3.3.1.11 | - | Piping Systems (UJA, except Primary Circuit) |  | - | Anterior ao EPC | 1538 | 214
5 | 3.3.1.11.1 | - | UJA General Erection Area |  | - | Anterior ao EPC | 1538 | 214
6 | 3.3.1.11.1.1 | CEG1840000 | Piping - Erection Units Design Released (UJA) | ETN | - | - | Anterior ao EPC | 124 | CEG1347000, CEGPA01500 | CEG1850000
6 | 3.3.1.11.1.2 | CEG1850000 | Piping - Engineering Phase 1 (Workbook) (UJA) | EPC | 727 | 152 | 878 | 124 | CEG1840000, CEG6680000, CEG6680000 | CEG1860000, CEG1860000
6 | 3.3.1.11.1.3 | CEG1860000 | Piping - Prefabrication (UJA) | EPC | 727 | 242 | 968 | 124 | CEG1850000, CEG1850000, CEG6600000, CEG6680000, CEG9272680 | CEG1870000, CEG1870100, CEG1870200, CEG1870300, CEG1870400, CEG1870500, CEG1870600, CEG1870700, CEG1870800, CEG1870900, CEG1870101, CEG1870110, CEG1870120, CEG1870130, CEG1870140, CEG1870150, CEG1870160, CEG1870170, CEG1870180, CEG1870190, CEG1870201, CEG1870210, CEG1870220, CEG1870230, CEG1870240, CEG1870250, CEG1870260, CEG1870270, CEG1870280, CEG1870290, CEG1870301, CEG1870310, CEG1870320, CEG1870330, CEG1870340, CEG1870350, CEG1870360, CEG1870370, CEG1870380, CEG1870390, CEG1870401, CEG1870410, CEG1870420, CEG1870430, CEG1870440, CEG1870450, CEG1870460, CEG1870470, CEG1870480, CEG1870490, CEG1870501, CEG1870510
6 | 3.3.1.11.1.4 | CEG1870000 | Start of Piping Erection (UJA) | EPC | - | 969 | - | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1400100, CEG6076000 | CEG1880000, CEG2670000, CEG1880000, CEG1870100, CEG1870600, CEG1870170, CEG1870250, CEG1870330, CEG1870370
6 | 3.3.1.11.1.5 | CEG1880000 | Pipings - Cleaning, Hydrostatic Testing and Painting Phase 2 (UJA) | EPC | 420 | 1029 | 1448 | 124 | CEG1870000, CEG1870000, CEG1870100, CEG1870200, CEG1870300, CEG1870400, CEG1870500, CEG1870600, CEG1870700, CEG1870800, CEG1870900, CEG1870101, CEG1870110, CEG1870120, CEG1870130, CEG1870140, CEG1870150, CEG1870160, CEG1870170, CEG1870180, CEG1870190, CEG1870201, CEG1870210, CEG1870220, CEG1870230, CEG1870240, CEG1870250, CEG1870260, CEG1870270, CEG1870280, CEG1870290, CEG1870301, CEG1870310, CEG1870320, CEG1870330, CEG1870340, CEG1870350, CEG1870360, CEG1870370, CEG1870380, CEG1870390, CEG1870401, CEG1870410, CEG1870420, CEG1870430, CEG1870440, CEG1870450, CEG1870460, CEG1870470, CEG1870480, CEG1870490, CEG1870501, CEG1870510 | CEG1890000, CEG1900000, CEG1401000, CEG1890000, CEG6440000
6 | 3.3.1.11.1.6 | CEG1890000 | Pipings - Engineering Phase 2 (Documentation Closing) (UJA) | ETN | 245 | 1294 | 1538 | 124 | CEG1880000, CEG1880000 | CEG6340000
6 | 3.3.1.11.1.7 | CEG1401000 | Completion of the Erection of the Water/Steam Circuit in the LAB Nuclear Area (UJA/UJE) | EPC | - | - | 1448 | 304 | CEG1880000, CEG2310000, CEG6440000 | CEG6470000
5 | 3.3.1.11.2 | - | JA01 Erection Area |  | 450 | 969 | 1418 | 124
6 | 3.3.1.11.2.1 | CEG1870100 | Piping - Erection JA000 (UJA) | EPC | 120 | 969 | 1088 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870000, CEG1400100 | CEG1880000, CEG1870200
6 | 3.3.1.11.2.2 | CEG1870200 | Piping - Erection JA001 (UJA) | EPC | 120 | 969 | 1088 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870100, CEG1400100 | CEG1880000
6 | 3.3.1.11.2.3 | CEG1870600 | Piping - Erection JA012 (UJA) | EPC | 300 | 969 | 1268 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870000, CEG1400100 | CEG1880000, CEG1870500, CEG1870700, CEG1870101
6 | 3.3.1.11.2.4 | CEG1870170 | Piping - Erection JA041 (UJA) | EPC | 420 | 969 | 1388 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870000, CEG1400100 | CEG1880000, CEG1870180
6 | 3.3.1.11.2.5 | CEG1870101 | Piping - Erection JA022 (UJA) | EPC | 270 | 999 | 1268 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870600, CEG1400100 | CEG1880000, CEG1870140
6 | 3.3.1.11.2.6 | CEG1870500 | Piping - Erection JA011 (UJA) | EPC | 300 | 999 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870600, CEG1400100 | CEG1880000, CEG1870900
6 | 3.3.1.11.2.7 | CEG1870140 | Piping - Erection JA032 (UJA) | EPC | 270 | 1029 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870101, CEG1400100 | CEG1880000
6 | 3.3.1.11.2.8 | CEG1870700 | Piping - Erection JA013 (UJA) | EPC | 240 | 1059 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870600, CEG1400100 | CEG1880000, CEG1870800, CEG1870110
6 | 3.3.1.11.2.9 | CEG1870180 | Piping - Erection JA042 (UJA) | EPC | 300 | 1059 | 1358 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870170, CEG1400100 | CEG1880000, CEG1870190
6 | 3.3.1.11.2.10 | CEG1870190 | Piping - Erection JA043 (UJA) | EPC | 300 | 1089 | 1388 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870180, CEG1400100 | CEG1880000, CEG1870201, CEG1870210
6 | 3.3.1.11.2.11 | CEG1870900 | Piping - Erection JA021 (UJA) | EPC | 210 | 1119 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870500, CEG1400100 | CEG1880000, CEG1870130
6 | 3.3.1.11.2.12 | CEG1870110 | Piping - Erection JA023 (UJA) | EPC | 210 | 1119 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870700, CEG1400100 | CEG1880000, CEG1870150
6 | 3.3.1.11.2.13 | CEG1870150 | Piping - Erection JA033 (UJA) | EPC | 210 | 1119 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870110, CEG1400100 | CEG1880000
6 | 3.3.1.11.2.14 | CEG1870210 | Piping - Erection JA121 (UJA) | EPC | 210 | 1119 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870190, CEG1400100 | CEG1880000, CEG1870220
6 | 3.3.1.11.2.15 | CEG1870800 | Piping - Erection JA015 (UJA) | EPC | 150 | 1149 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870700, CEG1400100 | CEG1880000, CEG1870120, CEG1870300
6 | 3.3.1.11.2.16 | CEG1870130 | Piping - Erection JA031 (UJA) | EPC | 180 | 1149 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870900, CEG1400100 | CEG1880000
6 | 3.3.1.11.2.17 | CEG1870220 | Piping - Erection JA122 (UJA) | EPC | 210 | 1149 | 1358 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870210, CEG1400100 | CEG1880000, CEG1870230
6 | 3.3.1.11.2.18 | CEG1870300 | Piping - Erection JA002 (UJA) | EPC | 120 | 1179 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870800, CEG1400100 | CEG1880000, CEG1870400
6 | 3.3.1.11.2.19 | CEG1870120 | Piping - Erection JA025 (UJA) | EPC | 120 | 1209 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870800, CEG1400100 | CEG1880000, CEG1870160
6 | 3.3.1.11.2.20 | CEG1870400 | Piping - Erection JA003 (UJA) | EPC | 120 | 1239 | 1358 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870300, CEG1400100 | CEG1880000
6 | 3.3.1.11.2.21 | CEG1870160 | Piping - Erection JA035 (UJA) | EPC | 120 | 1239 | 1358 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870120, CEG1400100 | CEG1880000
6 | 3.3.1.11.2.22 | CEG1870201 | Piping - Erection JA045 (UJA) | EPC | 150 | 1269 | 1418 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870190, CEG1400100 | CEG1880000
5 | 3.3.1.11.3 | - | JA02 Erection Area |  | 330 | 969 | 1298 | 124
6 | 3.3.1.11.3.1 | CEG1870250 | Piping - Erection JA061 (UJA) | EPC | 240 | 969 | 1208 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870000, CEG1400100 | CEG1880000, CEG1870240, CEG1870280
6 | 3.3.1.11.3.2 | CEG1870290 | Piping - Erection JA093 (UJA) | EPC | 180 | 1029 | 1208 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870280, CEG1400100 | CEG1880000
6 | 3.3.1.11.3.3 | CEG1870280 | Piping - Erection JA092 (UJA) | EPC | 240 | 1029 | 1268 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870250, CEG1400100 | CEG1880000, CEG1870290
6 | 3.3.1.11.3.4 | CEG1870240 | Piping - Erection JA006 (UJA) | EPC | 150 | 1059 | 1208 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870250, CEG1400100 | CEG1880000, CEG1870260, CEG1870270, CEG1870490
6 | 3.3.1.11.3.5 | CEG1870270 | Piping - Erection JA091 (UJA) | EPC | 120 | 1089 | 1208 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870240, CEG1400100 | CEG1880000
6 | 3.3.1.11.3.6 | CEG1870260 | Piping - Erection JA062 (UJA) | EPC | 90 | 1119 | 1208 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870240, CEG1400100 | CEG1880000
6 | 3.3.1.11.3.7 | CEG1870230 | Piping - Erection JA005 (UJA) | EPC | 120 | 1179 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870220, CEG1400100 | CEG1880000
5 | 3.3.1.11.4 | - | JA03 Erection Area |  | 420 | 969 | 1388 | 124
6 | 3.3.1.11.4.1 | CEG1870330 | Piping - Erection JA054 (UJA) | EPC | 330 | 969 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870000, CEG1400100 | CEG1880000, CEG1870320, CEG1870340
6 | 3.3.1.11.4.2 | CEG1870320 | Piping - Erection JA053 (UJA) | EPC | 270 | 999 | 1268 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870330, CEG1400100 | CEG1880000, CEG1870310
6 | 3.3.1.11.4.3 | CEG1870310 | Piping - Erection JA052 (UJA) | EPC | 270 | 1029 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870320, CEG1400100 | CEG1880000, CEG1870301
6 | 3.3.1.11.4.4 | CEG1870301 | Piping - Erection JA051 (UJA) | EPC | 300 | 1029 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870310, CEG1400100 | CEG1880000
6 | 3.3.1.11.4.5 | CEG1870340 | Piping - Erection JA055 (UJA) | EPC | 270 | 1119 | 1388 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870330, CEG1400100 | CEG1880000, CEG1870350
6 | 3.3.1.11.4.6 | CEG1870350 | Piping - Erection JA056 (UJA) | EPC | 180 | 1179 | 1358 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870340, CEG1400100 | CEG1880000
5 | 3.3.1.11.5 | - | JA04 Erection Area |  | 450 | 969 | 1418 | 124
6 | 3.3.1.11.5.1 | CEG1870370 | Piping - Erection JA102 (UJA) | EPC | 360 | 969 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870000, CEG1400100 | CEG1880000, CEG1870380
6 | 3.3.1.11.5.2 | CEG1870380 | Piping - Erection JA103 (UJA) | EPC | 330 | 999 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870370, CEG1400100 | CEG1880000, CEG1870360
6 | 3.3.1.11.5.3 | CEG1870360 | Piping - Erection JA101 (UJA) | EPC | 300 | 1029 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870380, CEG1400100 | CEG1880000, CEG1870390, CEG1870401
6 | 3.3.1.11.5.4 | CEG1870390 | Piping - Erection JA104 (UJA) | EPC | 360 | 1059 | 1418 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870360, CEG1400100 | CEG1880000
5 | 3.3.1.11.6 | - | JA05 Erection Area |  | 300 | 1029 | 1328 | 124
6 | 3.3.1.11.6.1 | CEG1870401 | Piping - Erection JA007 (UJA) | EPC | 300 | 1029 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870360, CEG4976000, CEG1400100 | CEG1880000, CEG1870410
6 | 3.3.1.11.6.2 | CEG1870410 | Piping - Erection JA008 (UJA) | EPC | 270 | 1059 | 1328 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870401, CEG1400100 | CEG1880000, CEG1870420
6 | 3.3.1.11.6.3 | CEG1870420 | Piping - Erection JA014 (UJA) | EPC | 180 | 1089 | 1268 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870410, CEG1400100 | CEG1880000, CEG1870430
6 | 3.3.1.11.6.4 | CEG1870460 | Piping - Erection JA111 (UJA) | EPC | 120 | 1119 | 1238 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870440, CEG1400100 | CEG1880000, CEG1870470
6 | 3.3.1.11.6.5 | CEG1870470 | Piping - Erection JA112 (UJA) | EPC | 120 | 1119 | 1238 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870460, CEG1400100 | CEG1880000
6 | 3.3.1.11.6.6 | CEG1870430 | Piping - Erection JA024 (UJA) | EPC | 180 | 1119 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870420, CEG1400100 | CEG1880000, CEG1870440
6 | 3.3.1.11.6.7 | CEG1870440 | Piping - Erection JA034 (UJA) | EPC | 180 | 1119 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870430, CEG1400100 | CEG1880000, CEG1870450, CEG1870460
6 | 3.3.1.11.6.8 | CEG1870450 | Piping - Erection JA044 (UJA) | EPC | 150 | 1149 | 1298 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870440, CEG1400100 | CEG1880000
5 | 3.3.1.11.7 | - | JA06 Erection Area |  | 300 | 1059 | 1358 | 124
6 | 3.3.1.11.7.1 | CEG1870490 | Piping - Erection JA009 (UJA) | EPC | 150 | 1059 | 1208 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870240, CEG1400100 | CEG1880000, CEG1870510, CEG1870501
6 | 3.3.1.11.7.2 | CEG1870510 | Piping - Erection JA114 (UJA) | EPC | 90 | 1089 | 1178 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870490, CEG1400100 | CEG1880000
6 | 3.3.1.11.7.3 | CEG1870501 | Piping - Erection JA113 (UJA) | EPC | 210 | 1149 | 1358 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870490, CEG1400100 | CEG1880000, CEG1870480
6 | 3.3.1.11.7.4 | CEG1870480 | Piping - Erection JA004 (UJA) | EPC | 180 | 1179 | 1358 | 124 | CEG1750000, CEG1860000, CEG1400000, CEG1410000, CEG0916700, CEG1870501, CEG1400100 | CEG1880000
3 | 3.3.2 | - | Erection in the Reactor Building (Annulus) (UJB) |  | - | Anterior ao EPC | 1598 | 124
4 | 3.3.2.1 | - | Mechanical Components (UJB) |  | 440 | 682 | 1121 | 470
5 | 3.3.2.1.1 | CEG2324000 | Erection of Mechanical Components (UJB) | EPC | 440 | 682 | 1121 | 470 | CEG2322000, CEG1140000, CEG9230000, CEG9271300, CEG9272500, CEG9272650, CEG2323000, CEG1140100 | CEG1190000
4 | 3.3.2.2 | - | Piping Systems (UJB) |  | - | Anterior ao EPC | 1598 | 124
5 | 3.3.2.2.1 | - | UJB General Erection Area |  | - | Anterior ao EPC | 1598 | 124
6 | 3.3.2.2.1.1 | CEG1155000 | Piping - Erection Units Design Released (UJB) | ETN | - | - | Anterior ao EPC | 124 | CEG1347000, CEGPA01500 | CEG1160100
6 | 3.3.2.2.1.2 | CEG1160100 | Piping - Engineering Phase 1 (Workbook) (UJB) Remaining | EPC | 640 | 152 | 791 | 124 | CEG1155000, CEG6680000 | CEG1170000, CEG1170000
6 | 3.3.2.2.1.3 | CEG1170000 | Piping - Prefabrication (UJB) | EPC | 640 | 237 | 876 | 124 | CEG1160000, CEG1160000, CEG6610000, CEG6680000, CEG6680000, CEG1160100, CEG1160100 | CEG1180000, CEG1180100, CEG1180200, CEG1180300, CEG1180400, CEG1180500, CEG1180600, CEG1180700, CEG1180800, CEG1180900, CEG1180101, CEG1180110, CEG1180120, CEG1180130, CEG1180140, CEG1180150, CEG1180160, CEG1180170, CEG1180180, CEG1180190, CEG1180201, CEG1180210, CEG1180220, CEG1180230, CEG1180240, CEG1180250, CEG1180260, CEG1180270, CEG1180280, CEG1180290, CEG1180301, CEG1180310, CEG1180320, CEG1180330, CEG1180340, CEG1180350, CEG1180360, CEG1180370, CEG1180380, CEG1180390, CEG1180401, CEG1180410, CEG1180420, CEG1180430, CEG1180440, CEG1180450, CEG1180460, CEG1180470, CEG1180480, CEG1180490, CEG1180501, CEG1180510, CEG1180520, CEG1180530
6 | 3.3.2.2.1.4 | CEG1180000 | Start of Piping Erection (JNK/... ) (UJB) | EPC | - | 877 | - | 124 | CEG1170000, CEG1140100 | CEG1190000, CEG2660000, CEG1190000, CEG1391000, CEG1180100, CEG1180200, CEG1180300, CEG1180400, CEG1180600, CEG1180700, CEG1180270, CEG1180320, CEG1180340, CEG1180420, CEG1180380, CEG1180490
6 | 3.3.2.2.1.5 | CEG1190000 | Pipes - Cleaning, Hydrostatic Testing and Painting Phase 2 (UJB) | EPC | 411 | 1087 | 1497 | 124 | CEG1180000, CEG1180000, CEG1180100, CEG1180100, CEG1180200, CEG1180200, CEG1180300, CEG1180300, CEG1180400, CEG1180400, CEG1180500, CEG1180500, CEG1180600, CEG1180600, CEG1180700, CEG1180700, CEG1180800, CEG1180800, CEG1180900, CEG1180900, CEG1180101, CEG1180101, CEG1180110, CEG1180110, CEG1180120, CEG1180130, CEG1180130, CEG1180140, CEG1180140, CEG1180150, CEG1180150, CEG1180160, CEG1180160, CEG1180170, CEG1180180, CEG1180180, CEG1180190, CEG1180190, CEG1180201, CEG1180201, CEG1180210, CEG1180210, CEG1180220, CEG1180230, CEG1180230, CEG1180240, CEG1180240, CEG1180250, CEG1180250, CEG1180260, CEG1180260, CEG1180270, CEG1180270, CEG1180280, CEG1180280, CEG1180290, CEG1180290, CEG1180301, CEG1180301, CEG1180310, CEG1180310, CEG1180320, CEG1180320, CEG1180330, CEG1180330, CEG1180340, CEG1180340, CEG1180350, CEG1180350, CEG1180360, CEG1180360, CEG1180370, CEG1180370, CEG1180380, CEG1180380, CEG1180390, CEG1180390, CEG1180401, CEG1180410, CEG1180420, CEG1180420, CEG1180430, CEG1180430, CEG1180440, CEG1180440, CEG1180450, CEG1180450, CEG1180460, CEG1180460, CEG1180470, CEG1180470, CEG1180480, CEG1180480, CEG1180490, CEG1180490, CEG1180501, CEG1180501, CEG1180510, CEG1180510, CEG1180520, CEG1180530, CEG2324000 | CEG1200000, CEG1590000, CEG1200000
6 | 3.3.2.2.1.6 | CEG1200000 | Piping - Engineering Phase 2 (Documentation Closing) (UJB) | EPC | 300 | 1299 | 1598 | 124 | CEG1190000, CEG1190000 | CEG6340000
5 | 3.3.2.2.2 | - | JB01 Erection Area |  | 450 | 877 | 1326 | 265
6 | 3.3.2.2.2.1 | CEG1180700 | Piping - Erection JB018 (JNK/... ) (UJB) | EPC | 30 | 877 | 906 | 124 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000, CEG1180900, CEG1180101, CEG1180800, CEG1180110
6 | 3.3.2.2.2.2 | CEG1180100 | Piping - Erection JB001 (JNK/... ) (UJB) | EPC | 210 | 877 | 1086 | 295 | CEG1170000, CEG1180000, CEG1391000, CEG5016000 | CEG1190000, CEG1190000, CEG1180520
6 | 3.3.2.2.2.3 | CEG1180270 | Piping - Erection JB111 (JNK/... ) (UJB) | EPC | 240 | 877 | 1116 | 214 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000, CEG1180280
6 | 3.3.2.2.2.4 | CEG1180200 | Piping - Erection JB011 (JNK/... ) (UJB) | EPC | 240 | 877 | 1116 | 304 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.5 | CEG1180300 | Piping - Erection JB012 (JNK/... ) (UJB) | EPC | 240 | 877 | 1116 | 304 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.6 | CEG1180400 | Piping - Erection JB013 (JNK/... ) (UJB) | EPC | 330 | 877 | 1206 | 124 | CEG1170000, CEG1180000, CEG5076000 | CEG1190000, CEG1190000, CEG1180500
6 | 3.3.2.2.2.7 | CEG1180500 | Piping - Erection JB016 (JNK/... ) (UJB) | EPC | 330 | 877 | 1206 | 124 | CEG1170000, CEG1180400 | CEG1190000, CEG1190000, CEG1180600
6 | 3.3.2.2.2.8 | CEG1180800 | Piping - Erection JB021 (JNK/... ) (UJB) | EPC | 240 | 907 | 1146 | 124 | CEG1170000, CEG1180700 | CEG1190000, CEG1190000, CEG1180130
6 | 3.3.2.2.2.9 | CEG1180900 | Piping - Erection JB022 (JNK/... ) (UJB) | EPC | 240 | 907 | 1146 | 214 | CEG1170000, CEG1180700 | CEG1190000, CEG1190000, CEG1180140
6 | 3.3.2.2.2.10 | CEG1180280 | Piping - Erection JB121 (JNK/... ) (UJB) | EPC | 240 | 907 | 1146 | 214 | CEG1170000, CEG1180270 | CEG1190000, CEG1190000, CEG1180290
6 | 3.3.2.2.2.11 | CEG1180110 | Piping - Erection JB026 (JNK/... ) (UJB) | EPC | 240 | 907 | 1146 | 274 | CEG1170000, CEG1180700 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.12 | CEG1180101 | Piping - Erection JB023 (JNK/... ) (UJB) | EPC | 330 | 907 | 1236 | 214 | CEG1170000, CEG1180700 | CEG1190000, CEG1190000, CEG1180150
6 | 3.3.2.2.2.13 | CEG1180260 | Piping - Erection JB081 (JNK/... ) (UJB) | EPC | 150 | 937 | 1086 | 244 | CEG1170000, CEG1180230 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.14 | CEG1180130 | Piping - Erection JB031 (JNK/... ) (UJB) | EPC | 180 | 937 | 1116 | 124 | CEG1170000, CEG1180800 | CEG1190000, CEG1190000, CEG1180180, CEG1180230
6 | 3.3.2.2.2.15 | CEG1180230 | Piping - Erection JB051 (JNK/... ) (UJB) | EPC | 180 | 937 | 1116 | 124 | CEG1170000, CEG1180130 | CEG1190000, CEG1190000, CEG1180240, CEG1180250, CEG1180260, CEG1180310
6 | 3.3.2.2.2.16 | CEG1180140 | Piping - Erection JB032 (JNK/... ) (UJB) | EPC | 240 | 937 | 1176 | 214 | CEG1170000, CEG1180900 | CEG1190000, CEG1190000, CEG1180190
6 | 3.3.2.2.2.17 | CEG1180160 | Piping - Erection JB036 (JNK/... ) (UJB) | EPC | 240 | 937 | 1176 | 214 | CEG1170000, CEG1180150 | CEG1190000, CEG1190000, CEG1180210
6 | 3.3.2.2.2.18 | CEG1180290 | Piping - Erection JB131 (JNK/... ) (UJB) | EPC | 240 | 937 | 1176 | 214 | CEG1170000, CEG1180280 | CEG1190000, CEG1190000, CEG1180301
6 | 3.3.2.2.2.19 | CEG1180150 | Piping - Erection JB033 (JNK/... ) (UJB) | EPC | 360 | 937 | 1296 | 214 | CEG1170000, CEG1180101 | CEG1190000, CEG1190000, CEG1180201, CEG1180160
6 | 3.3.2.2.2.20 | CEG1180250 | Piping - Erection JB071 (JNK/... ) (UJB) | EPC | 360 | 937 | 1296 | 244 | CEG1170000, CEG1180230 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.21 | CEG1180180 | Piping - Erection JB041 (JNK/... ) (UJB) | EPC | 180 | 967 | 1146 | 214 | CEG1170000, CEG1180130 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.22 | CEG1180190 | Piping - Erection JB042 (JNK/... ) (UJB) | EPC | 240 | 967 | 1206 | 214 | CEG1170000, CEG1180140 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.23 | CEG1180301 | Piping - Erection JB141 (JNK/... ) (UJB) | EPC | 240 | 967 | 1206 | 214 | CEG1170000, CEG1180290 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.24 | CEG1180201 | Piping - Erection JB043 (JNK/... ) (UJB) | EPC | 330 | 967 | 1296 | 214 | CEG1170000, CEG1180150 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.25 | CEG1180210 | Piping - Erection JB046 (JNK/... ) (UJB) | EPC | 330 | 967 | 1296 | 214 | CEG1170000, CEG1180160 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.26 | CEG1180600 | Piping - Erection JB017 (JNK/... ) (UJB) | EPC | 210 | 1057 | 1266 | 124 | CEG1170000, CEG1180000, CEG1180500 | CEG1190000, CEG1190000, CEG1180120
6 | 3.3.2.2.2.27 | CEG1180240 | Piping - Erection JB061 (JNK/... ) (UJB) | EPC | 210 | 1057 | 1266 | 124 | CEG1170000, CEG1180230 | CEG1190000, CEG1190000
6 | 3.3.2.2.2.28 | CEG1180120 | Piping - Erection JB027 (JNK/... ) (UJB) | EPC | 240 | 1087 | 1326 | 265 | CEG1170000, CEG1180600 | CEG1190000, CEG1180170
6 | 3.3.2.2.2.29 | CEG1180170 | Piping - Erection JB037 (JNK/... ) (UJB) | EPC | 180 | 1117 | 1296 | 295 | CEG1170000, CEG1180120 | CEG1190000, CEG1180220
6 | 3.3.2.2.2.30 | CEG1180220 | Piping - Erection JB047 (JNK/... ) (UJB) | EPC | 120 | 1147 | 1266 | 325 | CEG1170000, CEG1180170 | CEG1190000
5 | 3.3.2.2.3 | - | JB02 Erection Area |  | 450 | 877 | 1326 | 154
6 | 3.3.2.2.3.1 | CEG1180340 | Piping - Erection JB102 (JNK/... ) (UJB) | EPC | 270 | 877 | 1146 | 124 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000, CEG1180350
6 | 3.3.2.2.3.2 | CEG1180320 | Piping - Erection JB082 (JNK/... ) (UJB) | EPC | 150 | 907 | 1056 | 244 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000, CEG1180330
6 | 3.3.2.2.3.3 | CEG1180350 | Piping - Erection JB103 (JNK/... ) (UJB) | EPC | 240 | 907 | 1146 | 124 | CEG1170000, CEG1180340 | CEG1190000, CEG1190000, CEG1180360
6 | 3.3.2.2.3.4 | CEG1180330 | Piping - Erection JB101 (JNK/... ) (UJB) | EPC | 300 | 937 | 1236 | 244 | CEG1170000, CEG1180320 | CEG1190000, CEG1190000
6 | 3.3.2.2.3.5 | CEG1180360 | Piping - Erection JB104 (JNK/... ) (UJB) | EPC | 240 | 967 | 1206 | 124 | CEG1170000, CEG1180350 | CEG1190000, CEG1190000, CEG1180370
6 | 3.3.2.2.3.6 | CEG1180310 | Piping - Erection JB052 (JNK/... ) (UJB) | EPC | 210 | 1057 | 1266 | 124 | CEG1170000, CEG1180230 | CEG1190000, CEG1190000
6 | 3.3.2.2.3.7 | CEG1180370 | Piping - Erection JB105 (JNK/... ) (UJB) | EPC | 270 | 1057 | 1326 | 124 | CEG1170000, CEG1180360 | CEG1190000, CEG1190000
5 | 3.3.2.2.4 | - | JB03 Erection Area |  | 420 | 877 | 1296 | 295
6 | 3.3.2.2.4.1 | CEG1180420 | Piping - Erection JB091 (JNK/... ) (UJB) | EPC | 30 | 877 | 906 | 304 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000
6 | 3.3.2.2.4.2 | CEG1180380 | Piping - Erection JB014 (JNK/... ) (UJB) | EPC | 210 | 997 | 1206 | 154 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000, CEG1180390, CEG1180440, CEG1180530
6 | 3.3.2.2.4.3 | CEG1180440 | Piping - Erection JB108 (JNK/... ) (UJB) | EPC | 300 | 997 | 1296 | 184 | CEG1170000, CEG1180380 | CEG1190000, CEG1190000
6 | 3.3.2.2.4.4 | CEG1180430 | Piping - Erection JB106 (JNK/... ) (UJB) | EPC | 90 | 1027 | 1116 | 154 | CEG1170000, CEG1180390 | CEG1190000, CEG1190000
6 | 3.3.2.2.4.5 | CEG1180390 | Piping - Erection JB024 (JNK/... ) (UJB) | EPC | 180 | 1027 | 1206 | 154 | CEG1170000, CEG1180380 | CEG1190000, CEG1190000, CEG1180430, CEG1180401
6 | 3.3.2.2.4.6 | CEG1180410 | Piping - Erection JB044 (JNK/... ) (UJB) | EPC | 180 | 1087 | 1266 | 325 | CEG1170000, CEG1180401 | CEG1190000
6 | 3.3.2.2.4.7 | CEG1180401 | Piping - Erection JB034 (JNK/... ) (UJB) | EPC | 210 | 1087 | 1296 | 295 | CEG1170000, CEG1180390 | CEG1190000, CEG1180410
5 | 3.3.2.2.5 | - | JB04 Erection Area |  | 360 | 937 | 1296 | 184
6 | 3.3.2.2.5.1 | CEG1180490 | Piping - Erection JB107 (JNK/... ) (UJB) | EPC | 120 | 937 | 1056 | 124 | CEG1170000, CEG1180000 | CEG1190000, CEG1190000, CEG1180501, CEG1180450
6 | 3.3.2.2.5.2 | CEG1180450 | Piping - Erection JB015 (JNK/... ) (UJB) | EPC | 210 | 967 | 1176 | 124 | CEG1170000, CEG1180490 | CEG1190000, CEG1190000, CEG1180460
6 | 3.3.2.2.5.3 | CEG1180460 | Piping - Erection JB025 (JNK/... ) (UJB) | EPC | 210 | 997 | 1206 | 124 | CEG1170000, CEG1180450 | CEG1190000, CEG1190000, CEG1180470
6 | 3.3.2.2.5.4 | CEG1180501 | Piping - Erection JB109 (JNK/... ) (UJB) | EPC | 300 | 997 | 1296 | 184 | CEG1170000, CEG1180490 | CEG1190000, CEG1190000, CEG1180510
6 | 3.3.2.2.5.5 | CEG1180470 | Piping - Erection JB035 (JNK/... ) (UJB) | EPC | 240 | 1057 | 1296 | 124 | CEG1170000, CEG1180460 | CEG1190000, CEG1190000, CEG1180480
6 | 3.3.2.2.5.6 | CEG1180480 | Piping - Erection JB045 (JNK/... ) (UJB) | EPC | 240 | 1057 | 1296 | 124 | CEG1170000, CEG1180470 | CEG1190000, CEG1190000
5 | 3.3.2.2.6 | - | JB05 Erection Area |  | 210 | 997 | 1206 | 184
6 | 3.3.2.2.6.1 | CEG1180510 | Piping - Erection JB002 (JNK/... ) (UJB) | EPC | 210 | 997 | 1206 | 184 | CEG1170000, CEG1180501 | CEG1190000, CEG1190000
5 | 3.3.2.2.7 | - | JB06 Erection Area |  | 270 | 1087 | 1356 | 235
6 | 3.3.2.2.7.1 | CEG1180520 | Piping - Erection JB003 (JNK/... ) (UJB) | EPC | 210 | 1087 | 1296 | 295 | CEG1170000, CEG1180100, CEG7046000 | CEG1190000
6 | 3.3.2.2.7.2 | CEG1180530 | Piping - Erection JB004 (JNK/... ) (UJB) | EPC | 150 | 1207 | 1356 | 231 | CEG1170000, CEG1180380 | CEG1190000, CEG6120000, CEG6100000
3 | 3.3.3 | - | Erection of Common Systems UJA / UJB / UKA / UJE |  | 1084 | 335 | 1418 | 235
4 | 3.3.3.1 | - | Ventilation Systems (UJA / UJB) |  | 630 | 382 | 1011 | 370
5 | 3.3.3.1.1 | CEG2720000 | Erection of KLB/KLA (UJB/UJA) Ventilation Ducts and Components | EPC | 630 | 382 | 1011 | 370 | CEG1140000, CEG6680000, CEG6680000, CEG1140100 | CEG2730000
4 | 3.3.3.2 | - | Electrical and I&C Systems and Equipment (UJA/ UJB / UJE) |  | 542 | 877 | 1418 | 235
5 | 3.3.3.2.1 | CEG2660000 | Erection of Electrical and I&C Equipment and Systems (UJB) | EPC | 542 | 877 | 1418 | 214 | CEG1180000, CEG2711000 | CEG2690000, CEG6590000
5 | 3.3.3.2.2 | CEG2680000 | Erection of Electrical and I&C Equipment and Systems (UJE) | EPC | 182 | 939 | 1120 | 422 | CEG2300000, CEG2300100, CEG2300200, CEG2300300, CEG2300400 | CEG3190000, CEG6590000, CEG2690000
5 | 3.3.3.2.3 | CEG2670000 | Erection of Electrical and I&C Equipment and Systems (UJA) | EPC | 390 | 969 | 1358 | 265 | CEG1870000, CEG2710000, CEG1422000 | CEG2690000, CEG6590000, CEG6590000
5 | 3.3.3.2.4 | CEG2690000 | Erection of CZ Physical Protection (UJB/ UJA/ UJE) | EPC | 120 | 1299 | 1418 | 235 | CEG2660000, CEG2670000, CEG2680000 | CEG2920000, CEG4260000, CEG1310000, CEG2780000
4 | 3.3.3.3 | - | Temporary Ventilation (UJA / UJB / UKA Controlled Area) |  | 240 | 335 | 574 | 516
5 | 3.3.3.3.1 | CEG2710000 | Erection of Temporary Ventilation and Cooling Systems (UJA) | EPC | 120 | 335 | 454 | 516 | CEG6680000, CEG6680000, CEG9272200, CEG9272230, CEG9272260, CEG9272290, CEG9272320, CEG9272350, CEG9272410 | CEG2670000, CEG2711000
5 | 3.3.3.3.2 | CEG2712000 | Erection of Temporary Ventilation and Cooling Systems (UKA) | EPC | 120 | 452 | 571 | 309 | CEGLIC0000 | CEG2770000
5 | 3.3.3.3.3 | CEG2711000 | Erection of Temporary Ventilation and Cooling Systems (UJB) | EPC | 120 | 455 | 574 | 516 | CEGLIC0000, CEG2710000 | CEG2660000
3 | 3.3.4 | - | Erection in the Reactor Auxiliary Building (UKA) and Discharge Chimney (UKH) |  | - | Anterior ao EPC | 1418 | 304
4 | 3.3.4.1 | - | Mechanical Components (UKA) |  | 450 | 542 | 991 | 606
5 | 3.3.4.1.1 | CEG2260000 | Erection of Mechanical Components (UKA) - Except KP | EPC | 360 | 542 | 901 | 309 | CEG2030000, CEG2050000, CEG2060000, CEG2080000, CEG2020000, CEG2040000, CEG2100000, CEG2120000, CEG2090000, CEG2165000, CEG9230000 | CEG2220000, CEG2800000, CEG2770000
5 | 3.3.4.1.2 | CEG5410000 | Erection of Mechanical Components (UKA) - KP | EPC | 300 | 692 | 991 | 606 | CEG2030000, CEG2050000, CEG2080000, CEG2140000 | CEG5390000, CEG2780000
4 | 3.3.4.2 | - | Piping Systems (UKA) |  | - | Anterior ao EPC | 1261 | 461
5 | 3.3.4.2.1 | - | General Erection Area |  | - | Anterior ao EPC | 1261 | 461
6 | 3.3.4.2.1.1 | CEG2190000 | Piping - Erection Units Design Released (UKA) | ETN | - | - | Anterior ao EPC | 469 | CEG1347000, CEGPA01500 | CEG2200000, CEG5370000
6 | 3.3.4.2.1.2 | CEG2200000 | Piping - Engineering Phase 1 (Workbook) - Except KP (UKA) | EPC | 760 | 152 | 911 | 541 | CEG2190000, CEG6680000 | CEG2210000, CEG6160000
6 | 3.3.4.2.1.3 | CEG5370000 | Piping - Engineering Phase 1 (Workbook) KP (UKA) | EPC | 420 | 204 | 623 | 469 | CEG2190000, CEG6680000, CEG6700000, CEG6680000 | CEG5380000, CEG2210000
6 | 3.3.4.2.1.4 | CEG2210000 | Piping - Prefabrication - Except KP (UKA) | EPC | 760 | 242 | 1001 | 671 | CEG2200000, CEG5370000, CEG6620000, CEG6680000, CEG6680000 | CEG2220000
6 | 3.3.4.2.1.5 | CEG5380000 | Piping - Prefabrication - KP (UKA) | EPC | 350 | 444 | 793 | 469 | CEG5370000, CEG6620000 | CEG5390000, CEG2220100, CEG2220200, CEG2220300, CEG2220400, CEG2220500, CEG2220600, CEG2220700, CEG2220800, CEG2220900, CEG2220101, CEG2220110, CEG2220120, CEG2220130, CEG2220140, CEG2220150, CEG2220160, CEG2220170, CEG2220180, CEG2220190, CEG2220201, CEG2220210, CEG2220220, CEG2220230, CEG2220240, CEG2220250, CEG2220260, CEG2220270, CEG2220280, CEG2220290, CEG2220301, CEG2220310, CEG2220320, CEG2220330, CEG2220340, CEG2220350, CEG2220360, CEG2220370, CEG2220380, CEG2220390, CEG2220401, CEG2220410, CEG2220420, CEG2220430, CEG2220440, CEG2220450, CEG2220460, CEG2220470, CEG2220480, CEG2220490, CEG2220501, CEG2220510, CEG2220520, CEG2220530, CEG2220540, CEG2220550, CEG2220560, CEG2220730, CEG2220740, CEG2220750, CEG2220760, CEG2220770, CEG2220780, CEG2220570, CEG2220580, CEG2220590, CEG2220601, CEG2220610, CEG2220620, CEG2220630, CEG2220640, CEG2220650, CEG2220660, CEG2220670, CEG2220680, CEG2220690, CEG2220701, CEG2220710, CEG2220720
6 | 3.3.4.2.1.6 | CEG2220000 | Start of Piping Erection - Except KP (UKA) | EPC | - | 542 | - | 461 | CEG2210000, CEG2160000, CEG2060000, CEG2260000, CEG6680000, CEG6680000, CEG2161000 | CEG2230000, CEG2230000, CEG2220200, CEG2220300, CEG2220400, CEG2220500, CEG2220900, CEG2220101, CEG2220120
6 | 3.3.4.2.1.7 | CEG2230000 | Piping - Cleaning, Hydrostatic Testing and Painting Phase 2 - Except KP (UKA) | EPC | 450 | 752 | 1201 | 461 | CEG2220000, CEG2220000, CEG2220100, CEG2220100, CEG2220200, CEG2220200, CEG2220300, CEG2220300, CEG2220400, CEG2220400, CEG2220500, CEG2220500, CEG2220600, CEG2220600, CEG2220700, CEG2220700, CEG2220800, CEG2220800, CEG2220900, CEG2220900, CEG2220101, CEG2220101, CEG2220110, CEG2220110, CEG2220120, CEG2220120, CEG2220130, CEG2220140, CEG2220140, CEG2220150, CEG2220150, CEG2220160, CEG2220160, CEG2220170, CEG2220170, CEG2220180, CEG2220180, CEG2220190, CEG2220190, CEG2220201, CEG2220201, CEG2220210, CEG2220210, CEG2220220, CEG2220220, CEG2220230, CEG2220240, CEG2220240, CEG2220250, CEG2220250, CEG2220260, CEG2220260, CEG2220270, CEG2220280, CEG2220280, CEG2220290, CEG2220290, CEG2220301, CEG2220301, CEG2220310, CEG2220310, CEG2220320, CEG2220330, CEG2220340, CEG2220350, CEG2220350, CEG2220360, CEG2220360, CEG2220370, CEG2220370, CEG2220380, CEG2220380, CEG2220390, CEG2220390, CEG2220401, CEG2220401, CEG2220410, CEG2220410, CEG2220420, CEG2220430, CEG2220440, CEG2220450, CEG2220450, CEG2220460, CEG2220470, CEG2220480, CEG2220480, CEG2220490, CEG2220490, CEG2220501, CEG2220501, CEG2220510, CEG2220510, CEG2220520, CEG2220520, CEG2220530, CEG2220540, CEG2220540, CEG2220550, CEG2220550, CEG2220560, CEG2220730, CEG2220740, CEG2220750, CEG2220760, CEG2220770, CEG2220780, CEG2220570, CEG2220580, CEG2220590, CEG2220601, CEG2220610, CEG2220620, CEG2220630, CEG2220640, CEG2220650, CEG2220660, CEG2220670, CEG2220680, CEG2220690, CEG2220701, CEG2220710, CEG2220720 | CEG2240000, CEG2240000
6 | 3.3.4.2.1.8 | CEG5390000 | Start of Piping Erection - KP (UKA) | EPC | - | 767 | - | 606 | CEG5380000, CEG5410000, CEG2115000, CEG9272710 | CEG5400000, CEG5400000
6 | 3.3.4.2.1.9 | CEG5400000 | Piping - Cleaning, Hydrostatic Testing, Painting and Insulation Phase 2 - KP (UKA) | EPC | 260 | 852 | 1111 | 551 | CEG5390000, CEG5390000, CEG2220100, CEG2220100, CEG2220200, CEG2220200, CEG2220300, CEG2220300, CEG2220400, CEG2220400, CEG2220500, CEG2220500, CEG2220600, CEG2220600, CEG2220700, CEG2220700, CEG2220800, CEG2220800, CEG2220900, CEG2220900, CEG2220101, CEG2220101, CEG2220110, CEG2220110, CEG2220120, CEG2220120, CEG2220130, CEG2220130, CEG2220140, CEG2220140, CEG2220150, CEG2220150, CEG2220160, CEG2220160, CEG2220170, CEG2220170, CEG2220180, CEG2220180, CEG2220190, CEG2220190, CEG2220201, CEG2220201, CEG2220210, CEG2220210, CEG2220220, CEG2220220, CEG2220230, CEG2220230, CEG2220240, CEG2220240, CEG2220250, CEG2220250, CEG2220260, CEG2220260, CEG2220270, CEG2220270, CEG2220280, CEG2220280, CEG2220290, CEG2220290, CEG2220301, CEG2220301, CEG2220310, CEG2220310, CEG2220320, CEG2220320, CEG2220330, CEG2220330, CEG2220340, CEG2220340, CEG2220350, CEG2220350, CEG2220360, CEG2220360, CEG2220370, CEG2220370, CEG2220380, CEG2220380, CEG2220390, CEG2220390, CEG2220401, CEG2220401, CEG2220410, CEG2220410, CEG2220420, CEG2220420, CEG2220430, CEG2220430, CEG2220440, CEG2220440, CEG2220450, CEG2220450, CEG2220460, CEG2220460, CEG2220470, CEG2220470, CEG2220480, CEG2220480, CEG2220490, CEG2220490, CEG2220501, CEG2220501, CEG2220510, CEG2220510, CEG2220520, CEG2220520, CEG2220530, CEG2220530, CEG2220540, CEG2220540, CEG2220550, CEG2220550, CEG2220560, CEG2220560, CEG2220730, CEG2220740, CEG2220750, CEG2220760, CEG2220770, CEG2220780, CEG2220570, CEG2220580, CEG2220590, CEG2220601, CEG2220610, CEG2220620, CEG2220630, CEG2220640, CEG2220650, CEG2220660, CEG2220670, CEG2220680, CEG2220690, CEG2220701, CEG2220710, CEG2220720 | CEG2250000, CEG2240000
6 | 3.3.4.2.1.10 | CEG2240000 | Piping - Engineering Phase 2 (Documentation Closing) (UKA) | EPC | 334 | 928 | 1261 | 461 | CEG2230000, CEG5400000, CEG2230000 | CEG6340000
5 | 3.3.4.2.2 | - | KA01 Erection Area |  | 330 | 542 | 871 | 581
6 | 3.3.4.2.2.1 | CEG2220200 | Piping - Erection - KA004 (UKA) | EPC | 60 | 542 | 601 | 461 | CEG5380000, CEG2220000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220140
6 | 3.3.4.2.2.2 | CEG2220101 | Piping - Erection - KA031 (UKA) | EPC | 60 | 542 | 601 | 641 | CEG5380000, CEG2220000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.2.3 | CEG2220300 | Piping - Erection - KA011 (UKA) | EPC | 90 | 542 | 631 | 551 | CEG5380000, CEG2220000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220110
6 | 3.3.4.2.2.4 | CEG2220900 | Piping - Erection - KA021 (UKA) | EPC | 120 | 542 | 661 | 641 | CEG5380000, CEG2220000, CEG6056000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.2.5 | CEG2220500 | Piping - Erection - KA013 (UKA) | EPC | 240 | 542 | 781 | 491 | CEG5380000, CEG2220000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220600
6 | 3.3.4.2.2.6 | CEG2220400 | Piping - Erection - KA012 (UKA) | EPC | 240 | 542 | 781 | 641 | CEG5380000, CEG2220000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.2.7 | CEG2220120 | Piping - Erection - KA061 (UKA) | EPC | 330 | 542 | 871 | 581 | CEG5380000, CEG2220000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220260
6 | 3.3.4.2.2.8 | CEG2220600 | Piping - Erection - KA014 (UKA) | EPC | 150 | 572 | 721 | 491 | CEG5380000, CEG2220500 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220700, CEG2220800
6 | 3.3.4.2.2.9 | CEG2220800 | Piping - Erection - KA016 (UKA) | EPC | 90 | 602 | 691 | 491 | CEG5380000, CEG2220600 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220390
6 | 3.3.4.2.2.10 | CEG2220700 | Piping - Erection - KA015 (UKA) | EPC | 60 | 617 | 676 | 506 | CEG5380000, CEG2220600 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220100
6 | 3.3.4.2.2.11 | CEG2220110 | Piping - Erection - KA041 (UKA) | EPC | 90 | 632 | 721 | 551 | CEG5380000, CEG2220300 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.2.12 | CEG2220100 | Piping - Erection - KA001 (UKA) | EPC | 180 | 677 | 856 | 506 | CEG5380000, CEG2220700 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220130
5 | 3.3.4.2.3 | - | KA02 Erection Area |  | 450 | 572 | 1021 | 581
6 | 3.3.4.2.3.1 | CEG2220260 | Piping - Erection - KA131 (UKA) | EPC | 450 | 572 | 1021 | 581 | CEG5380000, CEG2220120 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.3.2 | CEG2220220 | Piping - Erection - KA071 (UKA) | EPC | 60 | 602 | 661 | 581 | CEG5380000, CEG2220190 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.3.3 | CEG2220170 | Piping - Erection - KA033 (UKA) | EPC | 120 | 602 | 721 | 461 | CEG5380000, CEG2220160 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220180
6 | 3.3.4.2.3.4 | CEG2220190 | Piping - Erection - KA051 (UKA) | EPC | 120 | 602 | 721 | 461 | CEG5380000, CEG2220180 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220201, CEG2220210, CEG2220220, CEG2220250
6 | 3.3.4.2.3.5 | CEG2220160 | Piping - Erection - KA022 (UKA) | EPC | 150 | 602 | 751 | 461 | CEG5380000, CEG2220140 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220170, CEG2220280
6 | 3.3.4.2.3.6 | CEG2220180 | Piping - Erection - KA034 (UKA) | EPC | 150 | 602 | 751 | 461 | CEG5380000, CEG2220170 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220230, CEG2220190
6 | 3.3.4.2.3.7 | CEG2220140 | Piping - Erection - KA005 (UKA) | EPC | 210 | 602 | 811 | 461 | CEG5380000, CEG2220200, CEG4956000, CEG4996000 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220150, CEG2220160
6 | 3.3.4.2.3.8 | CEG2220250 | Piping - Erection - KA101 (UKA) | EPC | 300 | 602 | 901 | 581 | CEG5380000, CEG2220190 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.3.9 | CEG2220210 | Piping - Erection - KA063 (UKA) | EPC | 90 | 632 | 721 | 461 | CEG5380000, CEG2220190 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220240
6 | 3.3.4.2.3.10 | CEG2220150 | Piping - Erection - KA017 (UKA) | EPC | 180 | 632 | 811 | 491 | CEG5380000, CEG2220140 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220360
6 | 3.3.4.2.3.11 | CEG2220201 | Piping - Erection - KA062 (UKA) | EPC | 150 | 662 | 811 | 521 | CEG5380000, CEG2220190 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.3.12 | CEG2220130 | Piping - Erection - KA002 (UKA) | EPC | 120 | 722 | 841 | 551 | CEG5380000, CEG2220100 | CEG5400000, CEG5400000, CEG2230000, CEG2220570
6 | 3.3.4.2.3.13 | CEG2220240 | Piping - Erection - KA073 (UKA) | EPC | 180 | 722 | 901 | 461 | CEG5380000, CEG2220210 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220320
6 | 3.3.4.2.3.14 | CEG2220230 | Piping - Erection - KA072 (UKA) | EPC | 60 | 752 | 811 | 621 | CEG5380000, CEG2220180 | CEG5400000, CEG5400000, CEG2230000
5 | 3.3.4.2.4 | - | KA03 Erection Area |  | 360 | 632 | 991 | 561
6 | 3.3.4.2.4.1 | CEG2220310 | Piping - Erection - KA064 (UKA) | EPC | 30 | 632 | 661 | 551 | CEG5380000, CEG2220301 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.4.2 | CEG2220290 | Piping - Erection - KA032 (UKA) | EPC | 90 | 632 | 721 | 551 | CEG5380000, CEG2220280 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220301
6 | 3.3.4.2.4.3 | CEG2220280 | Piping - Erection - KA023 (UKA) | EPC | 180 | 632 | 811 | 551 | CEG5380000, CEG2220160 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220270, CEG2220290, CEG2220350
6 | 3.3.4.2.4.4 | CEG2220301 | Piping - Erection - KA052 (UKA) | EPC | 180 | 632 | 811 | 551 | CEG5380000, CEG2220290 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220310
6 | 3.3.4.2.4.5 | CEG2220350 | Piping - Erection - KA111 (UKA) | EPC | 360 | 632 | 991 | 551 | CEG5380000, CEG2220280 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.4.6 | CEG2220270 | Piping - Erection - KA003 (UKA) | EPC | 90 | 722 | 811 | 651 | CEG5380000, CEG2220280 | CEG5400000, CEG5400000, CEG2230000
6 | 3.3.4.2.4.7 | CEG2220340 | Piping - Erection - KA076 (UKA) | EPC | 150 | 782 | 931 | 591 | CEG5380000, CEG2220320 | CEG5400000, CEG5400000, CEG2230000
6 | 3.3.4.2.4.8 | CEG2220320 | Piping - Erection - KA074 (UKA) | EPC | 180 | 782 | 961 | 561 | CEG5380000, CEG2220240 | CEG5400000, CEG5400000, CEG2230000, CEG2220330, CEG2220340, CEG2220760
6 | 3.3.4.2.4.9 | CEG2220330 | Piping - Erection - KA075 (UKA) | EPC | 180 | 812 | 991 | 561 | CEG5380000, CEG2220320 | CEG5400000, CEG5400000, CEG2230000
5 | 3.3.4.2.5 | - | KA04 Erection Area |  | 360 | 692 | 1051 | 531
6 | 3.3.4.2.5.1 | CEG2220380 | Piping - Erection - KA026 (UKA) | EPC | 30 | 692 | 721 | 491 | CEG5380000, CEG2220370 | CEG5400000, CEG5400000, CEG2230000, CEG2230000
6 | 3.3.4.2.5.2 | CEG2220410 | Piping - Erection - KA053 (UKA) | EPC | 60 | 692 | 751 | 491 | CEG5380000, CEG2220401 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220420, CEG2220440
6 | 3.3.4.2.5.3 | CEG2220501 | Piping - Erection - KA132 (UKA) | EPC | 90 | 692 | 781 | 491 | CEG5380000, CEG2220490 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220510
6 | 3.3.4.2.5.4 | CEG2220401 | Piping - Erection - KA037 (UKA) | EPC | 120 | 692 | 811 | 491 | CEG5380000, CEG2220390 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220410
6 | 3.3.4.2.5.5 | CEG2220370 | Piping - Erection - KA024 (UKA) | EPC | 150 | 692 | 841 | 491 | CEG5380000, CEG2220360 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220380
6 | 3.3.4.2.5.6 | CEG2220360 | Piping - Erection - KA019 (UKA) | EPC | 180 | 692 | 871 | 491 | CEG5380000, CEG2220150 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220370, CEG2220540
6 | 3.3.4.2.5.7 | CEG2220390 | Piping - Erection - KA036 (UKA) | EPC | 180 | 692 | 871 | 491 | CEG5380000, CEG2220800 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220401, CEG2220450
6 | 3.3.4.2.5.8 | CEG2220520 | Piping - Erection - KA134 (UKA) | EPC | 270 | 692 | 961 | 491 | CEG5380000, CEG2220510 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220530
6 | 3.3.4.2.5.9 | CEG2220490 | Piping - Erection - KA121 (UKA) | EPC | 330 | 692 | 1021 | 491 | CEG5380000, CEG2220480 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220501
6 | 3.3.4.2.5.10 | CEG2220510 | Piping - Erection - KA133 (UKA) | EPC | 330 | 692 | 1021 | 491 | CEG5380000, CEG2220501 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220520
6 | 3.3.4.2.5.11 | CEG2220450 | Piping - Erection - KA065 (UKA) | EPC | 360 | 692 | 1051 | 491 | CEG5380000, CEG2220390 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220460, CEG2220480
6 | 3.3.4.2.5.12 | CEG2220480 | Piping - Erection - KA102 (UKA) | EPC | 360 | 692 | 1051 | 491 | CEG5380000, CEG2220450 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220490
6 | 3.3.4.2.5.13 | CEG2220420 | Piping - Erection - KA054 (UKA) | EPC | 60 | 722 | 781 | 591 | CEG5380000, CEG2220410 | CEG5400000, CEG5400000, CEG2230000, CEG2220430
6 | 3.3.4.2.5.14 | CEG2220530 | Piping - Erection - KA171 (UKA) | EPC | 210 | 722 | 931 | 651 | CEG5380000, CEG2220520 | CEG5400000, CEG5400000, CEG2230000
6 | 3.3.4.2.5.15 | CEG2220440 | Piping - Erection - KA056 (UKA) | EPC | 180 | 752 | 931 | 621 | CEG5380000, CEG2220410 | CEG5400000, CEG5400000, CEG2230000
6 | 3.3.4.2.5.16 | CEG2220460 | Piping - Erection - KA081 (UKA) | EPC | 210 | 752 | 961 | 591 | CEG5380000, CEG2220450 | CEG5400000, CEG5400000, CEG2230000, CEG2220470
6 | 3.3.4.2.5.17 | CEG2220430 | Piping - Erection - KA055 (UKA) | EPC | 30 | 782 | 811 | 591 | CEG5380000, CEG2220420 | CEG5400000, CEG5400000, CEG2230000
6 | 3.3.4.2.5.18 | CEG2220470 | Piping - Erection - KA082 (UKA) | EPC | 150 | 782 | 931 | 591 | CEG5380000, CEG2220460 | CEG5400000, CEG5400000, CEG2230000
5 | 3.3.4.2.6 | - | KA05 Erection Area |  | 270 | 692 | 961 | 561
6 | 3.3.4.2.6.1 | CEG2220550 | Piping - Erection - KA025 (UKA) | EPC | 90 | 692 | 781 | 491 | CEG5380000, CEG2220540 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220560
6 | 3.3.4.2.6.2 | CEG2220540 | Piping - Erection - KA018 (UKA) | EPC | 270 | 692 | 961 | 491 | CEG5380000, CEG2220360 | CEG5400000, CEG5400000, CEG2230000, CEG2230000, CEG2220550
6 | 3.3.4.2.6.3 | CEG2220560 | Piping - Erection - KA112 (UKA) | EPC | 150 | 752 | 901 | 621 | CEG5380000, CEG2220550 | CEG5400000, CEG5400000, CEG2230000
5 | 3.3.4.2.7 | - | KA06 Erection Area |  | 210 | 842 | 1051 | 551
6 | 3.3.4.2.7.1 | CEG2220570 | Piping - Erection - KA035 (UKA) | EPC | 30 | 842 | 871 | 551 | CEG5380000, CEG2220130 | CEG5400000, CEG2230000, CEG2220580
6 | 3.3.4.2.7.2 | CEG2220590 | Piping - Erection - KA058 (UKA) | EPC | 60 | 842 | 901 | 551 | CEG5380000, CEG2220580 | CEG5400000, CEG2230000, CEG2220601, CEG2220610
6 | 3.3.4.2.7.3 | CEG2220610 | Piping - Erection - KA092 (UKA) | EPC | 60 | 842 | 901 | 551 | CEG5380000, CEG2220590 | CEG5400000, CEG2230000, CEG2220620
6 | 3.3.4.2.7.4 | CEG2220580 | Piping - Erection - KA057 (UKA) | EPC | 90 | 842 | 931 | 551 | CEG5380000, CEG2220570 | CEG5400000, CEG2230000, CEG2220590
6 | 3.3.4.2.7.5 | CEG2220630 | Piping - Erection - KA094 (UKA) | EPC | 90 | 842 | 931 | 551 | CEG5380000, CEG2220620 | CEG5400000, CEG2230000, CEG2220640
6 | 3.3.4.2.7.6 | CEG2220680 | Piping - Erection - KA163 (UKA) | EPC | 120 | 842 | 961 | 551 | CEG5380000, CEG2220670 | CEG5400000, CEG2230000, CEG2220690, CEG2220710
6 | 3.3.4.2.7.7 | CEG2220620 | Piping - Erection - KA093 (UKA) | EPC | 180 | 842 | 1021 | 551 | CEG5380000, CEG2220610 | CEG5400000, CEG2230000, CEG2220630
6 | 3.3.4.2.7.8 | CEG2220640 | Piping - Erection - KA103 (UKA) | EPC | 210 | 842 | 1051 | 551 | CEG5380000, CEG2220630 | CEG5400000, CEG2230000, CEG2220650
6 | 3.3.4.2.7.9 | CEG2220650 | Piping - Erection - KA123 (UKA) | EPC | 210 | 842 | 1051 | 551 | CEG5380000, CEG2220640 | CEG5400000, CEG2230000, CEG2220660
6 | 3.3.4.2.7.10 | CEG2220660 | Piping - Erection - KA124 (UKA) | EPC | 210 | 842 | 1051 | 551 | CEG5380000, CEG2220650 | CEG5400000, CEG2230000, CEG2220670
6 | 3.3.4.2.7.11 | CEG2220670 | Piping - Erection - KA141 (UKA) | EPC | 210 | 842 | 1051 | 551 | CEG5380000, CEG2220660 | CEG5400000, CEG2230000, CEG2220680, CEG2220701
6 | 3.3.4.2.7.12 | CEG2220690 | Piping - Erection - KA164 (UKA) | EPC | 210 | 842 | 1051 | 551 | CEG5380000, CEG2220680 | CEG5400000, CEG2230000
6 | 3.3.4.2.7.13 | CEG2220601 | Piping - Erection - KA091 (UKA) | EPC | 30 | 872 | 901 | 701 | CEG5380000, CEG2220590 | CEG5400000, CEG2230000
5 | 3.3.4.2.8 | - | KA07 Erection Area |  | 210 | 842 | 1051 | 551
6 | 3.3.4.2.8.1 | CEG2220720 | Piping - Erection - KA162 (UKA) | EPC | 150 | 842 | 991 | 611 | CEG5380000, CEG2220710 | CEG5400000, CEG2230000
6 | 3.3.4.2.8.2 | CEG2220710 | Piping - Erection - KA161 (UKA) | EPC | 210 | 842 | 1051 | 551 | CEG5380000, CEG2220680 | CEG5400000, CEG2230000, CEG2220720
6 | 3.3.4.2.8.3 | CEG2220701 | Piping - Erection - KA143 (UKA) | EPC | 90 | 872 | 961 | 551 | CEG5380000, CEG2220670 | CEG5400000, CEG2230000, CEG2220730
5 | 3.3.4.2.9 | - | KA08 Erection Area |  | 150 | 902 | 1051 | 551
6 | 3.3.4.2.9.1 | CEG2220740 | Piping - Erection - KA181 (UKA) | EPC | 30 | 902 | 931 | 551 | CEG5380000, CEG2220730 | CEG5400000, CEG2230000, CEG2220750
6 | 3.3.4.2.9.2 | CEG2220730 | Piping - Erection - KA142 (UKA) | EPC | 120 | 902 | 1021 | 551 | CEG5380000, CEG2220701 | CEG5400000, CEG2230000, CEG2220740
6 | 3.3.4.2.9.3 | CEG2220750 | Piping - Erection - KA191 (UKA) | EPC | 150 | 902 | 1051 | 551 | CEG5380000, CEG2220740 | CEG5400000, CEG2230000
5 | 3.3.4.2.10 | - | KA09 Erection Area |  | 60 | 962 | 1021 | 581
6 | 3.3.4.2.10.1 | CEG2220760 | Piping - Erection - KA077 (UKA) | EPC | 60 | 962 | 1021 | 581 | CEG5380000, CEG2220320 | CEG5400000, CEG2230000, CEG2220770
6 | 3.3.4.2.10.2 | CEG2220770 | Piping - Erection - KA095 (UKA) | EPC | 60 | 962 | 1021 | 581 | CEG5380000, CEG2220760 | CEG5400000, CEG2230000, CEG2220780
6 | 3.3.4.2.10.3 | CEG2220780 | Piping - Erection - KA192 (UKA) | EPC | 60 | 962 | 1021 | 581 | CEG5380000, CEG2220770 | CEG5400000, CEG2230000
4 | 3.3.4.3 | - | Electrical and I&C Systems and Equipment (UKA) |  | 847 | 572 | 1418 | 235
5 | 3.3.4.3.1 | CEG2770000 | Erection of Electrical and I&C Equipment and Systems (UKA) | EPC | 486 | 572 | 1057 | 309 | CEG2260000, CEG2712000 | CEG2780000, CEG2790000
5 | 3.3.4.3.2 | CEG2780000 | Erection of CZ Physical Protection (UKA) | EPC | 120 | 1299 | 1418 | 235 | CEG2770000, CEG5410000, CEG2690000 | CEG1310000, CEG2790000
4 | 3.3.4.4 | - | Ventilation Systems (UKA) |  | 540 | 572 | 1111 | 309
5 | 3.3.4.4.1 | CEG2800000 | Erection of KLE (UKA) Ventilation Ducts and Components | EPC | 540 | 572 | 1111 | 309 | CEG2260000, CEG6680000, CEG6680000 | CEG2810000
4 | 3.3.4.5 | - | Piping Systems (UKH) |  | 390 | 732 | 1121 | 601
5 | 3.3.4.5.1 | CEG6160000 | Piping - Engineering Phase 1 (Workbook) (UKH/UKY) | EPC | 180 | 732 | 911 | 541 | CEG2200000 | CEG6170000, CEG6170000
5 | 3.3.4.5.2 | CEG6170000 | Piping - Prefabrication (UKH / UKY) | EPC | 180 | 822 | 1001 | 541 | CEG6160000, CEG6160000 | CEG6200000, CEG4910290, CEG4910290
5 | 3.3.4.5.3 | CEG6200000 | Start of Piping Erection (UKH/UKY) | EPC | - | 912 | - | 541 | CEG6170000, CEG9271570, CEG9272590, CEG9272620 | CEG6180000, CEG6180000, CEG4910290
5 | 3.3.4.5.4 | CEG4910290 | Piping - Erection KH001 (UKH / UKY) | EPC | 120 | 912 | 1031 | 541 | CEG6170000, CEG6170000, CEG6200000 | CEG6180000, CEG6180000
5 | 3.3.4.5.5 | CEG6180000 | Piping - Cleaning, Hydrostatic Testing and Painting Phase 2 (UKH/UKY) | EPC | 100 | 962 | 1061 | 541 | CEG6200000, CEG6200000, CEG4910290, CEG4910290 | CEG6190000, CEG6190000, CEG2250000
5 | 3.3.4.5.6 | CEG6190000 | Piping - Engineering Phase 2 (Documentation Closing) (UKH / UKY) | EPC | 100 | 1022 | 1121 | 601 | CEG6180000, CEG6180000 | CEG6340000
3 | 3.3.5 | - | Erection in the Valve Compartment (UJE) and in the Equipment Lock and Gantry Structure (UJF) |  | 1025 | 249 | 1273 | 449
4 | 3.3.5.1 | - | Piping Systems (UJE) |  | 960 | 249 | 1208 | 514
5 | 3.3.5.1.1 | - | General Erection Area |  | 960 | 249 | 1208 | 514
6 | 3.3.5.1.1.1 | CEG2280000 | Piping - Erection Units Design Released (UJE) | ETN | - | 249 | - | 422 | CEG1347000, CEGPA01500 | CEG2290000
6 | 3.3.5.1.1.2 | CEG2290000 | Piping - Engineering Phase 1 (Workbook) (UJE) | EPC | 420 | 489 | 908 | 422 | CEG2280000, CEG6680000, CEG6680000 | CEG5340000, CEG5340000
6 | 3.3.5.1.1.3 | CEG5340000 | Piping - Prefabrication - Adjustment LAB/ LBA/ Valves (UJE) | EPC | 420 | 579 | 998 | 422 | CEG2290000, CEG2290000, CEG6630000 | CEG2300000, CEG2300100, CEG2300100, CEG2300200, CEG2300200, CEG2300300, CEG2300300, CEG2300400, CEG2300400
6 | 3.3.5.1.1.4 | CEG2310000 | Pipes - Cleaning, Hydrostatic Testing and Painting Phase 2 (UJE) | EPC | 240 | 909 | 1148 | 474 | CEG2300000, CEG2300000, CEG2300100, CEG2300100, CEG2300200, CEG2300200, CEG2300300, CEG2300300, CEG2300400, CEG2300400 | CEG2315000, CEG1401000, CEG2320000, CEG2315000
6 | 3.3.5.1.1.5 | CEG2315000 | Piping - Engineering Phase 2 (Documentation Closing) (UJE) | EPC | 240 | 969 | 1208 | 514 | CEG2310000, CEG2310000 | CEG6340000
5 | 3.3.5.1.2 | - | JE01 Erection Area |  | 300 | 819 | 1118 | 422
6 | 3.3.5.1.2.1 | CEG2300000 | Start of Piping Erection (UJE) | EPC | - | 819 | - | 422 | CEG1720000, CEG5340000, CEG6070000, CEG6076000 | CEG2310000, CEG2680000, CEG2310000, CEG2300100, CEG2300300
6 | 3.3.5.1.2.2 | CEG2300100 | Piping - Erection JE011 (UJE) | EPC | 240 | 819 | 1058 | 422 | CEG1720000, CEG5340000, CEG6070000, CEG5340000, CEG2300000 | CEG2310000, CEG2680000, CEG2310000, CEG2300200
6 | 3.3.5.1.2.3 | CEG2300300 | Piping - Erection JE013 (UJE) | EPC | 240 | 819 | 1058 | 422 | CEG1720000, CEG5340000, CEG6070000, CEG5340000, CEG2300000 | CEG2310000, CEG2680000, CEG2310000, CEG2300400
6 | 3.3.5.1.2.4 | CEG2300200 | Piping - Erection JE012 (UJE) | EPC | 240 | 879 | 1118 | 422 | CEG1720000, CEG5340000, CEG6070000, CEG5340000, CEG2300100 | CEG2310000, CEG2680000, CEG2310000
6 | 3.3.5.1.2.5 | CEG2300400 | Piping - Erection JE014 (UJE) | EPC | 240 | 879 | 1118 | 422 | CEG1720000, CEG5340000, CEG6070000, CEG5340000, CEG2300300 | CEG2310000, CEG2680000, CEG2310000
4 | 3.3.5.2 | - | Piping Systems (UJF) |  | 795 | 479 | 1273 | 449
5 | 3.3.5.2.1 | CEG6210000 | Piping - Engineering Phase 1 (Workbook) (UJF) | EPC | 420 | 479 | 898 | 584 | CEG6680000, CEG6680000 | CEG6250000, CEG6250000
5 | 3.3.5.2.2 | CEG6250000 | Piping - Prefabrication (UJF) | EPC | 420 | 569 | 988 | 584 | CEG6210000, CEG6210000 | CEG6220000, CEG6220000
5 | 3.3.5.2.3 | CEG6220000 | Piping - Erection (UJF) | EPC | 390 | 794 | 1183 | 449 | CEG6250000, CEG6060000, CEG6250000, CEG4996000 | CEG6230000, CEG6230000
5 | 3.3.5.2.4 | CEG6230000 | Pipes - Cleaning, Hydrostatic Testing and Painting Phase 2 (UJF) | EPC | 210 | 1004 | 1213 | 449 | CEG6220000, CEG6220000 | CEG6240000, CEG6240000
5 | 3.3.5.2.5 | CEG6240000 | Piping - Engineering Phase 2 (Documentation Closing) (UJF) | EPC | 210 | 1064 | 1273 | 449 | CEG6230000, CEG6230000 | CEG6340000
2 | 3.4 | - | Final Erection and Commissioning Services for Nuclear Area Systems |  | 741 | 1012 | 1752 | 0
3 | 3.4.1 | - | Piping Systems and Mechanical Components |  | 721 | 1032 | 1752 | 0
4 | 3.4.1.1 | CEG2250000 | Final Services of Erection and Commissioning of the Piping Systems and Mechanical Components (UKA/UKH) | EPC | 180 | 1032 | 1211 | 541 | CEG5400000, CEG1520000, CEG6180000, CEG9270220, CEG9270940, CEG9270970, CEG9271000, CEG9271030, CEG9271060, CEG9271090, CEG9271120, CEG9271150, CEG9270250, CEG9271180, CEG9271210, CEG9271240, CEG9271270, CEG9272470, CEG9272530 | CEG6470000, CEG6340000
4 | 3.4.1.2 | CEG2320000 | Final Services of Erection and Commissioning of the Piping Systems (UJE) | EPC | 130 | 1149 | 1278 | 474 | CEG1520000, CEG2310000 | CEG6470000, CEG6340000
4 | 3.4.1.3 | CEG1900000 | Final Services of Erection and Commissioning of the Piping Systems (UJA, except Primary Circuit) | EPC | 150 | 1449 | 1598 | 124 | CEG1880000, CEG1520000 | CEG6470000, CEG6340000
4 | 3.4.1.4 | CEG1590000 | Final Services of Erection and Commissioning of the Piping Systems (UJB) | EPC | 131 | 1498 | 1628 | 124 | CEG1190000, CEG1520000 | CEG6470000, CEG6340000
4 | 3.4.1.5 | CEG1650000 | Commissioning of FCB Fuel Refilling Machine (UJA) | EPC | 99 | 1654 | 1752 | 0 | CEG1640000, CEG1632000, CEG1634000, CEG1310000, CEG9274500 | CEG6470000
3 | 3.4.2 | - | Electrical and I&C Systems and Components |  | 481 | 1058 | 1538 | 214
4 | 3.4.2.1 | CEG2790000 | Final Services of Erection and Commissioning of the Electrical and I&C Sys. (UKA / UKH) | EPC | 386 | 1058 | 1443 | 309 | CEG2770000, CEG1520000, CEG2780000 | CEG6470000, CEG6340000
4 | 3.4.2.2 | CEG6590000 | Final Services of Erection and Commissioning of the Electrical and I&C Sys. (UJA / UJB / UJE)) | EPC | 450 | 1089 | 1538 | 214 | CEG2670000, CEG2660000, CEG2680000, CEG2670000 | CEG6340000, CEG6470000
3 | 3.4.3 | - | Ventilation Systems and Components |  | 432 | 1012 | 1443 | 309
4 | 3.4.3.1 | CEG2730000 | Final Services of Erection and Commissioning of the Ventilation Sys. KLB/KLA (UJB/ UJA) | EPC | 371 | 1012 | 1382 | 370 | CEG2720000, CEG1520000 | CEG6470000, CEG6340000
4 | 3.4.3.2 | CEG2810000 | Final Services of Erection and Commissioning of the Ventilation Sys. KLE (UKA / UKH) | EPC | 332 | 1112 | 1443 | 309 | CEG2800000, CEG1520000 | CEG6470000, CEG6340000
1 | 4 | - | ELECTRICAL AREA / DIESEL GENERATORS / TRANSFORMERS (UBA / UBP / ULB / Transformers) |  | - | Anterior ao EPC | 1556 | 226
2 | 4.1 | - | Civil Construction |  | 1156 | 106 | 1261 | 392
3 | 4.1.1 | - | Construction of the Emergency Power Building (ULB) |  | 789 | 151 | 939 | 714
4 | 4.1.1.1 | - | Concrete Structure (ULB) |  | 154 | 152 | 305 | 380
5 | 4.1.1.1.1 | CEG3391000 | Wall demolition, removal of diesel tank and positioning of material for the new tank | ADDITIONAL | 30 | 152 | 181 | 317 | CEG1460000, CEG9273815 | CEG3420000, CEG6010000, CEG3410000
5 | 4.1.1.1.2 | CEG3390010 | Concrete Structure between elev. +5.70m and +16.70m (ULB) | ADDITIONAL | 154 | 152 | 305 | 380 | CEG3389999, CEG9273815 | CEG3420000, CEG6010000, CEG3410000
4 | 4.1.1.2 | - | Finishing (ULB) |  | 668 | 272 | 939 | 714
5 | 4.1.1.2.1 | CEG3410000 | Civil Finishing Service phase 1/ Release Rooms (EU) for Erection up to elev. +5.70m (ULB) | EPC | 218 | 272 | 489 | 317 | CEG3400000, CEG3380000, CEG3390000, CEGPA03200, CEG3391000, CEG3390010 | CEG3420000, CEG4010000, CEG6410000
5 | 4.1.1.2.2 | CEG3420000 | Civil Finishing Service phase 1/ Release Rooms (EU) for Erection up to elev. +12.70m (ULB) | EPC | 291 | 332 | 622 | 354 | CEG3410000, CEG3390000, CEG3391000, CEG3390010 | CEG4070000, CEG3430000, CEG4010000
5 | 4.1.1.2.3 | CEG3430000 | Civil Finishing Services Final Phase (ULB) | EPC | 358 | 582 | 939 | 714 | CEG3420000, CEG6010000 | CEG1310000
4 | 4.1.1.3 | - | Steel Structure (ULB) |  | 759 | 151 | 909 | 714
5 | 4.1.1.3.1 | CEG5950000 | Release of the Steel Structure Design up to elev. +5.70m (ULB) | ETN | - | - | 151 | 714 | CEG1346000, CEGPA01500 | CEG6001000
5 | 4.1.1.3.2 | CEG6001000 | Erection of Steel Structures up to Elev. +5.70m (ULB) | EPC | 371 | 152 | 522 | 714 | CEG5950000, CEG3380000, CEGPA03200 | CEG6010000
5 | 4.1.1.3.3 | CEG6010000 | Erection of Steel Structures up to elev. +12.70m (ULB) | EPC | 387 | 523 | 909 | 714 | CEG3390000, CEG6000000, CEG3391000, CEG6001000, CEG3390010 | CEG3430000
3 | 4.1.2 | - | Construction of the Emergency Generators and Chilled Water Building (UBP) |  | 1153 | 106 | 1258 | 395
4 | 4.1.2.1 | - | Concrete Structure (UBP) |  | 424 | 152 | 575 | 482
5 | 4.1.2.1.1 | CEG2821000 | Foundation Slab and Walls and Slabs up to elevation +5.60m (UBP) | EPC | 299 | 152 | 450 | 395 | CEG2360000, CEG1346000, CEGPA03200, CEG9273700 | CEG2830000, CEG2850000, CEG6020000, CEG2850000, CEG3941000, CEG3991000
5 | 4.1.2.1.2 | CEG2830000 | Walls and Slabs between elevations +5.60m to +18.95m (UBP) | EPC | 207 | 369 | 575 | 482 | CEG2820000, CEG2821000 | CEG2860000, CEG6030000
4 | 4.1.2.2 | - | Finishing (UBP) |  | 1153 | 106 | 1258 | 395
5 | 4.1.2.2.1 | CEG2840000 | Release of the Civil Finishing Design up to elev. +5.60m (UBP) | ETN | - | - | 106 | 395 | CEG1346000, CEGPA01500 | CEG2850000
5 | 4.1.2.2.2 | CEG2850000 | Civil Finishing Service phase 1/ Lib. Rooms (EU) for Erection up to elev. +5.60m (UBP) | EPC | 164 | 347 | 510 | 395 | CEG2840000, CEG2820000, CEG2820000, CEG2821000, CEG2821000 | CEG2870000
5 | 4.1.2.2.3 | CEG2860000 | Civil Finishing Service phase 1/ Lib. Rooms (EU) for Erection up to elev. +18.95m (UBP) | EPC | 214 | 369 | 582 | 482 | CEG2830000 | CEG2870000, CEG2890000, CEG2950000, CEG6020000
5 | 4.1.2.2.4 | CEG2870000 | Civil Finishing Services Final Phase (UBP) | EPC | 638 | 621 | 1258 | 395 | CEG2860000, CEG6030000, CEG2850000 | CEG1310000
4 | 4.1.2.3 | - | Steel Structure (UBP) |  | 431 | 128 | 558 | 1065
5 | 4.1.2.3.1 | CEG5960000 | Release of the Steel Structure Design up to elev. +5.60m (UBP) | ETN | - | - | 128 | 1065 | CEG1346000, CEGPA01500 | CEG6020000
5 | 4.1.2.3.2 | CEG6020000 | Erection of Steel Structures up to elev. +5.60m (UBP) | EPC | 60 | 369 | 428 | 1065 | CEG5960000, CEG2820000, CEG2860000, CEG2821000 | CEG6030000
5 | 4.1.2.3.3 | CEG6030000 | Erection of Steel Structures up to elev. +18.85m (UBP) | EPC | 100 | 459 | 558 | 1065 | CEG2830000, CEG6020000 | CEG2870000
3 | 4.1.3 | - | Construction of Generator Transformer Structures (UBF) |  | 372 | 152 | 523 | 598
4 | 4.1.3.1 | - | Civil Construction / Structures and Finishing (UBF) |  | 372 | 152 | 523 | 598
5 | 4.1.3.1.1 | CEG4171000 | Concrete Foundation and Structure (UBF) | EPC | 98 | 152 | 249 | 571 | CEG1346000, CEGPA03200 | CEG4180000, CEG4120000, CEG4181000, CEG4121000
5 | 4.1.3.1.2 | CEG4181000 | Civil Finishing (UBF) | EPC | 273 | 251 | 523 | 598 | CEG4170000, CEGPA03200, CEG4171000 | CEG4230000, CEG4240000, CEG6420000, CEG4191000
3 | 4.1.4 | - | Construction of the Control Building (UBA/UBD) |  | 1110 | 152 | 1261 | 392
4 | 4.1.4.1 | - | Concrete Structure (UBA/UBD) |  | 74 | 152 | 225 | 947
5 | 4.1.4.1.1 | CEG2460000 | Walls and Slabs up to elevation. +35.40m (UBA) | ADDITIONAL | 49 | 152 | 200 | 947 | CEG1460000, CEG2459999, CEG9273815 | CEG2470000, CEG2540000
5 | 4.1.4.1.2 | CEG2470000 | Walls and Slabs up to elevation. +36.00m (UBA) | ADDITIONAL | 19 | 207 | 225 | 947 | CEG2460000 | CEG5990000, CEG2540000
4 | 4.1.4.2 | - | Finishing (UBA / UBD) |  | 1110 | 152 | 1261 | 392
5 | 4.1.4.2.1 | CEG2521000 | Civil Finishing Service phase 1/ Release Rooms (EU) for Erection up to elev. +10.71m (UBA) | ADDITIONAL | 168 | 152 | 319 | 362 | CEG2510000, CEG1460000, CEG9273815 | CEG2530000, CEG3640000, CEG3650000, CEG3660000, CEG1240000, CEG3740000, CEG5770000
5 | 4.1.4.2.2 | CEG2530000 | Civil Finishing Service phase 1/ Release Rooms (EU) for Erection up to elev. +26.45m (UBA) | ADDITIONAL | 238 | 320 | 557 | 362 | CEG2390000, CEG2520000, CEG2430000, CEG2420000, CEG2521000 | CEG2540000, CEG3655000, CEG1441000
5 | 4.1.4.2.3 | CEG2540000 | Civil Finishing Services Final Phase (UBA) | EPC | 762 | 500 | 1261 | 392 | CEG2530000, CEG2470000, CEG2440000, CEG2450000, CEG2460000, CEGPA03200 | CEG1310000
4 | 4.1.4.3 | - | Steel Structure (UBA / UBD) |  | 555 | 152 | 706 | 947
5 | 4.1.4.3.1 | CEG5981000 | Erection of Steel Structures up to elev. +10.71m (UBA) | ADDITIONAL | 420 | 152 | 571 | 1021 | CEG5940000, CEG2430000, CEG1460000, CEG9273815 | CEG5990000
5 | 4.1.4.3.2 | CEG5990000 | Erection of Steel Structures up to elev. +28.85m (UBA) | ADDITIONAL | 481 | 226 | 706 | 947 | CEG2470000, CEG5980000, CEG1460000, CEG5981000, CEG9273815 | CEG1310000
3 | 4.1.5 | - | Construction of Unit Auxiliary Transformer Structures (UBE) |  | 371 | 180 | 550 | 571
4 | 4.1.5.1 | - | Civil Construction / Structures and Finishing (UBE) |  | 371 | 180 | 550 | 571
5 | 4.1.5.1.1 | CEG4121000 | Concrete Foundation and Structure (UBE) | EPC | 98 | 180 | 277 | 571 | CEG3300000, CEG4170000, CEGPA03200, CEG4171000 | CEG4130000, CEG4131000
5 | 4.1.5.1.2 | CEG4131000 | Civil Finishing (UBE) | EPC | 273 | 278 | 550 | 571 | CEG4120000, CEGPA03200, CEG4121000 | CEG4141000
3 | 4.1.6 | - | Construction of Structures for External Network Transformer (UBC) |  | 91 | 152 | 242 | 707
4 | 4.1.6.1 | - | Civil Construction / Structures and Finishing (UBC) |  | 91 | 152 | 242 | 707
5 | 4.1.6.1.1 | CEG4090000 | Civil Finishing (UBC) | EPC | 91 | 152 | 242 | 707 | CEG4080000, CEGPA03200 | CEG4100000
2 | 4.2 | - | Electromechanical Erection in Buildings (UBA / UBP / ULB / Transformers) |  | - | Anterior ao EPC | 1481 | 301
3 | 4.2.1 | - | Erection in the Control Building (UBA/UBD) |  | - | Anterior ao EPC | 1481 | 271
4 | 4.2.1.1 | - | Servers and Communication Network (I&C) (UBA) |  | 90 | 791 | 880 | 872
5 | 4.2.1.1.1 | CEG3700000 | Erection of Servers and I&C Communication Networks (UBA) | EPC | 90 | 791 | 880 | 872 | CEG3680000, CEG3730000 | CEG5710000
4 | 4.2.1.2 | - | Ventilation System (UBA) |  | 666 | 152 | 817 | 438
5 | 4.2.1.2.1 | CEG5720000 | Erection of Phase 1 Ventilation Ducts (UBA) for Environmental Control I&C Panel Rooms and Switchgears (UBA) | EPC | 215 | 152 | 366 | 403 | CEG1230000, CEG9272440, CEG9272380, CEG9271810, CEG9271510, CEG9272800, CEG9272830, CEG9272860, CEG9272920, CEG9271840 | CEG3650000, CEG3640000, CEG3660000, CEG3655000, CEG3670000, CEG3680000, CEG4360000, CEG3730000
5 | 4.2.1.2.2 | CEG3710000 | Erection of SAC Ventilation Ducts (UBA) | EPC | 450 | 272 | 721 | 438 | CEG1230000, CEG3705000 | CEG3720000, CEG3525000
5 | 4.2.1.2.3 | CEG3720000 | Erection of QKC Ventilation Components (UBA) | EPC | 396 | 422 | 817 | 438 | CEG3710000, CEG3706000, CEG6700000, CEG6700000 | CEG3525000
4 | 4.2.1.3 | - | Temporary Ventilation (I&C, CW and Server Panel Rooms) (UBA) |  | 90 | 397 | 486 | 403
5 | 4.2.1.3.1 | CEG3730000 | Erection and Commissioning of the Temporary Coolant Unit (UBA) (Use of Permanent Ducts) | EPC | 90 | 397 | 486 | 403 | CEG5720000 | CEG3650000, CEG3640000, CEG3655000, CEG3670000, CEG3680000, CEG4360000, CEG5540000, CEG5600000, CEG5550000, CEG5640000, CEG5520000, CEG5700000, CEG5610000, CEG5620000, CEG5650000, CEG5630000, CEG5500000, CEG5510000, CEG5530000, CEG5560000, CEG5570000, CEG5580000, CEG5680000, CEG5690000, CEG5590000, CEG5660000, CEG5670000, CEG5740000, CEG3700000, CEG1441000
4 | 4.2.1.4 | - | Piping Systems (UBA - QKC) |  | - | Anterior ao EPC | 665 | 1057
5 | 4.2.1.4.1 | CEG4820000 | Piping - Released Design (UBA) | ETN | - | - | Anterior ao EPC | 561 | CEG1347000, CEGPA01500 | CEG4830000, CEG4830100
5 | 4.2.1.4.2 | CEG4830100 | Piping - Engineering Phase 1 (Workbook) (UBA) Remaining | EPC | 379 | 152 | 530 | 561 | CEG4820000, CEG6700000 | CEG4840000, CEG5760000, CEG4840000
5 | 4.2.1.4.3 | CEG4840000 | Piping - Prefabrication (UBA - QKC) | EPC | 180 | 381 | 560 | 872 | CEG4830000, CEG5800000, CEG4830000, CEG4830100, CEG4830100 | CEG3740000, CEG3740000
5 | 4.2.1.4.4 | CEG3740000 | Piping - Erection BA001 to BA010 (UBA - QKC) | EPC | 180 | 441 | 620 | 872 | CEG4840000, CEG2520000, CEG4840000, CEG6016000, CEG7026000, CEG6036000, CEG5056000, CEG9273310, CEG9273340, CEG9273370, CEG9273400, CEG9273430, CEG9273460, CEG9273490, CEG9273520, CEG9273550, CEG9273580, CEG9273610, CEG2521000 | CEG3680000, CEG4860000, CEG4860000
5 | 4.2.1.4.5 | CEG4860000 | Piping - Cleaning, Hydrostatic Testing and Painting Phase 2 (UBA - QKC) | EPC | 60 | 591 | 650 | 1057 | CEG3740000, CEG3740000 | CEG4850000, CEG4850000
5 | 4.2.1.4.6 | CEG4850000 | Piping - Engineering Phase 2 (Documentation Closing) (UBA - QKC) | EPC | 30 | 636 | 665 | 1057 | CEG4860000, CEG4860000 | CEG6350000
4 | 4.2.1.5 | - | Fire Network Piping Systems (UBA) |  | 292 | 322 | 613 | 1109
5 | 4.2.1.5.1 | CEG5760000 | Piping - Prefabrication of the Fire Network (UBA) | EPC | 180 | 322 | 501 | 418 | CEG5750000, CEG4830000, CEG3735000, CEG4830100 | CEG5770000, CEG5770000
5 | 4.2.1.5.2 | CEG5770000 | Piping - Erection of Fire Network BA001 to BA010 (UBA) | EPC | 180 | 382 | 561 | 418 | CEG5760000, CEG5760000, CEG2520000, CEG9273160, CEG9272950, CEG2521000 | CEG5780000, CEG5780000, CEG1016140
5 | 4.2.1.5.3 | CEG5780000 | Piping - Cleaning, Hydrostatic Testing and Painting Phase 2 - Fire Network - (UBA) | EPC | 60 | 532 | 591 | 1109 | CEG5770000, CEG5770000 | CEG5790000, CEG5790000
5 | 4.2.1.5.4 | CEG5790000 | Piping - Engineering Phase 2 (Documentation Closing) Fire Network (UBA) | EPC | 30 | 584 | 613 | 1109 | CEG5780000, CEG5780000 | CEG6350000
4 | 4.2.1.6 | - | Lighting Systems and Power Take-offs (UBA) |  | 365 | 272 | 636 | 583
5 | 4.2.1.6.1 | CEG4400000 | Erection (including cabling) of Lighting Systems and Power Take-offs (UBA) | EPC | 365 | 272 | 636 | 583 | CEG4380000, CEG4390000, CEG4410000, CEG6700000, CEG9271960, CEG9272140 | CEG1262000
4 | 4.2.1.7 | - | Main Control Room (CW) (UBA) |  | 384 | 558 | 941 | 158
5 | 4.2.1.7.1 | CEG1441000 | Start of Erection of the CW Main Control Room (UBA) | EPC | - | 558 | - | 362 | CEG3685000, CEG3730000, CEG2530000 | CEG3690000
5 | 4.2.1.7.2 | CEG3690000 | Erection of the Main Control Room CW/ Safety Panel (UBA) | EPC | 180 | 558 | 737 | 362 | CEG1441000 | CEG1451000, CEG1016240
5 | 4.2.1.7.3 | CEG1451000 | Completion of Erection of the CW Main Control Room (UBA) | EPC | - | - | 941 | 158 | CEG3690000, CEG1016200, CEG1016240, CEG3600000, CEG3600001 | CEG1262000, CEG1016280
4 | 4.2.1.8 | - | Cable Trays and Cable Launching (Power and I&C) (UBA) |  | 1204 | 0 | 1203 | 188
5 | 4.2.1.8.1 | CEG3608000 | Wiring - CF Power and I&C Cable Pull Cards: S1 released (UBA) | ETN | - | 0 | - | 461 | CEG1341000, CEG6670000 | CEG3610000
5 | 4.2.1.8.2 | CEG3600000 | Erection of Cable Trays and Launching (UBA) | ADDITIONAL | 680 | 152 | 831 | 158 | CEG9271990, CEG3598000, CEG9272050, CEG9272080, CEG9272110, CEG4390000, CEG9273815 | CEG3610000, CEG3620000, CEG1451000
5 | 4.2.1.8.3 | CEG3610000 | Launching and Connections of Power Force Cables and I&C Cables: S1 (UBA) | EPC | 250 | 392 | 641 | 158 | CEG3600000, CEG3596000, CEG3608000, CEG3599000, CEG1016140, CEG3596100, CEGPA03200 | CEG3620000, CEG1262000, CEG1016020, CEG1016040, CEG1016060, CEG1016080
5 | 4.2.1.8.4 | CEG3620000 | Launching and Connections of Power Force Cables and I&C of the other Functional Complexes (UBA) | EPC | 720 | 484 | 1203 | 188 | CEG3610000, CEG3600000, CEG3600001 | CEG1315000, CEG3745000, CEG0916160
4 | 4.2.1.9 | - | Low Voltage Transformers (UBA/UBD) |  | 60 | 216 | 275 | 404
5 | 4.2.1.9.1 | CEG3630000 | Erection of Low Voltage Transformers (UBD) | EPC | 60 | 216 | 275 | 404 | CEG3625000, CEG6700000, CEG6700000 | CEG1262000, CEG1016120
4 | 4.2.1.10 | - | Distribution Panels (BT, MT, CC and Package Systems) (UBA) |  | 528 | 380 | 907 | 402
5 | 4.2.1.10.1 | CEG3660000 | Erection of Package Systems Panels (UBA) | EPC | 278 | 380 | 657 | 442 | CEG2520000, CEG5720000, CEG2521000 | CEG1262000
5 | 4.2.1.10.2 | CEG3640000 | Erection of AC Low Voltage Panels (UBA) | EPC | 250 | 410 | 659 | 440 | CEG3635000, CEG2520000, CEG5720000, CEG3730000, CEG6700000, CEG6700000, CEG2521000 | CEG1262000
5 | 4.2.1.10.3 | CEG3650000 | Erection of Medium Voltage Panels (UBA) | EPC | 300 | 430 | 729 | 370 | CEG3636000, CEG2520000, CEG5720000, CEG3730000, CEG6700000, CEG6700000, CEG2521000 | CEG1262000
5 | 4.2.1.10.4 | CEG3655000 | Erection of Direct Current Panels (UBA) | EPC | 210 | 698 | 907 | 402 | CEG3637000, CEG2530000, CEG5720000, CEG3730000 | CEG1262000
4 | 4.2.1.11 | - | Electronic Panels (I&C) (UBA) |  | 394 | 487 | 880 | 872
5 | 4.2.1.11.1 | CEG3670000 | SPPA Cabinets Erection (UBA) (CF: S1) | EPC | 30 | 487 | 516 | 583 | CEG3665000, CEG5720000, CEG3730000 | CEG1262000
5 | 4.2.1.11.2 | CEG5740000 | SPPA Cabinets Erection(UBA) (CF: V) | EPC | 30 | 487 | 516 | 583 | CEG5730000, CEG3730000 | CEG1262000
5 | 4.2.1.11.3 | CEG5500000 | SPPA Cabinets Erection(UBA) (CF: K1) | EPC | 30 | 487 | 516 | 1236 | CEG5430000, CEG3730000 | CEG6470000
5 | 4.2.1.11.4 | CEG5510000 | SPPA Cabinets Erection (UBA)(CF: K2) | EPC | 30 | 487 | 516 | 1236 | CEG5430000, CEG3730000 | CEG6470000
5 | 4.2.1.11.5 | CEG5520000 | SPPA Cabinets Erection (UBA) (CF: E) | EPC | 30 | 487 | 516 | 1236 | CEG5430000, CEG3730000 | CEG6470000
5 | 4.2.1.11.6 | CEG5530000 | SPPA Cabinets Erection (UBA)(CF: K3) | EPC | 30 | 487 | 516 | 1236 | CEG5490000, CEG3730000 | CEG6470000
5 | 4.2.1.11.7 | CEG5570000 | SPPA Cabinets Erection (UBA)(CF: M2) | EPC | 30 | 487 | 516 | 1236 | CEG5450000, CEG3730000 | CEG6470000
5 | 4.2.1.11.8 | CEG5620000 | SPPA Cabinets Erection (UBA)(CF: G2) | EPC | 30 | 487 | 516 | 1236 | CEG5440000, CEG3730000 | CEG6470000
5 | 4.2.1.11.9 | CEG5630000 | SPPA Cabinets Erection (UBA) (CF: J) | EPC | 30 | 487 | 516 | 1236 | CEG5440000, CEG3730000 | CEG6470000
5 | 4.2.1.11.10 | CEG5660000 | SPPA Cabinets Erection (UBA) (CF: S2) | EPC | 30 | 487 | 516 | 1236 | CEG3665000, CEG3730000 | CEG6470000
5 | 4.2.1.11.11 | CEG5670000 | SPPA Cabinets Erection (UBA)(CF: S3) | EPC | 30 | 487 | 516 | 1236 | CEG3665000, CEG3730000 | CEG6470000
5 | 4.2.1.11.12 | CEG5680000 | SPPA Cabinets Erection (UBA) (CF: P) | EPC | 30 | 487 | 516 | 1236 | CEG3665000, CEG3730000 | CEG6470000
5 | 4.2.1.11.13 | CEG5690000 | SPPA Cabinets Erection (UBA) (CF: Q) | EPC | 30 | 487 | 516 | 1236 | CEG3665000, CEG3730000 | CEG6470000
5 | 4.2.1.11.14 | CEG5550000 | SPPA Cabinets Erection (UBA) (CF: C) | EPC | 60 | 487 | 546 | 1206 | CEG5450000, CEG3730000 | CEG6470000
5 | 4.2.1.11.15 | CEG5580000 | SPPA Cabinets Erection (UBA) (CF: N) | EPC | 60 | 487 | 546 | 1206 | CEG5450000, CEG3730000 | CEG6470000
5 | 4.2.1.11.16 | CEG5590000 | SPPA Cabinets Erection (UBA) (CF: R) | EPC | 60 | 487 | 546 | 1206 | CEG5450000, CEG3730000 | CEG6470000
5 | 4.2.1.11.17 | CEG5600000 | SPPA Cabinets Erection (UBA) (CF: B) | EPC | 60 | 487 | 546 | 1206 | CEG5480000, CEG3730000 | CEG6470000
5 | 4.2.1.11.18 | CEG5610000 | SPPA Cabinets Erection (UBA) (CF: G1) | EPC | 60 | 487 | 546 | 1206 | CEG5440000, CEG3730000 | CEG6470000
5 | 4.2.1.11.19 | CEG5640000 | SPPA Cabinets Erection (UBA) (CF: D) | EPC | 60 | 487 | 546 | 1206 | CEG5440000, CEG3730000 | CEG6470000
5 | 4.2.1.11.20 | CEG5700000 | SPPA Cabinets Erection (UBA) (CF: F) | EPC | 60 | 487 | 546 | 1206 | CEG3665000, CEG3730000 | CEG6470000
5 | 4.2.1.11.21 | CEG4360000 | SPPA Cabinets Erection (UBA) (CF: L) | EPC | 90 | 487 | 576 | 987 | CEG5470000, CEG5720000, CEG3730000 | CEG1431000, CEG4530000
5 | 4.2.1.11.22 | CEG5540000 | SPPA Cabinets Erection (UBA) (CF: A) | EPC | 90 | 487 | 576 | 1176 | CEG5450000, CEG3730000 | CEG6470000
5 | 4.2.1.11.23 | CEG5560000 | SPPA Cabinets Erection (UBA) (CF: M1) | EPC | 120 | 487 | 606 | 1146 | CEG5450000, CEG3730000 | CEG6470000
5 | 4.2.1.11.24 | CEG5650000 | SPPA Cabinets Erection (UBA) (CF: H) | EPC | 120 | 487 | 606 | 1146 | CEG5460000, CEG3730000 | CEG6470000
5 | 4.2.1.11.25 | CEG3680000 | Erection of Local Control Stations (UBA) | EPC | 90 | 791 | 880 | 872 | CEG3740000, CEG5720000, CEG3730000 | CEG3700000
4 | 4.2.1.12 | - | Installation of I&C Equipment (UBA) |  | 180 | 522 | 701 | 495
5 | 4.2.1.12.1 | CEG1016020 | TLSU (OM690 System) Installation Activities (UBA) | EPC | 120 | 522 | 641 | 158 | CEG1016120, CEG3610000 | CEG1016160
5 | 4.2.1.12.2 | CEG1016060 | Operational I&C Installation Activities (FC-A3-6, B2-3, Ñ1-3, D1-6, E1-4, F1-2) (UBA) | EPC | 180 | 522 | 701 | 177 | CEG3610000 | CEG1016200
5 | 4.2.1.12.3 | CEG1016040 | EE I&C Installation Activities (System BY) (FC-A1) (UBA) | EPC | 161 | 541 | 701 | 495 | CEG3610000 | CEG1016220
5 | 4.2.1.12.4 | CEG1016080 | Safety I&C Installation Activities (UBA) | EPC | 150 | 542 | 691 | 387 | CEG3610000 | CEG1016180, CEG1016240
4 | 4.2.1.13 | - | I&C Commissioning (UBA) |  | 1206 | 276 | 1481 | 124
5 | 4.2.1.13.1 | CEG1016120 | Power supply via Building transformers (UBA) | EPC | - | 276 | - | 404 | CEG3630000 | CEG1016020
5 | 4.2.1.13.2 | CEG1016140 | Temporary Start-up Operation of Fire Fighting Systems SGA, SGC (UBA) | EPC | - | - | 561 | 418 | CEG5770000, CEG9271600, CEG9273250, CEG9273040, CEG9273070, CEG9273100, CEG9273130, CEG9273190, CEG9273220 | CEG3610000
5 | 4.2.1.13.3 | CEG1016160 | Commissioning and Start-up of TLSU (OM690 System) (UBA) | EPC | 89 | 613 | 701 | 158 | CEG1016020 | CEG1016240, CEG1016200, CEG1016220
5 | 4.2.1.13.4 | CEG1016180 | Commissioning and Start-up of Safety I&C (UBA) | EPC | 50 | 663 | 712 | 387 | CEG1016080 | CEG1016240
5 | 4.2.1.13.5 | CEG1016220 | Commissioning and Start-up of EE I&C (FC-A1) (UBA) | EPC | 50 | 702 | 751 | 495 | CEG1016040, CEG1016160 | CEG1016280
5 | 4.2.1.13.6 | CEG1016200 | Commissioning and Start-up Operation of the Operator. I&C (FC-A3-6, B2-3, Ñ1-3, D1-6, E1-4, F1-2) (UBA) | EPC | 240 | 702 | 941 | 158 | CEG1016060, CEG1016160 | CEG1016240, CEG1451000
5 | 4.2.1.13.7 | CEG1016240 | Commissioned Control Room for the scope of Priority Systems (PICS) (UBA) | EPC | - | 762 | - | 338 | CEG1016080, CEG3690000, CEG1016160, CEG1016180, CEG1016200 | CEG1451000
5 | 4.2.1.13.8 | CEG1016260 | Initial Voltage Supply via Busbars (UBA) | EPC | - | - | 1034 | 571 | CEG4250000 | CEG1016280
5 | 4.2.1.13.9 | CEG1016280 | Commissioning and Start-up of Process Systems | EPC | 359 | 1123 | 1481 | 124 | CEG3280000, CEG1016220, CEG1016260, CEG1451000, CEG0916160, CEG4290000 | CEG0916180
5 | 4.2.1.13.10 | CEG0916160 | Poiwer Power Supply Available for Testing (UBA) | EPC | - | - | 1203 | 188 | CEG3620000 | CEG0916180, CEG1016280
4 | 4.2.1.14 | - | Physical Protection Systems (UBA) |  | 240 | 976 | 1215 | 438
5 | 4.2.1.14.1 | CEG3745000 | Erection of CZ Physical Protection (UBA) | EPC | 240 | 976 | 1215 | 438 | CEG1262000, CEG3525000, CEG3620000 | CEG1310000
3 | 4.2.2 | - | Erection of Emergency Generators and Chilled Water (UBP) in the Building |  | - | Anterior ao EPC | 1418 | 304
4 | 4.2.2.1 | - | Emergency Diesel Generating Sets 1 (UBP) |  | 390 | 583 | 972 | 482
5 | 4.2.2.1.1 | CEG2890000 | Erection of Emergency Diesel Generating Sets 1/2/3/4XJ (UBP) | EPC | 390 | 583 | 972 | 482 | CEG2880000, CEG2860000, CEG6700000, CEG6700000 | CEG2900000, CEG2910000, CEG4980000
4 | 4.2.2.2 | - | Electrical and I&C Systems and Equipment (UBP) |  | 826 | 593 | 1418 | 235
5 | 4.2.2.2.1 | CEG2910000 | Erection of Electrical and I&C Equipment and Systems (UBP) | EPC | 410 | 593 | 1002 | 543 | CEG2890000 | CEG4290000, CEG6260000
5 | 4.2.2.2.2 | CEG2920000 | Erection of CZ Physical Protection (UBP) | EPC | 120 | 1299 | 1418 | 235 | CEG2690000 | CEG1310000
4 | 4.2.2.3 | - | Chilled Water System (UBP) |  | 420 | 745 | 1164 | 196
5 | 4.2.2.3.1 | CEG2950000 | Erection of Chilled Water System Components, QKA (UBP) | EPC | 420 | 745 | 1164 | 196 | CEG2940000, CEG1341000, CEG2860000 | CEG2960000, CEG2970000, CEG4320000, CEG4980000
4 | 4.2.2.4 | - | Ventilation Systems (UBP) |  | 420 | 745 | 1164 | 196
5 | 4.2.2.4.1 | CEG2970000 | Erection of SAD Ventilation Ducts and Components (UBP) | EPC | 420 | 745 | 1164 | 196 | CEG2950000 | CEG2980000
4 | 4.2.2.5 | - | Piping Systems (UBP) |  | - | Anterior ao EPC | 1334 | 388
5 | 4.2.2.5.1 | - | UBP General Erection Area |  | - | Anterior ao EPC | 1334 | 388
6 | 4.2.2.5.1.1 | CEG4940000 | Piping - Released Design (UBP) | ETN | - | - | Anterior ao EPC | 619 | CEG1341000, CEGPA01500 | CEG4960000
6 | 4.2.2.5.1.2 | CEG4960000 | Piping - Engineering Phase 1 (Workbook) (UBP) | EPC | 630 | 204 | 833 | 619 | CEG4940000, CEG6700000, CEG6700000 | CEG4970000, CEG4970000
6 | 4.2.2.5.1.3 | CEG4970000 | Piping - Prefabrication (UBP) | EPC | 630 | 294 | 923 | 619 | CEG4950000, CEG4960000, CEG4960000 | CEG4980000, CEG4980100, CEG4980100, CEG4980200, CEG4980200, CEG4980300, CEG4980300, CEG4980400, CEG4980400
6 | 4.2.2.5.1.4 | CEG4990000 | Piping - Cleaning, Hydrostatic Testing and Painting Phase 2 (UBP) | EPC | 270 | 1005 | 1274 | 388 | CEG4980000, CEG4980000, CEG4980100, CEG4980100, CEG4980200, CEG4980200, CEG4980300, CEG4980400 | CEG5420000, CEG5420000
6 | 4.2.2.5.1.5 | CEG5420000 | Piping - Engineering Phase 2 (Documentation Closing) (UBP) | EPC | 270 | 1065 | 1334 | 388 | CEG4990000, CEG4990000 | CEG6350000
5 | 4.2.2.5.2 | - | BP01 Erection Area |  | 300 | 945 | 1244 | 388
6 | 4.2.2.5.2.1 | CEG4980000 | Start of Piping Erection (UBP) | EPC | - | 945 | - | 388 | CEG4970000, CEG2890000, CEG2950000 | CEG4990000, CEG4990000, CEG4980100, CEG4980200
6 | 4.2.2.5.2.2 | CEG4980200 | Piping - Erection BP002 (UBP) | EPC | 240 | 945 | 1184 | 388 | CEG4970000, CEG4970000, CEG4980000 | CEG4990000, CEG4990000, CEG4980300
6 | 4.2.2.5.2.3 | CEG4980100 | Piping - Erection BP001 (UBP) | EPC | 270 | 945 | 1214 | 418 | CEG4970000, CEG4970000, CEG4980000 | CEG4990000, CEG4990000
6 | 4.2.2.5.2.4 | CEG4980300 | Piping - Erection BP003 (UBP) | EPC | 240 | 1005 | 1244 | 388 | CEG4970000, CEG4970000, CEG4980200 | CEG4990000, CEG4980400
6 | 4.2.2.5.2.5 | CEG4980400 | Piping - Erection BP004 (UBP) | EPC | 240 | 1005 | 1244 | 388 | CEG4970000, CEG4970000, CEG4980300 | CEG4990000
3 | 4.2.3 | - | Erection in the Emergency Power Building (ULB) |  | - | Anterior ao EPC | 1418 | 334
4 | 4.2.3.1 | - | Redundancy Tanks (ULB) |  | 390 | 652 | 1041 | 342
5 | 4.2.3.1.1 | CEG3489000 | Erection of Redundancy Tanks 5/6/7/8XJ (ULB) | EPC | 390 | 652 | 1041 | 342 | CEG4030000, CEG3606000, CEG3616000, CEG6700000, CEG6700000 | CEG3500000, CEG3460000
4 | 4.2.3.2 | - | Emergency Diesel Generating Sets 2 (ULB) |  | 390 | 652 | 1041 | 342
5 | 4.2.3.2.1 | CEG3490000 | Erection of Emergency Power Pumps 5/6/7/8XJ (ULB) | EPC | 390 | 652 | 1041 | 342 | CEG4030000, CEG3606000, CEG3616000, CEG6700000, CEG6700000 | CEG3500000, CEG3460000
4 | 4.2.3.3 | - | Cable Trays and Cable Launching (Power and I&C) (ULB) |  | 794 | 482 | 1275 | 317
5 | 4.2.3.3.1 | CEG4010000 | Erection of Cable Trays and Launching (ULB) | EPC | 570 | 482 | 1051 | 317 | CEG3410000, CEG6410000, CEG3420000, CEG6700000, CEG6700000 | CEG4020000, CEG4050000, CEG4020000, CEG4030000
5 | 4.2.3.3.2 | CEG4020000 | Launching and Connections of Power and I&C Cables (ULB) | EPC | 490 | 786 | 1275 | 317 | CEG4010000, CEG4040000, CEG4010000 | CEG3717000
4 | 4.2.3.4 | - | Local Control Panels and Stations (ULB) |  | 390 | 652 | 1041 | 711
5 | 4.2.3.4.1 | CEG4030000 | Erection of Low Voltage AC (E006/4.lot) and Direct Current (E007/2.lot) Panels (ULB) | EPC | 304 | 652 | 955 | 326 | CEG3637000, CEG4010000 | CEG3490000, CEG4040000, CEG3489000
5 | 4.2.3.4.2 | CEG4040000 | Erection of SPPA I&C Cabinets (ULB) (CF: S3) and Local Control Stations (ULB) | EPC | 330 | 712 | 1041 | 326 | CEG4070000, CEG3665000, CEG4030000 | CEG4020000, CEG6280000
5 | 4.2.3.4.3 | CEG4370000 | Erection of Reactor Protection (TXS) Cabinets (ULB) (CF:L) | EPC | 103 | 714 | 816 | 936 | CEG4070000, CEG4350000 | CEG6470000
4 | 4.2.3.5 | - | Physical Protection Systems (ULB) |  | 120 | 1299 | 1418 | 235
5 | 4.2.3.5.1 | CEG4260000 | Erection of CZ Physical Protection (ULB) | EPC | 120 | 1299 | 1418 | 235 | CEG2690000 | CEG1310000
4 | 4.2.3.6 | - | Piping Systems (ULB) |  | - | Anterior ao EPC | 951 | 771
5 | 4.2.3.6.1 | - | ULB General Erection Area |  | - | Anterior ao EPC | 951 | 771
6 | 4.2.3.6.1.1 | CEG5000000 | Piping - Released Erection Areas Design (ULB) | ETN | - | Anterior ao EPC | - | 964 | CEG1341000, CEGPA01500 | CEG5030000, CEG5020000
6 | 4.2.3.6.1.2 | CEG5020000 | Piping - Engineering Phase 1 (Workbook) (ULB) | EPC | 360 | 239 | 598 | 964 | CEG5000000, CEG6700000, CEG6700000 | CEG5030000, CEG5030000
6 | 4.2.3.6.1.3 | CEG6640000 | Piping - Available Erection Area Materials (ULB) | EPC | - | 272 | - | 901 | CEG1341000, CEG5010000, CEGPA01500, CEG6700000 | CEG5030000
6 | 4.2.3.6.1.4 | CEG5030000 | Piping - Prefabrication (ULB) | EPC | 360 | 392 | 751 | 901 | CEG5010000, CEG5020000, CEG5000000, CEG5020000, CEG6640000 | CEG3460000
6 | 4.2.3.6.1.5 | CEG5040000 | Pipes - Cleaning, Hydrostatic Testing and Painting Phase 2 (ULB) | EPC | 210 | 682 | 891 | 731 | CEG3460000, CEG3460000, CEG3460100, CEG3460100, CEG3460200, CEG3460200, CEG3460300, CEG3460300, CEG3460400, CEG3460400, CEG3460500, CEG3460500 | CEG6080000, CEG6080000, CEG6270000
6 | 4.2.3.6.1.6 | CEG6080000 | Piping - Engineering Phase 2 (Documentation Closing) (ULB) | EPC | 210 | 742 | 951 | 771 | CEG5040000, CEG5040000 | CEG6350000
5 | 4.2.3.6.2 | - | LB01 Erection Area |  | 210 | 652 | 861 | 731
6 | 4.2.3.6.2.1 | CEG3460000 | Start of Piping Erection (ULB) | EPC | - | 652 | - | 731 | CEG5030000, CEG3490000, CEG6700000, CEG6700000, CEG3489000 | CEG5040000, CEG5040000, CEG3460100, CEG3460200, CEG3460300, CEG3460400, CEG3460500
6 | 4.2.3.6.2.2 | CEG3460500 | Piping - Erection LB005 (ULB) | EPC | 120 | 652 | 771 | 731 | CEG3460000 | CEG5040000, CEG5040000
6 | 4.2.3.6.2.3 | CEG3460100 | Piping - Erection LB001 (ULB) | EPC | 150 | 652 | 801 | 731 | CEG3460000 | CEG5040000, CEG5040000
6 | 4.2.3.6.2.4 | CEG3460400 | Piping - Erection LB004 (ULB) | EPC | 150 | 652 | 801 | 731 | CEG3460000 | CEG5040000, CEG5040000
6 | 4.2.3.6.2.5 | CEG3460300 | Piping - Erection LB003 (ULB) | EPC | 180 | 652 | 831 | 731 | CEG3460000 | CEG5040000, CEG5040000
6 | 4.2.3.6.2.6 | CEG3460200 | Piping - Erection LB002 (ULB) | EPC | 210 | 652 | 861 | 731 | CEG3460000 | CEG5040000, CEG5040000
4 | 4.2.3.7 | - | Ventilation Systems (ULB) |  | 510 | 482 | 991 | 331
5 | 4.2.3.7.1 | CEG4050000 | Erection of SAL Ventilation Systems (ULB) | EPC | 510 | 482 | 991 | 331 | CEG4010000, CEG4270000, CEG9272170 | CEG4060000, CEG4070000
4 | 4.2.3.8 | - | Temporary Ventilation (I&C Panel Rooms) (ULB) |  | 61 | 623 | 683 | 354
5 | 4.2.3.8.1 | CEG4070000 | Installation of Temporary Ventilation in the I&C Panel Rooms (ULB) | EPC | 61 | 623 | 683 | 354 | CEG3420000, CEG4050000, CEG6700000, CEG6700000 | CEG4040000, CEG4370000
3 | 4.2.4 | - | Erection in the Transformer Structures Area |  | - | Anterior ao EPC | 969 | 813
4 | 4.2.4.1 | - | 138 kV External Network Transformer (BCT01) |  | 60 | 333 | 392 | 707
5 | 4.2.4.1.1 | CEG4100000 | Assembling the BCT01 External Network Transformer (UBC) | EPC | 60 | 333 | 392 | 707 | CEG4090000, CEG4095000, CEG3950000, CEG6700000, CEG6700000 | CEG1262000, CEG4115000, CEG4110000
4 | 4.2.4.2 | - | Unit Auxiliary Transformers (BBT01/02) |  | 270 | 551 | 820 | 608
5 | 4.2.4.2.1 | CEG4141000 | Assembling the Auxiliary Transformer of the BBT01 Unit (UBE) | EPC | 90 | 551 | 640 | 571 | CEG4135000, CEG4130000, CEG3707000, CEG6570000, CEG6700000, CEG4131000 | CEG4230000, CEG4160000, CEG4151000
5 | 4.2.4.2.2 | CEG4151000 | Assembling the Auxiliary Transformer of the BBT02 Unit (UBE) | EPC | 90 | 731 | 820 | 608 | CEG4140000, CEG6700000, CEG4141000 | CEG4160000
4 | 4.2.4.3 | - | Generator Transformers (BAT01/02/03) |  | 332 | 524 | 855 | 633
5 | 4.2.4.3.1 | CEG4191000 | Erection of the BAT03 Generator Transformer (UBF) | EPC | 90 | 524 | 613 | 598 | CEG4180000, CEG4185000, CEG3707000, CEG6570000, CEG6700000, CEG4181000 | CEG4230000, CEG4220000, CEG6420000, CEG4201000
5 | 4.2.4.3.2 | CEG4201000 | Erection of the BAT02 Generator Transformer (UBF) | EPC | 90 | 706 | 795 | 633 | CEG4190000, CEG6700000, CEG4191000 | CEG4220000, CEG4211000
5 | 4.2.4.3.3 | CEG4211000 | Erection of the BAT01 Generator Transformer (UBF) | EPC | 90 | 766 | 855 | 633 | CEG4200000, CEG6700000, CEG4201000 | CEG4220000
4 | 4.2.4.4 | - | Shielded Busbars (BAA) / Generator Circuit Breaker (BAC) |  | 419 | 551 | 969 | 571
5 | 4.2.4.4.1 | CEG4230000 | Erection of the BAA Generator Shielded Busbars (UMA) | EPC | 385 | 551 | 935 | 571 | CEG4190000, CEG4140000, CEG4180000, CEG6420000, CEG6700000, CEG6700000, CEG4181000, CEG4141000, CEG4191000 | CEG4240000, CEG4250000
5 | 4.2.4.4.2 | CEG4240000 | Erection of BAC Generator Circuit Breakers (UMA) | EPC | 235 | 735 | 969 | 571 | CEG4230000, CEG4180000, CEG4181000 | CEG4250000
4 | 4.2.4.5 | - | Piping Systems (UBC/ UBE/ UBF) |  | - | Anterior ao EPC | 730 | 1052
5 | 4.2.4.5.1 | CEG5280000 | Piping - Released Design (UBE/ UBF) | ETN | - | - | Anterior ao EPC | 1052 | CEG1347000, CEGPA01500 | CEG5300000
5 | 4.2.4.5.2 | CEG5270000 | Piping - Released Design (UBC) | ETN | - | - | Anterior ao EPC | 1052 | CEG1347000, CEGPA01500 | CEG5300000
5 | 4.2.4.5.3 | CEG5300000 | Piping - Engineering Phase 1 (Workbook) (UBC/ UBE/ UBF) | EPC | 345 | 206 | 550 | 1052 | CEG5270000, CEG5280000, CEG6700000, CEG6700000 | CEG5310000, CEG5310000
5 | 4.2.4.5.4 | CEG5310000 | Piping - Prefabrication (UBC/ UBE/ UBF) | EPC | 345 | 296 | 640 | 1052 | CEG5290000, CEG5300000, CEG5300000 | CEG5320000, CEG5320000
5 | 4.2.4.5.5 | CEG5320000 | Piping - Erection (UBC/ UBE/ UBF) | EPC | 315 | 386 | 700 | 1052 | CEG5310000, CEG5310000 | CEG5330000, CEG5330000
5 | 4.2.4.5.6 | CEG5330000 | Piping - Cleaning, Hydrostatic Testing and Painting Phase 2 (UBC/ UBE/ UBF) | EPC | 180 | 551 | 730 | 1052 | CEG5320000, CEG5320000 | CEG6350000
2 | 4.3 | - | Final Erection and Commissioning Services for Central Area Systems |  | 1164 | 393 | 1556 | 196
3 | 4.3.1 | - | Piping Systems and Mechanical Components |  | 693 | 712 | 1404 | 348
4 | 4.3.1.1 | CEG6270000 | Final Erection and Commissioning Services of the Piping System (ULB) | EPC | 310 | 712 | 1021 | 731 | CEG5040000, CEG3330000, CEG6390000 | CEG6470000, CEG6350000
4 | 4.3.1.2 | CEG2900000 | Final Erection and Commissioning Services of Emergency Diesel Generating Sets 1/2/3/4XJ (UBP) | EPC | 300 | 900 | 1199 | 405 | CEG2890000, CEG3800000, CEG3960000 | CEG4290000, CEG1310000, CEG6350000, CEG6260000
4 | 4.3.1.3 | CEG3500000 | Final Erection and Commissioning Services of the Emergency Feeding Pumps 5/6/7/8XJ (ULB) | EPC | 270 | 1042 | 1311 | 342 | CEG3490000, CEG3800000, CEG3960000, CEG3489000 | CEG1310000, CEG6350000
4 | 4.3.1.4 | CEG4320000 | Final Erection Services and Preparatory Tests of the Cold Water Sys. QK (UBP) | EPC | 210 | 1165 | 1374 | 249 | CEG2950000, CEG1520000 | CEG2960000, CEG6350000
4 | 4.3.1.5 | CEG4290000 | Completion of the UBP System Commissioning | EPC | - | - | 1200 | 405 | CEG2910000, CEG2900000, CEG1520000, CEG6260000 | CEG6470000, CEG6350000, CEG1016280
4 | 4.3.1.6 | CEG2960000 | Commissioning of the QK Cold Water System (UBP) | EPC | 100 | 1305 | 1404 | 249 | CEG2950000, CEG4320000 | CEG1310000, CEG6350000
3 | 4.3.2 | - | Electrical and I&C Systems and Components |  | 1043 | 393 | 1435 | 317
4 | 4.3.2.1 | CEG4110000 | Commissioning of the BCT01 External Network Transformer (UBC) | EPC | 90 | 393 | 482 | 797 | CEG4100000 | CEG1279000
4 | 4.3.2.2 | CEG5710000 | Complementary Erection of I&C (UBA) (Reactor Protection TXS Cabinets CF: L/M1/M2/L-UBA/N) | EPC | 90 | 791 | 880 | 872 | CEG4350000, CEG3700000 | CEG6470000
4 | 4.3.2.3 | CEG4115000 | Interconnection line with the External Network (138 kV) ready and commissioned (BCT) | EPC | - | - | 820 | 459 | CEG4100000 | CEG1279000, CEG4160000, CEG4220000
4 | 4.3.2.4 | CEG4160000 | Commissioning of Auxiliary Transformers of Unit BBT01/02 (UBE) | EPC | 210 | 821 | 1030 | 608 | CEG4150000, CEG4140000, CEG4115000, CEG4141000, CEG4151000 | CEG1290000
4 | 4.3.2.5 | CEG4220000 | Commissioning of Generator Transformers BAT01/02/03 (UBF) | EPC | 150 | 856 | 1005 | 633 | CEG4210000, CEG4200000, CEG4190000, CEG4115000, CEG4191000, CEG4201000, CEG4211000 | CEG1290000
4 | 4.3.2.6 | CEG6260000 | Final Erection and Comissioning Services of the Electrical and I&C Systems (UBP) | EPC | 270 | 930 | 1199 | 406 | CEG2910000, CEG2900000 | CEG4290000, CEG1310000, CEG6350000
4 | 4.3.2.7 | CEG4710000 | Commissioning of Energy Supply System for Auxiliaries Unit Sys. (S1) | EPC | 450 | 942 | 1391 | 158 | CEG1262000, CEG9270310, CEG9270340, CEG9270370, CEG9270400, CEG9270430, CEG9272020, CEG9270490, CEG9270580, CEG9271630, CEG9271660, CEG9271720, CEG7035000, CEG7035100 | CEG1474000
4 | 4.3.2.8 | CEG3717000 | Final Erection and Comissioning Services of the Electrical and I&C Systems (ULB) | EPC | 480 | 956 | 1435 | 317 | CEG1520000, CEG4020000 | CEG6470000, CEG6350000
4 | 4.3.2.9 | CEG4250000 | Commissioning of BAA Shielded Busbars and BAC Generator Circuit Breaker (UMA) | EPC | 65 | 970 | 1034 | 571 | CEG4230000, CEG4240000 | CEG1290000, CEG1016260
4 | 4.3.2.10 | CEG6280000 | Final Erection and Comissioning Services of the Local Control Panels and Stations (ULB) | EPC | 385 | 1042 | 1426 | 326 | CEG4040000 | CEG6470000, CEG6350000
3 | 4.3.3 | - | Ventilation Systems and Components |  | 793 | 764 | 1556 | 196
4 | 4.3.3.1 | CEG3525000 | Final Erection and Comissioning Services of the Ventilation System SAC (UBA) | EPC | 500 | 764 | 1263 | 438 | CEG3710000, CEG3720000, CEG6430000 | CEG3745000, CEG6470000, CEG6350000
4 | 4.3.3.2 | CEG4060000 | Commissioning of the SAL Ventilation System (ULB) | EPC | 430 | 992 | 1421 | 331 | CEG4050000, CEG3780000 | CEG6470000
4 | 4.3.3.3 | CEG2980000 | Final Erection and Comissioning Services of the Ventilation (UBP) | EPC | 392 | 1165 | 1556 | 196 | CEG2970000 | CEG6470000, CEG6350000
1 | 5 | - | CONVENTIONAL AND EXTERNAL AREAS (ONE / Other Buildings) |  | - | Anterior ao EPC | 1513 | 269
2 | 5.1 | - | Civil Construction |  | 1362 | 152 | 1513 | 140
3 | 5.1.1 | - | Civil Construction - Discharge Channels (UGZ / UQT / UQN) |  | 1170 | 152 | 1321 | 209
4 | 5.1.1.1 | CEG3361000 | Concrete Structure (UGZ and UQT) | EPC | 612 | 152 | 763 | 767 | CEG1000000, CEGPA03200 | CEG3570000
4 | 5.1.1.2 | CEG3371000 | Concrete Structure (UQN / UQT - Connection with Angra 2) | EPC | 570 | 752 | 1321 | 124 | CEG3340000, CEGPA03200, CEG4913610, CEG3341000 | CEG3800000, CEG3382000, CEG3384000
3 | 5.1.2 | - | Civil Construction - Protection Jetty and Beach Line (UZS / UZP) |  | 720 | 572 | 1291 | 124
4 | 5.1.2.1 | CEG3381000 | Containment Structure Design - Itaorna Beach Line (UZP) | EPC | 180 | 572 | 751 | 124 | CEG9273980 | CEG3382000
4 | 5.1.2.2 | CEG3383000 | UQX Structure Protection Jetty Design (UZS) | EPC | 180 | 572 | 751 | 124 | CEG9273980 | CEG3384000
4 | 5.1.2.3 | CEG3382000 | Containment Structure - Itaorna Beach Line (UZP) | EPC | 540 | 752 | 1291 | 124 | CEG3381000, CEG3371000 | CEG3280000
4 | 5.1.2.4 | CEG3384000 | Structure of the UQX Structure Protection Jetty (UZS) | EPC | 540 | 752 | 1291 | 124 | CEG3383000, CEG3371000 | CEG3280000
3 | 5.1.3 | - | Construction of Water Intake Structures (UPC / UQB) |  | 1362 | 152 | 1513 | 140
4 | 5.1.3.1 | - | Concrete Structure (UPC/UQB) |  | 600 | 152 | 751 | 124
5 | 5.1.3.1.1 | CEG4913600 | Concrete Structure (UPC/ UQB) | ADDITIONAL | 480 | 152 | 631 | 124 | CEG1460000, CEG9273730, CEG4913599, CEG9273815 | CEG3540000, CEG3260000, CEG4913610
5 | 5.1.3.1.2 | CEG4913610 | Concrete Structure (UPC/ UQB) - 2nd Stage Pump Volutes | EPC | 120 | 632 | 751 | 124 | CEG4913600, CEG9273760, CEGPA03200 | CEG3250000, CEG3371000
4 | 5.1.3.2 | - | Finishing (UPC/UQB) |  | 762 | 752 | 1513 | 140
5 | 5.1.3.2.1 | CEG3250000 | Civil Finishing (UPC/ UQB) | EPC | 762 | 752 | 1513 | 140 | CEGPA03200, CEG4913610 | CEG1310000, CEG3260000
3 | 5.1.4 | - | Construction of the Turbine Building (UMA) |  | 520 | 152 | 671 | 982
4 | 5.1.4.1 | - | Concrete Structure (UMA) |  | 180 | 492 | 671 | 409
5 | 5.1.4.1.1 | CEG3050000 | Construction and drying of the MA/MK Turbogenerator Set Foundation (UMA) | EPC | 180 | 492 | 671 | 409 | CEG3080000, CEG3087000, CEG3080100 | CEG3100000, CEG3120000
4 | 5.1.4.2 | - | Steel Structure (UMA) |  | 457 | 152 | 608 | 1045
5 | 5.1.4.2.1 | CEG6041000 | Erection of Steel Structures up to elev. +13.45m (UMA) | EPC | 312 | 152 | 463 | 1045 | CEG2990000, CEGPA03200 | CEG1310000, CEG6051000
5 | 5.1.4.2.2 | CEG6051000 | Erection of Steel Structures up to elev. +41.90m (UMA) | EPC | 145 | 464 | 608 | 1045 | CEG6040000, CEGPA03200, CEG6041000 | CEG1310000
3 | 5.1.5 | - | Construction of Water Discharge Structures (UQJ / UQM) |  | 61 | 152 | 212 | 473
4 | 5.1.5.1 | - | Concrete Structure (UQJ/UQM) |  | 61 | 152 | 212 | 473
5 | 5.1.5.1.1 | CEG3341000 | Concrete Structure (UQJ/ UQM) | EPC | 61 | 152 | 212 | 473 | CEG1000000, CEG1346000, CEGPA03200 | CEG3370000, CEG3330000, CEG6120000, CEG3371000
2 | 5.2 | - | Electromechanical Erection in Buildings (ONE and Other Buildings) |  | - | Anterior ao EPC | 1491 | 291
3 | 5.2.1 | - | Erection in the Turbine Building ( UMA ) |  | - | Anterior ao EPC | 1202 | 580
4 | 5.2.1.1 | - | Moisture Separators (LBJ61/62) (UMA) |  | 210 | 907 | 1116 | 441
5 | 5.2.1.1.1 | CEG3120000 | Welding of LBJ61/62 Moisture Separators (UMA) at the Plant (PCT M106/Delp) | ETN | 210 | 907 | 1116 | 441 | CEG3070000, CEG5360000, CEG3050000, CEG9250100, CEG4910600 | CEG4930000, CEG3115000
4 | 5.2.1.2 | - | Turbogenerator and Auxiliary Set (MA / MK) (UMA) |  | 390 | 737 | 1126 | 409
5 | 5.2.1.2.1 | CEG3128000 | Start of Erection of MA and Auxiliary Turbines/Piping (UMA) | EPC | - | 737 | - | 799 | CEG3100000, CEG3130000 | CEG6360000
5 | 5.2.1.2.2 | CEG3130000 | Erection of the MK/MA Turbogenerator and Auxiliary Erection (UMA) | EPC | 390 | 737 | 1126 | 409 | CEG3100000, CEG3124000, CEG3126000, CEG3070000 | CEG3870000, CEG6360000, CEG3128000, CEG3135000
5 | 5.2.1.2.3 | CEG3135000 | Start of Erection of the MK Generator and Auxiliaries (UMA) | EPC | - | 857 | - | 679 | CEG3070000, CEG3130000 | CEG6360000
4 | 5.2.1.3 | - | Ventilation System (UMA) |  | 546 | 335 | 880 | 452
5 | 5.2.1.3.1 | CEG3220000 | Erection of SAM1 (UMA) Ventilation Ducts and Components | EPC | 546 | 335 | 880 | 452 | CEG3180000, CEG6700000, CEG6700000 | CEG3230000
4 | 5.2.1.4 | - | Pre-Heaters (A1/A2) and Condensers (MAG10/20/30) (UMA) |  | 980 | 152 | 1131 | 441
5 | 5.2.1.4.1 | CEG3095100 | Cementing for Erection of MAG10/20/30 Condensers (UMA) | EPC | 42 | 152 | 193 | 409 | CEG2990000, CEG5810000, CEG6700000 | CEG3080000, CEG3080100
5 | 5.2.1.4.2 | CEG3080100 | Erection of MAG Capacitor Erection Devices (UMA) | EPC | 116 | 194 | 309 | 409 | CEG3095000, CEG3085000, CEG6700000, CEG3095100 | CEG3087000, CEG3100000, CEG3050000
5 | 5.2.1.4.3 | CEG3087000 | Positioning MAG Phase 1 Condensers (UMA) | EPC | 182 | 310 | 491 | 409 | CEG3080000, CEG4300000, CEG3085000, CEG1250000, CEG3070000, CEG3075000, CEG3105000, CEG3080100 | CEG1302000, CEG3050000
5 | 5.2.1.4.4 | CEG3100000 | Erection of Pre-Heaters A1/A2 and MAG Condensers Phase 2 (UMA) | EPC | 430 | 672 | 1101 | 409 | CEG3070000, CEG4310000, CEG3050000, CEG3080000, CEG4330000, CEG3080100 | CEG1302000, CEG5350000, CEG3130000, CEG3128000, CEG6460000
5 | 5.2.1.4.5 | CEG5350000 | Hydrostatic Test of MAG 10/20/30 Condensers (UMA) | EPC | 30 | 1102 | 1131 | 441 | CEG3100000 | CEG1302000, CEG3870000, CEG6460000
4 | 5.2.1.5 | - | Water-Steam Circuit Systems (UMA) |  | - | Anterior ao EPC | 1202 | 400
5 | 5.2.1.5.1 | CEG3150000 | Piping - LA Water-Steam Circuit Systems Design Released (UMA) | ETN | - | - | Anterior ao EPC | 410 | CEG1341000, CEGPA01500 | CEG3180000
5 | 5.2.1.5.2 | CEG3146000 | LAA10BB001 Feeding Water Tank welded (4 sections) and base tested (UMA) | EPC | 210 | 152 | 361 | 400 | CEG3145000, CEG3020000, CEG6700000, CEG3144000 | CEG1302000, CEG3180000, CEG6460000
5 | 5.2.1.5.3 | CEG3180000 | Erection of the LA Water-Steam Circuit System (UMA) | EPC | 680 | 152 | 831 | 400 | CEG3070000, CEG3150000, CEG3146000, CEG6650000, CEG6700000, CEG6700000, CEG9230000 | CEG3190000, CEG3220000, CEG1302000, CEG1411000, CEG6460000, CEG6400000
5 | 5.2.1.5.4 | CEG1411000 | Completion of the Erection of the Water/Steam Circuit Piping in the Conventional Area (UMA) | EPC | - | - | 831 | 400 | CEG3180000, CEG6400000, CEG9272560 | CEG1302000, CEG3190000, CEG6460000
5 | 5.2.1.5.5 | CEG3870000 | Secondary Circuit Cleanliness (UMA) | EPC | 30 | 1173 | 1202 | 400 | CEG3190000, CEG5350000, CEG3130000 | CEG1302000, CEG6460000, CEG0916180, CEG6450000
4 | 5.2.1.6 | - | Piping Systems (UMA) |  | - | Anterior ao EPC | 1161 | 621
5 | 5.2.1.6.1 | - | General Erection Area UMA |  | - | Anterior ao EPC | 1161 | 621
6 | 5.2.1.6.1.1 | CEG4880000 | Piping - Released Design(UMA) | ETN | - | - | Anterior ao EPC | 441 | CEG1347000, CEGPA01500 | CEG4890100
6 | 5.2.1.6.1.2 | CEG4890100 | Piping - Engineering Phase 1 (Workbook) (UMA) Remaining | EPC | 570 | 152 | 721 | 441 | CEG4880000, CEG6700000 | CEG4900000, CEG4900000
6 | 5.2.1.6.1.3 | CEG4900000 | Piping - Prefabrication - Except TG-Set (UMA) | EPC | 570 | 222 | 791 | 441 | CEG4890000, CEG4870000, CEG4890000, CEGPA01500, CEG6700000, CEG4890100, CEG4890100, CEG5840000 | CEG4910000, CEG4910100, CEG4910200, CEG4910300, CEG4910400, CEG4910500, CEG4910600, CEG4910700, CEG4910800, CEG4910900, CEG4910101, CEG4910110, CEG4910120, CEG4910130, CEG4910140, CEG4910150, CEG4910160, CEG4910170, CEG4910180, CEG4910190
6 | 5.2.1.6.1.4 | CEG4910000 | Start of Piping Erection Except TG-Set and Circ. Water-Steam (UMA) | EPC | - | 342 | - | 441 | CEG4900000, CEG9272980, CEG9272890, CEG9272770, CEG9273010, CEG9271870, CEG9271930, CEG9271900, CEG9273640, CEG9273280 | CEG4930000, CEG4930000, CEG4910100, CEG4910400, CEG4910600
6 | 5.2.1.6.1.5 | CEG4930000 | Pipes - Cleaning, Hydrostatic Testing and Painting Phase 2 (UMA) | EPC | 370 | 762 | 1131 | 441 | CEG4910000, CEG4910000, CEG3120000, CEG4910100, CEG4910100, CEG4910200, CEG4910200, CEG4910300, CEG4910300, CEG4910400, CEG4910400, CEG4910500, CEG4910500, CEG4910600, CEG4910600, CEG4910700, CEG4910700, CEG4910800, CEG4910800, CEG4910900, CEG4910900, CEG4910101, CEG4910101, CEG4910110, CEG4910110, CEG4910120, CEG4910120, CEG4910130, CEG4910130, CEG4910140, CEG4910140, CEG4910150, CEG4910150, CEG4910160, CEG4910160, CEG4910170, CEG4910170, CEG4910180, CEG4910180, CEG4910190, CEG4910190, CEG3115000 | CEG4920000, CEG4920000, CEG3190000
6 | 5.2.1.6.1.6 | CEG4920000 | Piping - Engineering Phase 2 (Documentation Closing) (UMA) | EPC | 360 | 802 | 1161 | 621 | CEG4930000, CEG4930000 | CEG6350000
5 | 5.2.1.6.2 | - | MA01 Erection Area |  | 480 | 342 | 821 | 661
6 | 5.2.1.6.2.1 | CEG4910100 | Piping - Erection - MA011 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 420 | 342 | 761 | 661 | CEG4900000, CEG4910000 | CEG4930000, CEG4930000, CEG4910200
6 | 5.2.1.6.2.2 | CEG4910200 | Piping - Erection - MA012 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 360 | 462 | 821 | 661 | CEG4900000, CEG4910100 | CEG4930000, CEG4930000
5 | 5.2.1.6.3 | - | MA02 Erection Area |  | 540 | 342 | 881 | 601
6 | 5.2.1.6.3.1 | CEG4910400 | Piping - Erection - MA022 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 510 | 342 | 851 | 601 | CEG4900000, CEG4910000, CEG5096000 | CEG4930000, CEG4930000, CEG4910300, CEG4910500
6 | 5.2.1.6.3.2 | CEG4910500 | Piping - Erection - MA023 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 390 | 432 | 821 | 661 | CEG4900000, CEG4910400 | CEG4930000, CEG4930000
6 | 5.2.1.6.3.3 | CEG4910300 | Piping - Erection - MA021 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 450 | 432 | 881 | 601 | CEG4900000, CEG4910400 | CEG4930000, CEG4930000
5 | 5.2.1.6.4 | - | MA03 Erection Area |  | 570 | 342 | 911 | 531
6 | 5.2.1.6.4.1 | CEG4910800 | Piping - Erection - MA033 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 330 | 342 | 671 | 691 | CEG4900000, CEG4910600, CEG5036000 | CEG4930000, CEG4930000, CEG4910900
6 | 5.2.1.6.4.2 | CEG4910600 | Piping - Erection - MA031 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 390 | 342 | 731 | 441 | CEG4900000, CEG4910000, CEG9230000 | CEG4930000, CEG4930000, CEG4910700, CEG4910800, CEG4910110, CEG4910130, CEG3120000
6 | 5.2.1.6.4.3 | CEG4910900 | Piping - Erection - MA034 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 150 | 372 | 521 | 691 | CEG4900000, CEG4910800 | CEG4930000, CEG4930000, CEG4910101, CEG4910190
6 | 5.2.1.6.4.4 | CEG4910110 | Piping - Erection - MA036 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 480 | 432 | 911 | 531 | CEG4900000, CEG4910600 | CEG4930000, CEG4930000, CEG4910120
6 | 5.2.1.6.4.5 | CEG4910101 | Piping - Erection - MA035 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 240 | 462 | 701 | 711 | CEG4900000, CEG4910900 | CEG4930000, CEG4930000
6 | 5.2.1.6.4.6 | CEG4910700 | Piping - Erection - MA032 - Except TG-Set and Water-Steam circuit(UMA) | EPC | 180 | 522 | 701 | 651 | CEG4900000, CEG4910600 | CEG4930000, CEG4930000
6 | 5.2.1.6.4.7 | CEG4910120 | Piping - Erection - MA037 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 210 | 642 | 851 | 531 | CEG4900000, CEG4910110 | CEG4930000, CEG4930000
5 | 5.2.1.6.5 | - | MA04 Erection Area |  | 480 | 432 | 911 | 441
6 | 5.2.1.6.5.1 | CEG4910130 | Piping - Erection - MA041 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 120 | 432 | 551 | 441 | CEG4900000, CEG4910600 | CEG4930000, CEG4930000, CEG4910140, CEG4910160
6 | 5.2.1.6.5.2 | CEG4910140 | Piping - Erection - MA042 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 210 | 522 | 731 | 441 | CEG4900000, CEG4910130 | CEG4930000, CEG4930000, CEG4910150
6 | 5.2.1.6.5.3 | CEG4910150 | Piping - Erection - MA043 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 180 | 732 | 911 | 441 | CEG4900000, CEG4910140 | CEG4930000, CEG4930000
5 | 5.2.1.6.6 | - | MA05 Erection Area |  | 390 | 432 | 821 | 661
6 | 5.2.1.6.6.1 | CEG4910190 | Piping - Erection - MA054 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 360 | 432 | 791 | 691 | CEG4900000, CEG4910900 | CEG4930000, CEG4930000
6 | 5.2.1.6.6.2 | CEG4910160 | Piping - Erection - MA051 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 90 | 492 | 581 | 591 | CEG4900000, CEG4910130 | CEG4930000, CEG4930000, CEG4910170, CEG4910180
6 | 5.2.1.6.6.3 | CEG4910180 | Piping - Erection - MA053 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 60 | 552 | 611 | 621 | CEG4900000, CEG4910160 | CEG4930000, CEG4930000
6 | 5.2.1.6.6.4 | CEG4910170 | Piping - Erection - MA052 - Except TG-Set and Water-Steam circuit (UMA) | EPC | 240 | 582 | 821 | 591 | CEG4900000, CEG4910160 | CEG4930000, CEG4930000
4 | 5.2.1.7 | - | Electrical and I&C Systems and Equipment (UMA) |  | 552 | 331 | 882 | 536
5 | 5.2.1.7.1 | CEG3200000 | Erection of Electrical and I&C Equipment and Systems (UMA) | EPC | 552 | 331 | 882 | 536 | CEG3636000, CEG6700000, CEG6700000 | CEG3210000
3 | 5.2.2 | - | Water Intake Mechanical Systems and Components (UPC / UQB) |  | 756 | 481 | 1236 | 159
4 | 5.2.2.1 | CEG5080000 | Piping - Released Design (UPC/ UQB) | ETN | - | - | 481 | 159 | CEG1341000, CEGPA01500 | CEG5110000
4 | 5.2.2.2 | CEG3253500 | Negotiation for the Return of Services for the Water Intake Gantry (M315) | ETN | 240 | 482 | 721 | 159 | CEGLIC0000 | CEG3255000
4 | 5.2.2.3 | CEG5090000 | Released Electrical Design (UPC/ UQB) | ETN | - | - | 601 | 159 | CEG1347000, CEGPA01500 | CEG3260000, CEG3270000
4 | 5.2.2.4 | CEG5100000 | Ventilation - Released Design (UPC/ UQB) | ETN | - | - | 601 | 159 | CEG1341000, CEGPA01500 | CEG3260000
4 | 5.2.2.5 | CEG3253400 | Mobilization of Supervision Service Team of Erection of the Water Inlet Mechanic Equip. (UPC/ UQB) - M201 | EPC | 120 | 722 | 841 | 159 | CEG3253000, CEG6680000 | CEG3260000
4 | 5.2.2.6 | CEG3255000 | Mobilization of Supervision Service Team of Erection of the Water Intake Gantry (M315) | EPC | 120 | 722 | 841 | 159 | CEG3253500 | CEG3260000
4 | 5.2.2.7 | CEG3260000 | Erection of Mechanical Water Intake Equipment (UPC/UQB) | EPC | 395 | 842 | 1236 | 159 | CEG5090000, CEG5100000, CEG5110000, CEG6700000, CEG6700000, CEG4913600, CEG3250000, CEG3253400, CEG3255000 | CEG3270000
3 | 5.2.3 | - | Electrical and I&C Systems and Equipment (UPC / UQB) |  | 515 | 872 | 1386 | 159
4 | 5.2.3.1 | CEG3270000 | Erection of Electrical and I&C Equipment and Systems (UPC/ UQB) | EPC | 515 | 872 | 1386 | 159 | CEG3260000, CEG5090000 | CEG3280000
3 | 5.2.4 | - | PEB Piping Systems (1/ 2/ 3/ 4/ 5 and 6 UPX) |  | 810 | 152 | 961 | 692
4 | 5.2.4.1 | CEG4470000 | Piping - Prefabricated, Erection, Pressure Tests, clogged piping before Erection (PEB) | EPC | 450 | 152 | 601 | 988 | CEG3306000, CEG3320000, CEG3305000, CEG3320000, CEGPA01500, CEG6700000 | CEG3330000, CEG3330000
4 | 5.2.4.2 | CEG3330000 | Piping - Tubular Erection. of the Coolant System of Security Service (PEB) | EPC | 450 | 512 | 961 | 692 | CEG3340000, CEG3750000, CEG4470000, CEG4470000, CEG6096000, CEG9270170, CEG9270460, CEG9270520, CEG3341000 | CEG1310000, CEG6270000, CEG6390000
3 | 5.2.5 | - | Electromechanical Erection in Water Discharge Structures (UQJ / UQM) |  | 285 | 1207 | 1491 | 231
4 | 5.2.5.1 | CEG6100000 | Piping - Engineering Phase 1 (Workbook) (UQJ/UQM) | EPC | 80 | 1207 | 1286 | 241 | CEG6700000, CEG6700000, CEG1180530 | CEG6110000
4 | 5.2.5.2 | CEG6110000 | Piping - Prefabrication (UQJ/UQM) | EPC | 80 | 1267 | 1346 | 241 | CEG6100000 | CEG6120000
4 | 5.2.5.3 | CEG6120000 | Piping - Erection QJ/QM001 (UQJ/UQM) | EPC | 75 | 1357 | 1431 | 231 | CEG6110000, CEG3340000, CEG1180530, CEG3341000 | CEG6130000, CEG6130000
4 | 5.2.5.4 | CEG6130000 | Pipes - Cleaning, Hydrostatic Test, Painting Phase 2 (UQJ/UQM) | EPC | 50 | 1412 | 1461 | 231 | CEG6120000, CEG6120000 | CEG6140000, CEG6140000
4 | 5.2.5.5 | CEG6140000 | Piping - Engineering Phase 2 (Documentation Closing) (UQJ/UQM) | EPC | 50 | 1442 | 1491 | 231 | CEG6130000, CEG6130000 | CEG6350000
2 | 5.3 | - | Other Buildings / Structures / Galleries |  | - | Anterior ao EPC | 1291 | 431
3 | 5.3.1 | - | Plant Area (UZT) and Pipe and Cable Galleries |  | - | Anterior ao EPC | 1152 | 570
4 | 5.3.1.1 | - | Galleries / Cable and Piping Ducts |  | 567 | 152 | 718 | 935
5 | 5.3.1.1.1 | CEG3981000 | 5/8 UBZ - Gallery between UBA and UBP | EPC | 61 | 152 | 212 | 866 | CEG2360000, CEGPA03200 | CEG3960000, CEG1310000
5 | 5.3.1.1.2 | CEG3931000 | 1 UMZ - Gallery between UMA and UKA | EPC | 147 | 152 | 298 | 734 | CEG2990000, CEGPA03200 | CEG3960000, CEG3791000
5 | 5.3.1.1.3 | CEG3911000 | 5 UMZ - Gallery between Pipe Way and UPC | EPC | 356 | 152 | 507 | 880 | CEG2990000, CEGPA03200 | CEG3850000, CEG3850000
5 | 5.3.1.1.4 | CEG3941000 | 1 UPZ - Gallery at UBP | EPC | 49 | 192 | 240 | 927 | CEG2820000, CEGPA03200, CEG2821000 | CEG3970000, CEG1310000
5 | 5.3.1.1.5 | CEG3960000 | 2 UMZ - Gallery from 1 UMZ to UBP (except 2 UMZ attached to UBA) | EPC | 77 | 314 | 390 | 734 | CEG3930000, CEG3980000, CEG3931000, CEG3981000 | CEG3830000, CEG2900000, CEG3500000
5 | 5.3.1.1.6 | CEG3830000 | 1UYZ - Pipe Gallery between UMA and UYF | EPC | 153 | 344 | 496 | 832 | CEG3030000, CEG3960000 | CEG3560000, CEG3820000
5 | 5.3.1.1.7 | CEG3820000 | Pipes - Gallery of Gas Pipings between UTG and UMA (1UTZ) | EPC | 53 | 666 | 718 | 935 | CEG3830000 | CEG1310000
4 | 5.3.1.2 | - | Miscellaneous Structures |  | 718 | 152 | 869 | 733
5 | 5.3.1.2.1 | CEG4001000 | UPX boxes - 4 (PEB) | EPC | 102 | 152 | 253 | 1349 | CEG3880000, CEGPA03200 | CEG5240000
5 | 5.3.1.2.2 | CEG3991000 | UPX boxes - 1/2/3/5/6 (PEB) | EPC | 126 | 152 | 277 | 1325 | CEG1000000, CEG2820000, CEGPA03200, CEG2821000 | CEG5240000
5 | 5.3.1.2.3 | CEG3791000 | 4 UQZ - Compensation Well Structure for PEB | EPC | 201 | 299 | 499 | 1103 | CEG3930000, CEGPA03200, CEG3931000 | CEG5240000
5 | 5.3.1.2.4 | CEG3850000 | Pipe Way between Angra 2 and Angra 3 (Concrete Structure) | EPC | 213 | 306 | 518 | 880 | CEG3910000, CEG3910000, CEG3911000, CEG3911000 | CEG3770000
5 | 5.3.1.2.5 | CEG3800000 | Concrete Structure for QHH Fuel Oil Tank (UTL) | EPC | 118 | 752 | 869 | 405 | CEG3370000, CEGPA03200, CEG3371000 | CEG2900000, CEG3500000
4 | 5.3.1.3 | - | Plant Area Piping and Piping Galleries |  | - | Anterior ao EPC | 1152 | 570
5 | 5.3.1.3.1 | CEG5130000 | Piping - Released Design (1/2UQB) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5221000
5 | 5.3.1.3.2 | CEG5120000 | Piping - Released Design (UZT) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5210000, CEG5221000
5 | 5.3.1.3.3 | CEG5140000 | Piping - Released Design (UQJ/UQM) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5221000
5 | 5.3.1.3.4 | CEG5150000 | Piping - Released Design (1/4UBZ) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5221000
5 | 5.3.1.3.5 | CEG5160000 | Piping - Released Design (1/4UMZ) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5221000
5 | 5.3.1.3.6 | CEG5170000 | Piping - Released Design (UGN) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5221000
5 | 5.3.1.3.7 | CEG5180000 | Piping - Released Design (1/5ULZ) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5221000
5 | 5.3.1.3.8 | CEG5190000 | Piping - Released Design (1/2UPZ) | ETN | - | - | Anterior ao EPC | 540 | CEG1347000, CEGPA01500 | CEG5221000
5 | 5.3.1.3.9 | CEG5221000 | Piping - Engineering Phase 1 (Workbook) (UZT and Piping Galleries) | EPC | 821 | 152 | 972 | 540 | CEG5120000, CEG5130000, CEG5140000, CEG5150000, CEG5160000, CEG5170000, CEG5180000, CEG5190000, CEG6570000, CEG3707000, CEG6700000 | CEG5230000, CEG5230000
5 | 5.3.1.3.10 | CEG5230000 | Piping - Prefabrication (UZT) and Piping Galleries | EPC | 570 | 433 | 1002 | 540 | CEG5220000, CEG5220000, CEG9271480, CEG9272740, CEG5221000, CEG5221000 | CEG5240000, CEG5240000
5 | 5.3.1.3.11 | CEG5240000 | Piping - Erection (UZT and Piping Galleries) | EPC | 540 | 523 | 1062 | 540 | CEG5230000, CEG5210000, CEG5230000, CEG4000000, CEG3890000, CEG3920000, CEG3990000, CEG3790000, CEG3791000, CEG3991000, CEG4001000 | CEG5250000, CEG5250000
5 | 5.3.1.3.12 | CEG5250000 | Piping - Cleaning, Hydrostatic Testing and Painting (UZT) | EPC | 350 | 743 | 1092 | 540 | CEG5240000, CEG5240000 | CEG5260000, CEG5260000, CEG6330000, CEG6330000
5 | 5.3.1.3.13 | CEG5260000 | Piping - Engineering Phase 2 (Documentation Closing) (UZT and Piping Galleries) | EPC | 300 | 853 | 1152 | 570 | CEG5250000, CEG5250000 | CEG6350000
3 | 5.3.2 | - | Condensate Purification Building (ULD) |  | - | Anterior ao EPC | 691 | 877
4 | 5.3.2.1 | CEG5050000 | Piping - Released Design (ULD) | ETN | - | - | Anterior ao EPC | 877 | CEG1347000, CEGPA01500 | CEG5070000, CEG3780000
4 | 5.3.2.2 | CEG5060000 | Released Electrical Design (ULD) | ETN | - | - | 61 | 877 | CEG1347000, CEGPA01500 | CEG3780000
4 | 5.3.2.3 | CEG3760000 | Concrete Structure (1/2GHC) | EPC | 92 | 152 | 243 | 935 | CEG3750000, CEGPA03200 | CEG3770000, CEG3780000
4 | 5.3.2.4 | CEG3765000 | Civil Finishing (ULD) | EPC | 275 | 152 | 426 | 877 | CEG3750000, CEGPA03200 | CEG3780000, CEG3780000
4 | 5.3.2.5 | CEG3780000 | Electromechanical Erection (GHC/ ULD) | EPC | 390 | 302 | 691 | 877 | CEG3760000, CEG3765000, CEG5050000, CEG5060000, CEG5070000, CEG3765000, CEG3770000, CEG6700000, CEG6700000 | CEG6320000, CEG4060000
4 | 5.3.2.6 | CEG3770000 | Erection of 1/2GHC Demineralized Water Tanks | EPC | 140 | 519 | 658 | 880 | CEG3760000, CEG3850000, CEG6700000, CEG6700000 | CEG3780000
3 | 5.3.3 | - | Control Gate (UYF) |  | 486 | 422 | 907 | 664
4 | 5.3.3.1 | CEG3540000 | Concrete Structure (UYF) | EPC | 153 | 422 | 574 | 664 | CEGPA03200, CEG4913600 | CEG3550000
4 | 5.3.3.2 | CEG3550000 | Civil Finishing Phase 1 (UYF) | EPC | 90 | 575 | 664 | 664 | CEG3540000 | CEG3560000
4 | 5.3.3.3 | CEG3560000 | CZ Electromechanical and Physical Protection Erection (UYF) | EPC | 243 | 665 | 907 | 664 | CEG3550000, CEG3830000, CEG6700000 | CEG6300000
3 | 5.3.4 | - | Administration Building/Refectory/Cold Workshop (UYA/UYB/UST) |  | 574 | 152 | 725 | 817
4 | 5.3.4.1 | CEG3511000 | Concrete Structure (UYA/ UYB/ UST) | EPC | 378 | 152 | 529 | 817 | CEG3290000, CEG3970000, CEG1346000, CEGPA03200 | CEG3520000
4 | 5.3.4.2 | CEG3520000 | Civil Finishing Phase 1 (UYA/ UYB/ UST) | EPC | 335 | 306 | 640 | 817 | CEG3510000, CEG3511000 | CEG3530000
4 | 5.3.4.3 | CEG3530000 | Electromechanical Erection (UYA/ UYB/ UST) | EPC | 360 | 366 | 725 | 817 | CEG3520000, CEG6700000, CEG6700000 | CEG1310000, CEG6290000
3 | 5.3.5 | - | Gas Cylinder Storage Area (UTG) |  | 454 | 352 | 805 | 767
4 | 5.3.5.1 | CEG3570000 | Concrete Structure (UTG) | EPC | 122 | 352 | 473 | 767 | CEG3360000, CEGPA03200, CEG3361000 | CEG3580000
4 | 5.3.5.2 | CEG3580000 | Civil Finishing Phase 1 (UTG) | EPC | 181 | 474 | 654 | 767 | CEG3570000 | CEG3590000
4 | 5.3.5.3 | CEG3590000 | Electromechanical Erection (UTG) | EPC | 151 | 655 | 805 | 767 | CEG3580000, CEG6700000, CEG6700000 | CEG1310000, CEG6310000
3 | 5.3.6 | - | Interconnections of 138kV and 500kV Lines |  | 1050 | 242 | 1291 | 347
4 | 5.3.6.1 | CEGPA42000 | Mobilization of the Contractor - Interconnections of the 138/500 kV Lines | EPC | 90 | 242 | 331 | 278 | CEG6680000 | CEG4910401
4 | 5.3.6.2 | CEG4910401 | Contractor's Preliminary Activities - 138/500 kV Lines | EPC | 120 | 332 | 451 | 278 | CEGPA42000 | CEG4910501, CEG4911100, CEG4911700, CEG4912300, CEG4912900
4 | 5.3.6.3 | - | SE-138 kV - Output Gap 138 kV - SE Furnas |  | 550 | 452 | 1001 | 278
5 | 5.3.6.3.1 | CEG4910501 | Executive Design - SE-138 kV - SE Furnas | EPC | 240 | 452 | 691 | 278 | CEG4910401 | CEG4910601, CEG4910701
5 | 5.3.6.3.2 | CEG4910601 | Supply - SE-138 kV - SE Furnas | EPC | 240 | 482 | 721 | 413 | CEG4910501 | CEG4910801
5 | 5.3.6.3.3 | CEG4910701 | Civil Construction - SE-138 kV - SE Furnas | EPC | 90 | 557 | 646 | 278 | CEG4910501 | CEG4910801
5 | 5.3.6.3.4 | CEG4910801 | Erection - SE-138 kV - SE Furnas | EPC | 240 | 647 | 886 | 278 | CEG4910701, CEG4910601, CEG9270550 | CEG4910901
5 | 5.3.6.3.5 | CEG4910901 | Commissioning - SE-138 kV - SE Furnas | EPC | 180 | 822 | 1001 | 278 | CEG4910801 | CEG4911000
5 | 5.3.6.3.6 | CEG4911000 | Energization - SE-138 kV - SE Furnas | EPC | 30 | 972 | 1001 | 278 | CEG4910901 | CEG1279000
4 | 5.3.6.4 | - | SE-138 kV - BCT |  | 510 | 452 | 961 | 288
5 | 5.3.6.4.1 | CEG4911100 | Executive Design - SE-138 kV - BCT | EPC | 180 | 452 | 631 | 288 | CEG4910401 | CEG4911200, CEG4911300
5 | 5.3.6.4.2 | CEG4911200 | Supply - SE-138 kV - BCT | EPC | 240 | 512 | 751 | 318 | CEG4911100 | CEG4911400
5 | 5.3.6.4.3 | CEG4911300 | Civil Construction - SE-138 kV - BCT | EPC | 90 | 632 | 721 | 288 | CEG4911100 | CEG4911400
5 | 5.3.6.4.4 | CEG4911400 | Erection - SE-138 kV - BCT | EPC | 90 | 722 | 811 | 288 | CEG4911300, CEG4911200 | CEG4911500
5 | 5.3.6.4.5 | CEG4911500 | Commissioning - SE-138 kV - BCT | EPC | 60 | 812 | 871 | 288 | CEG4911400 | CEG4911600
5 | 5.3.6.4.6 | CEG4911600 | Energization - SE-138 kV - BCT | EPC | 30 | 932 | 961 | 288 | CEG4911500 | CEG1279000
4 | 5.3.6.5 | - | LT 138 kV - Interconnection of SE Furnas - SE BCT |  | 510 | 452 | 961 | 288
5 | 5.3.6.5.1 | CEG4911700 | Executive Design - LT 138 kV | EPC | 180 | 452 | 631 | 288 | CEG4910401 | CEG4911800, CEG4911900
5 | 5.3.6.5.2 | CEG4911800 | Supply - LT 138 kV | EPC | 240 | 512 | 751 | 348 | CEG4911700 | CEG4912000
5 | 5.3.6.5.3 | CEG4911900 | Civil Construction - LT 138 kV | EPC | 120 | 572 | 691 | 288 | CEG4911700 | CEG4912000
5 | 5.3.6.5.4 | CEG4912000 | Erection - LT 138 kV | EPC | 150 | 692 | 841 | 288 | CEG4911900, CEG4911800 | CEG4912100
5 | 5.3.6.5.5 | CEG4912100 | Commissioning - LT 138 kV | EPC | 60 | 842 | 901 | 288 | CEG4912000 | CEG4912200
5 | 5.3.6.5.6 | CEG4912200 | Energization - LT 138 kV | EPC | 30 | 932 | 961 | 288 | CEG4912100 | CEG1279000
4 | 5.3.6.6 | - | SE 500 kV - Entrance Gap - SE Furnas |  | 630 | 572 | 1201 | 347
5 | 5.3.6.6.1 | CEG4912300 | Executive Design - SE 500 kV | EPC | 300 | 572 | 871 | 347 | CEG4910401 | CEG4912400, CEG4912500
5 | 5.3.6.6.2 | CEG4912500 | Civil Construction - SE 500 kV | EPC | 90 | 752 | 841 | 347 | CEG4912300 | CEG4912600
5 | 5.3.6.6.3 | CEG4912400 | Supply - SE 500 kV | EPC | 210 | 752 | 961 | 467 | CEG4912300 | CEG4912600
5 | 5.3.6.6.4 | CEG4912600 | Erection - SE 500 kV | EPC | 270 | 842 | 1111 | 347 | CEG4912500, CEG4912400 | CEG4912700
5 | 5.3.6.6.5 | CEG4912700 | Commissioning - SE 500 kV | EPC | 110 | 1092 | 1201 | 347 | CEG4912600 | CEG4912800
5 | 5.3.6.6.6 | CEG4912800 | Energization - SE 500 kV | EPC | 30 | 1172 | 1201 | 347 | CEG4912700 | CEG1290000, CEG4913200
4 | 5.3.6.7 | - | LT 500 kV - Interconnection of BAT's Trafos - SE Furnas |  | 630 | 662 | 1291 | 347
5 | 5.3.6.7.1 | CEG4912900 | Executive Design - LT 500 kV | EPC | 210 | 662 | 871 | 347 | CEG4910401 | CEG4913000, CEG4913100
5 | 5.3.6.7.2 | CEG4913000 | Supply - LT 500 kV | EPC | 260 | 762 | 1021 | 497 | CEG4912900 | CEG4913200
5 | 5.3.6.7.3 | CEG4913100 | Civil Construction - LT 500 kV | EPC | 180 | 782 | 961 | 347 | CEG4912900 | CEG4913200
5 | 5.3.6.7.4 | CEG4913200 | Erection - LT 500 kV | EPC | 240 | 962 | 1201 | 347 | CEG4913100, CEG4913000, CEG4912800 | CEG4913300
5 | 5.3.6.7.5 | CEG4913300 | Commissioning - LT 500 kV | EPC | 150 | 1142 | 1291 | 347 | CEG4913200 | CEG4913400
5 | 5.3.6.7.6 | CEG4913400 | Energization - LT 500 kV | EPC | 40 | 1252 | 1291 | 347 | CEG4913300 | CEG1290000
2 | 5.4 | - | Final Erection and Commissioning Services for Conventional and External Area Systems |  | 790 | 692 | 1481 | 271
3 | 5.4.1 | CEG6320000 | Final Erection and Comissioning Services of Components and Systems (GHC/ ULD) | EPC | 180 | 692 | 871 | 881 | CEG3780000 | CEG6470000, CEG6350000
3 | 5.4.2 | CEG6290000 | Final Erection and Comissioning Services of Components and Systems (UYA / UYB / UST) | EPC | 210 | 726 | 935 | 817 | CEG3530000 | CEG6470000, CEG6350000
3 | 5.4.3 | CEG6310000 | Final Erection and Comissioning Services of Components and Systems (UTG) | EPC | 180 | 806 | 985 | 767 | CEG3590000 | CEG6470000, CEG6350000
3 | 5.4.4 | CEG3190000 | Final Erection and Comissioning Services of the LA Water-Steam Circuit (UMA) | EPC | 341 | 832 | 1172 | 400 | CEG3180000, CEG1411000, CEG2680000, CEG4930000 | CEG3870000, CEG6470000, CEG6350000
3 | 5.4.5 | CEG3230000 | Ventilation System Commissioning (UMA) | EPC | 420 | 881 | 1300 | 452 | CEG3220000 | CEG6470000
3 | 5.4.6 | CEG3210000 | Final Erection and Comissioning Services of Electrical and I&C Systems(UMA) | EPC | 334 | 883 | 1216 | 536 | CEG3200000, CEG9270280, CEG9270910, CEG9270880, CEG9270850, CEG9270820, CEG9270790, CEG9270760, CEG9270730, CEG9270700, CEG9270670, CEG9270640, CEG9270610 | CEG6470000, CEG6350000
3 | 5.4.7 | CEG6300000 | Final Erection and Comissioning Services of Components and Systems (UYF) | EPC | 181 | 908 | 1088 | 664 | CEG3560000 | CEG6470000, CEG6350000
3 | 5.4.8 | CEG6330000 | Final Erection and Comissioning Services of the Plant Area (UZT) and Galleries | EPC | 200 | 1013 | 1212 | 540 | CEG5250000, CEG5250000 | CEG6470000, CEG6350000
3 | 5.4.9 | CEG6360000 | Final Erection and Comissioning Services of the Turbogenerator and Auxiliaries Set (UMA) | EPC | 217 | 1127 | 1343 | 409 | CEG3135000, CEG3128000, CEG3130000 | CEG1272000, CEG1273000, CEG6470000, CEG6350000
3 | 5.4.10 | CEG1272000 | Start of Commissioning of the CF H - Turbogenerator | EPC | - | 1277 | - | 476 | CEG6360000 | CEG1273000
3 | 5.4.11 | CEG3280000 | Final Erection and Comissioning Services of Components and Systems (UPC / UQB) | EPC | 190 | 1292 | 1481 | 124 | CEG3270000, CEG3382000, CEG3384000 | CEG1016280, CEG6350000
3 | 5.4.12 | CEG1273000 | Completion of CF H Commissioning - Turbogenerator | EPC | - | - | 1343 | 409 | CEG1272000, CEG6360000 | CEG6470000
1 | 6 | - | FINAL TESTS AND STARTUP |  | 1621 | 330 | 1950 | 0
2 | 6.1 | CEG1520000 | Start of Preparatory Activities for Commissioning Recommended by FRAMATOME | EPC | - | 330 | - | 935 | CEG6670000 | CEG1590000, CEG1900000, CEG2250000, CEG2320000, CEG2730000, CEG2790000, CEG2810000, CEG1279000, CEG4320000, CEG4290000, CEG3717000
2 | 6.2 | CEG0916180 | Equipment Testing and Testing Operations | EPC | 214 | 1366 | 1579 | 26 | CEG0916160, CEG1474000, CEG3870000, CEG1016280 | CEG1300000, CEG6450000
2 | 6.3 | CEG1470000 | Primary Circuit Pressure Test (UJA) | EPC | 35 | 1580 | 1614 | 0 | CEG1285000, CEG0916260, CEG0916280 | CEG1310000, CEG1300000, CEG6460000, CEG0916220, CEG6450000
2 | 6.4 | CEG1302000 | Secondary Circuit Pressure Test (UMA) (Phase A) | EPC | 35 | 1580 | 1614 | 23 | CEG3100000, CEG3180000, CEG3146000, CEG1285000, CEG3870000, CEG1411000, CEG5350000, CEG6460000, CEG3087000 | CEG1481000, CEG1310000, CEG0916220
2 | 6.5 | CEG0916220 | First Inspection of Primary Circuit Main Equipment | EPC | 20 | 1615 | 1634 | 23 | CEG1470000, CEG1302000 | CEG1311000, CEG0916470
2 | 6.6 | CEG1300000 | JMA Containment Ball Pressure Test - TPC (UJA) (Phase A) | EPC | 35 | 1615 | 1649 | 0 | CEG1110000, CEG1361000, CEG1075000, CEG1270000, CEG1470000, CEG6450000, CEG0916410, CEG0916180 | CEG1471000
2 | 6.7 | CEG1311000 | First Hot Operation (Phase B) | EPC | 45 | 1654 | 1698 | 4 | CEG1310000, CEG0916220, CEG9271450 | CEG2650000, CEG6470000, CEG0916240
2 | 6.8 | CEG0916240 | Second Inspection of Reactor Main Equipment | EPC | 50 | 1699 | 1748 | 4 | CEG1311000 | CEG6470000
2 | 6.9 | CEG1320000 | Core Loading (Phase C) | EPC | 29 | 1754 | 1782 | 0 | CEG6470000, CEG0916470, CEGLIC0150 | CEG1315000
2 | 6.10 | CEG6560000 | Second Hot Operation (Phase C) | EPC | 28 | 1783 | 1810 | 0 | CEG1315000 | CEG1330000
2 | 6.11 | CEG1330000 | Preparation for Power Tests (Phase D) | EPC | 20 | 1811 | 1830 | 0 | CEG6560000 | CEG1491000, CEG1337000
2 | 6.12 | CEG1337000 | First Criticality and Beginning of Physical Tests (Phase D) | EPC | - | 1831 | - | 0 | CEG1330000 | CEG1340000, CEG1325000, CEG6490000
2 | 6.13 | CEG6490000 | Power Escalation (0% to 30%) (Phase D) | EPC | 30 | 1831 | 1860 | 0 | CEG1491000, CEG1325000, CEG1337000 | CEG6500000, CEG6520000
2 | 6.14 | CEG6500000 | Power Escalation (30% to 80%) (Phase D) | EPC | 30 | 1861 | 1890 | 0 | CEG6490000, CEG6520000 | CEG6510000, CEG6530000
2 | 6.15 | CEG6510000 | Power Escalation (80% to 100%) (Phase D) | EPC | 30 | 1891 | 1920 | 0 | CEG6500000, CEG6530000 | CEG6540000, CEG0916780
2 | 6.16 | CEG0916780 | Plant Released for Pilot Operation | EPC | - | - | 1920 | 0 | CEG6510000 | CEG1335000
2 | 6.17 | CEG1335000 | Plant Demonstration Tests (Phase D) | EPC | 30 | 1921 | 1950 | 0 | CEG6540000, CEG0916780 | CEG6550000
1 | 7 | - | TRAINING CENTER |  | - | Em andamento | 764 | 808
2 | 7.1 | - | Detailed Building Design |  | - | Em andamento | Anterior ao EPC | 808
3 | 7.1.1 | CEG9012000 | Execution of the Executive Design of the Simulator Building | ETN | - | Em andamento | Anterior ao EPC | 808 | CEG9011000 | CEG9013000
2 | 7.2 | - | Construction of the Simulator Building |  | - | Anterior ao EPC | 126 | 808
3 | 7.2.1 | CEG9013000 | Hiring of the Construction of the Simulator Building | ETN | - | Anterior ao EPC | Anterior ao EPC | 808 | CEG9012000 | CEG9014000
3 | 7.2.2 | CEG9014000 | Mobilization for Construction of the Simulator Building | ETN | - | Anterior ao EPC | Anterior ao EPC | 808 | CEG9013000 | CEG9015000
3 | 7.2.3 | CEG9015000 | Hiring of the Simulator Building | ETN | - | Anterior ao EPC | 126 | 808 | CEG9014000 | CEG9023000
2 | 7.3 | - | Fabrication and Erection of the Simulator |  | - | Em andamento | 764 | 808
3 | 7.3.1 | CEG9021000 | Develop Simulator Design/Specifications | ETN | - | Em andamento | Anterior ao EPC | 1006 | CEG9010000 | CEG9022000
3 | 7.3.2 | CEG9020000 | Design, develop, assemble and test the Simulator | ETN | - | Em andamento | 188 | 1006 | CEG9010000 | CEG9030000
3 | 7.3.3 | CEG9022000 | Manufacture and Supply Simulator Equipment | ETN | - | Anterior ao EPC | Anterior ao EPC | 1006 | CEG9021000 | CEG9023000
3 | 7.3.4 | CEG9023000 | Carry out Simulator Erection and Testing | ETN | 260 | 127 | 386 | 808 | CEG9022000, CEG9015000 | CEG9030000
3 | 7.3.5 | CEG9030000 | Prepare the Simulator to start training | ETN | 183 | 387 | 569 | 808 | CEG9020000, CEG9023000 | CEG9040000
3 | 7.3.6 | CEG9040000 | Training of Angra 3 operators in the Simulator | ETN | 195 | 570 | 764 | 808 | CEG9030000 | CEG6470000