## Attachment II
Comments:
Days from the mobilization start date (D=0).
Total float = slack in relation to the project's critical path.
Level | Cod_aux | Activity Id | Description | Scope | Duration | Initial date (day) | Final date (day) | Total Float
0 | 0 | - | Angra 3 - EPC Construction Schedule |  | - | 0 | 1950 | 0
1 | 1 | - | KEY MILESTONES |  | 1951 | 0 | 1950 | 0
2 | 1.4 | - | Civil Construction |  | 570 | 0 | - | 354
3 | 1.4.1 | CEG6670000 | Beginning of EPCist Mobilization | EPC | - | 0 | - | 0
2 | 1.5 | - | Electromechanical Erection |  | 1507 | 152 | 1658 | 124
3 | 1.5.1 | CEG1230000 | Start of SAC Ventilation Erection (UBA) | EPC | - | 152 | - | 403
3 | 1.5.2 | CEG6400000 | Start of Piping Erection (UMA) | EPC | - | 152 | - | 1080
3 | 1.5.3 | CEG3085000 | Completion of Mobilization for the Erection of Condensers (UMA) | EPC | - | 194 | - | 409
3 | 1.5.4 | CEG6410000 | Start of Electrical and Ventilation Erection (ULB) | EPC | - | 400 | - | 399
3 | 1.5.5 | CEG6420000 | Start of Generator Busbars Erection (UMA / Ext.) | EPC | - | 524 | - | 598
3 | 1.5.7 | CEG6390000 | Start of Piping Erection (UZT / PEB) | EPC | - | 712 | - | 731
3 | 1.5.8 | CEG1391000 | Start of Piping Erection (UJB) | EPC | - | 877 | - | 295
3 | 1.5.9 | CEG6350000 | Completion of Electromechanical Erection - Conventional Area | EPC | - | - | 1556 | 226
3 | 1.5.10 | CEG6340000 | Completion of Electromechanical Erection - Nuclear Area | EPC | - | - | 1658 | 124
2 | 1.6 | - | Phase A Commissioning |  | 708 | 942 | 1649 | 4
3 | 1.6.1 | CEG1262000 | Start of Commissioning of the Auxiliary Electrical System (UBA/S1) (Phase A) | EPC | - | 942 | - | 158
3 | 1.6.2 | CEG1279000 | Connection of 138 kV Offsite Power Grid (138 kV "Switch-on") (Phase A) | EPC | - | 1062 | - | 218
3 | 1.6.3 | CEG6430000 | Auxiliary Electrical System ready to use (UBA / Start V-IBS) (Phase A) | EPC | - | - | 1106 | 218
3 | 1.6.4 | CEG6440000 | Start of Commissioning of JN / FAK (UJA) Systems (Phase A) | EPC | - | 1257 | - | 218
3 | 1.6.5 | CEG1285000 | Start of Primary Circuit Pressure Test (UJA) (Phase A) | EPC | - | 1580 | - | 0
3 | 1.6.6 | CEG6460000 | Start of Secondary Circuit Pressure Test (UMA) (Phase A) | EPC | - | 1580 | - | 23
3 | 1.6.7 | CEG1290000 | 500 kV Main Grid Connection (500 kV Switch-on) (Phase A) | EPC | - | 1580 | - | 59
3 | 1.6.8 | CEG1481000 | Completion of Secondary Circuit Pressure Test(UMA) (Phase A) | EPC | - | - | 1614 | 39
3 | 1.6.9 | CEG6450000 | Start of Pressure Test of the Containment Sphere JMA (UJA) (Phase A) | EPC | - | 1615 | - | 0
3 | 1.6.10 | CEG1471000 | Completion of Pressure Test of the Containment Sphere JMA (UJA) (Phase A) | EPC | - | - | 1649 | 0
2 | 1.7 | - | Commissioning Phases B, C and D |  | 297 | 1654 | 1950 | 0
3 | 1.7.1 | CEG1310000 | Start of the First Hot Operation (Phase B) | EPC | - | 1654 | - | 0
3 | 1.7.2 | CEG6470000 | Start of Core Loading (Phase C) | EPC | 1 | 1753 | 1753 | 0
3 | 1.7.3 | CEG1315000 | Start of the Second Hot Operation (Phase C) | EPC | - | 1783 | - | 0
3 | 1.7.4 | CEG1325000 | First Criticality (Phase D) | EPC | - | 1831 | - | 0
3 | 1.7.5 | CEG1491000 | Start of Power Tests (Start: rise 0% to 30%) (Phase D) | EPC | - | 1831 | - | 0
3 | 1.7.6 | CEG1327000 | Synchronization with the 500 kV Main Grid (Phase D) | EPC | - | 1841 | - | 20
3 | 1.7.7 | CEG6520000 | Power Escalation (Start rise 30% to 80%) (Phase D) | EPC | - | 1861 | - | 0
3 | 1.7.8 | CEG6530000 | Power Escalation (Finish: rise 80% to 100%) (Phase D) | EPC | - | - | 1890 | 0
3 | 1.7.9 | CEG6540000 | Start of Plant Demonstration Testing (Phase D) | EPC | - | 1921 | - | 0
3 | 1.7.10 | CEG6550000 | End of Trial Operation (Phase D) | EPC | - | - | 1950 | 0
1 | 2 | - | SITE AND MAIN CONTRACTS |  | - | 0 | 1169 | 297
2 | 2.1 | - | Mobilizations |  | 152 | 0 | 151 | 400
3 | 2.1.2 | CEG6680000 | Mobilization and Installation of the EPCist Site (Nuclear Area) | EPC | 152 | 0 | 151 | 124
3 | 2.1.3 | CEGPA03200 | Mobilization and Installation of the EPCist Site (Civil Construction) | EPC | 152 | 0 | 151 | 395
3 | 2.1.4 | CEG6700000 | Mobilization and Installation of the EPCist Site (Conventional Area) | EPC | 152 | 0 | 151 | 400
2 | 2.2 | - | Hiring Design Engineering Services |  | - | 121 | 542 | 1111
3 | 2.2.5 | - | Hiring Complementary Electrical Design |  | 422 | 121 | 542 | 1408
4 | 2.2.5.1 | CEG9274010 | Signing of the Engineering Services Contract for the Complementary Electrical Design | EPC | 31 | 121 | 151 | 1408
4 | 2.2.5.2 | CEG9274020 | Authorization Start of Activities of the Complementary Electrical Design Engineering Services Contract | EPC | 31 | 152 | 182 | 1408
4 | 2.2.5.3 | CEG9274030 | Issuance of Documentation for Engineering Services of the Complementary Electrical Design | EPC | 360 | 183 | 542 | 1408
3 | 2.2.8 | - | Hiring of Pools Erection for Fuel Elements (phases 1 and 2) |  | 439 | 407 | 528 | 184
4 | 2.2.8.2 | CEG1541000 | Mobilization for Pool Lining Erection Phase 2 | EPC | 122 | 407 | 528 | 184
2 | 2.3 | - | Procurement (UJA/UJB/UJE/UJF/UKA/UKH) |  | - | 152 | 1169 | 207
3 | 2.3.1 | - | Procurement of Equipment and Materials |  | - | 231 | 1169 | 504
4 | 2.3.1.10 | - | M114 Tanks - GR5 |  | - | 277 | 876 | 295
4 | 2.3.1.12 | - | M178A Special Ports |  | 535 | 259 | 793 | 449
4 | 2.3.1.16 | - | M302 Locks Sealing Walls |  | 549 | 429 | 977 | 175
4 | 2.3.1.17 | - | M307 Wall Crane *UJA* |  | 520 | 292 | 811 | 461
4 | 2.3.1.19 | - | M325 Reactor Pressure Vessel Support |  | 300 | 251 | 550 | 322
4 | 2.3.1.22 | - | M335 Pressure Equalizer Structure |  | 575 | 595 | 1169 | 691
4 | 2.3.1.24 | - | M354 Lifts |  | 390 | 231 | 620 | 872
3 | 2.3.2 | - | Civil Dependent Equipment Procurement |  | - | 152 | 691 | 606
4 | 2.3.2.2 | - | M130 KBF Degassing Column |  | - | 152 | 691 | 606
4 | 2.3.2.3 | - | M603 Hybrid Bed Filters |  | 150 | 392 | 541 | 309
3 | 2.3.3 | - | Procurement of Fuel Elements |  | 1241 | - | 413 | 0
4 | 2.3.3.1 | CEG9274100 | Signing of the Contract for the Fabrication of Fuel Elements | EPC | - | - | 413 | 0
2 | 2.4 | - | Procurement (UBA / UBP / ULB / Transformers) |  | - | 152 | 501 | 951
3 | 2.4.1 | - | Procurement of Equipment and Materials |  | - | 152 | 501 | 951
4 | 2.4.1.9 | CEG3598000 | CIP Delivery Cable Trays and Accessories (UBA) (Package E013/ Assembler/ 1. lot) | EPC | - | - | 151 | 158
4 | 2.4.1.10 | CEG4410000 | CIP Delivery Lamps and Luminaires of the Lighting Sys.(UBA) (Package E010/ Assembler) | EPC | - | - | 151 | 583
4 | 2.4.1.11 | CEG3705000 | CIP Delivery Ducts/ Ventilation Supports SAC (UBA) (Package M628/ Assembler/ 1. lot) | EPC | - | 152 | - | 438
4 | 2.4.1.12 | CEG5750000 | Delivery to the Construction Site of the Fire Network Pipes (UBA) supplied by the Assembler | EPC | - | - | 201 | 418
4 | 2.4.1.16 | - | M612A Fire Protection System |  | 350 | 152 | 501 | 418
2 | 2.5 | - | Procurement (UMA and Other Buildings) |  | - | 2 | 1031 | 39
3 | 2.5.1 | - | Procurement of Equipment and Materials |  | - | 2 | 1031 | 39
4 | 2.5.1.5 | CEG9210000 | Negotiation for Termination of Services - Tanks and Pressure Vessels (Package M116/M119) | EPC | 1 | 172 | 172 | 400
4 | 2.5.1.6 | CEG5070000 | CIP Delivery Materials for Electromechanical Erection (ULD) | EPC | - | - | 181 | 877
4 | 2.5.1.7 | CEG5210000 | CIP Delivery UZT Materials and Pipe Galleries | EPC | - | - | 402 | 540
4 | 2.5.1.9 | CEG5110000 | CIP Delivery Materials for Electromechanical Erection (UPC/ UQB) | EPC | - | - | 721 | 159
4 | 2.5.1.12 | - | C001 Shielding Doors |  | 519 | 423 | 941 | 158
4 | 2.5.1.13 | - | C002 Common Steel Doors |  | 519 | 423 | 941 | 158
4 | 2.5.1.15 | - | E011 Telephone System |  | 150 | 122 | 271 | 583
4 | 2.5.1.16 | - | E015 Grounding Material |  | 366 | 346 | 711 | 158
4 | 2.5.1.18 | - | E026 Radio System |  | 390 | 432 | 821 | 158
4 | 2.5.1.19 | - | E028 Distribution Boxes for the Communication System |  | 390 | 432 | 821 | 158
4 | 2.5.1.20 | - | E029 Sealing Materials |  | 390 | 322 | 711 | 158
4 | 2.5.1.21 | - | E032 Communication Cables |  | 390 | 322 | 711 | 158
4 | 2.5.1.22 | - | E034 Installation Materials |  | 390 | 322 | 711 | 158
4 | 2.5.1.23 | - | E039B Luminaires and Accessories for External Lighting System |  | 150 | 122 | 271 | 583
4 | 2.5.1.27 | - | E070 CCTV for JEB and Radiological Protection |  | 390 | 2 | 391 | 692
4 | 2.5.1.28 | - | E104 Line + Equipment for Connection to 138 kV network |  | 390 | 137 | 526 | 278
4 | 2.5.1.30 | - | GR011 Protective Shutters |  | 150 | 332 | 481 | 331
4 | 2.5.1.31 | - | GR013B Electric Air Humidifier |  | 150 | 185 | 334 | 516
4 | 2.5.1.32 | - | GR019 Block Valves |  | 150 | 185 | 334 | 516
4 | 2.5.1.33 | - | GR028A Air Handling Unit - AHU |  | 150 | 185 | 334 | 516
4 | 2.5.1.34 | - | GR028B Air Handling Unit - AHU |  | 150 | 185 | 334 | 516
4 | 2.5.1.35 | - | GR046 Remote actuation cables for Dampers |  | - | 185 | 334 | 516
4 | 2.5.1.37 | - | GR200 Temporary Ventilation System ULB |  | 150 | 217 | 366 | 403
4 | 2.5.1.38 | - | GR201 Temporary Ventilation System UJA/UJB/UKA |  | 150 | 185 | 334 | 516
4 | 2.5.1.39 | - | GR202 Temporary UBA System (FANCOILS, PUMPS...) |  | 150 | 217 | 366 | 403
4 | 2.5.1.40 | - | I001 Electronic Transmitters |  | 332 | 551 | 882 | 536
4 | 2.5.1.41 | - | I002 Pressure gauges |  | 332 | 551 | 882 | 536
4 | 2.5.1.42 | - | I006 Control System (PLC) |  | 423 | 460 | 882 | 536
4 | 2.5.1.43 | - | I007 Signal Distribution Module |  | 332 | 551 | 882 | 536
4 | 2.5.1.44 | - | I009 Electro-electronic Equipment for Commissioning and I&C Cold Workshop |  | 332 | 551 | 882 | 536
4 | 2.5.1.45 | - | I003 Orifice Plates |  | 362 | 521 | 882 | 536
4 | 2.5.1.46 | - | I010 Pressure Measuring Equipment for Commissioning and I&C Cold Workshop (New Code Value) |  | 332 | 551 | 882 | 536
4 | 2.5.1.47 | - | I011 Tools for Commissioning and I&C Cold Workshop |  | 362 | 521 | 882 | 536
4 | 2.5.1.48 | - | I012 Workbenches for Commissioning and I&C Cold Workshop |  | 332 | 551 | 882 | 536
4 | 2.5.1.49 | - | I015 Automation of the Modernization of the Demineralization System |  | 390 | 373 | 762 | 536
4 | 2.5.1.50 | - | M102 Heat Exchangers - GR3 |  | 690 | 162 | 851 | 409
4 | 2.5.1.51 | - | M113 Feeding Water Tank |  | 1 | 152 | 152 | 400
4 | 2.5.1.52 | - | M116 Sample Collection Tank |  | 240 | 172 | 411 | 400
4 | 2.5.1.53 | - | M161B Waste Transfer Station |  | 150 | 762 | 911 | 541
4 | 2.5.1.54 | - | M174 Water Separator |  | 180 | 732 | 911 | 541
4 | 2.5.1.55 | - | M176 Decontamination Basins with Agitator |  | 397 | 635 | 1031 | 541
4 | 2.5.1.56 | - | M181 Tube Covers |  | 150 | 762 | 911 | 541
4 | 2.5.1.57 | - | M191 Hot Laundry |  | 214 | 818 | 1031 | 541
4 | 2.5.1.58 | - | M192 Cold Workshop |  | 305 | 607 | 911 | 541
4 | 2.5.1.59 | - | M193 Hot Workshop |  | 214 | 698 | 911 | 541
4 | 2.5.1.62 | - | M196 Injectors and Sprinklers GN |  | 275 | 637 | 911 | 541
4 | 2.5.1.64 | - | M198 Electrolytic Cell Bank |  | 244 | 668 | 911 | 541
4 | 2.5.1.65 | - | M203 Air Compressors |  | 420 | 612 | 1031 | 541
4 | 2.5.1.66 | - | M215 Control Air Compressor |  | 150 | 562 | 711 | 400
4 | 2.5.1.67 | - | M219 Air Blowers |  | 244 | 788 | 1031 | 541
4 | 2.5.1.68 | - | M224 Bitumen Charging Pump |  | 150 | 642 | 791 | 541
4 | 2.5.1.70 | - | M226 Plastic Pumps GN |  | 275 | 757 | 1031 | 541
4 | 2.5.1.71 | - | M227 Circulation Pumps GN |  | 275 | 757 | 1031 | 541
4 | 2.5.1.72 | - | M228 Dosing PumpsGN |  | 275 | 757 | 1031 | 541
4 | 2.5.1.75 | - | M342 Radiation Sample Holder |  | 244 | 626 | 869 | 182
4 | 2.5.1.77 | - | M380 Component/Pipe Identification System |  | 150 | 92 | 241 | 124
4 | 2.5.1.79 | - | M400 Drainage Boxes / Drains |  | 150 | 301 | 450 | 395
4 | 2.5.1.80 | - | M401 Rectangular Ferritic Lugs |  | 150 | 283 | 432 | 540
4 | 2.5.1.81 | - | M403 Containment Discs in FRP |  | 120 | 193 | 312 | 540
4 | 2.5.1.82 | - | M404 Galvanized Piping |  | 150 | 2 | 151 | 403
4 | 2.5.1.83 | - | M405 Cast Iron Piping |  | 150 | 2 | 151 | 403
4 | 2.5.1.84 | - | M413 Miscellaneous (Miscellaneous Materials) |  | 270 | 72 | 341 | 441
4 | 2.5.1.85 | - | M420A Welded Piping - ESPES |  | 400 | 272 | 671 | 441
4 | 2.5.1.86 | - | M432A Screws, Nuts and Bolts on RCD5 |  | 31 | 121 | 151 | 403
4 | 2.5.1.87 | - | M434B Piping in PVC + GRP |  | 150 | 2 | 151 | 403
4 | 2.5.1.88 | - | M434C PRFC piping |  | 150 | 2 | 151 | 403
4 | 2.5.1.89 | - | M436 Polyethylene Piping |  | 150 | 2 | 151 | 403
4 | 2.5.1.90 | - | M437 PVC piping |  | 150 | 2 | 151 | 403
4 | 2.5.1.91 | - | M438 Copper Tubing |  | 120 | 222 | 341 | 441
4 | 2.5.1.92 | - | M440Embedded Parts for PAB/UMA |  | 150 | 2 | 151 | 124
4 | 2.5.1.93 | - | M441 Embedded Parts for PAB/UPC |  | 270 | 362 | 631 | 124
4 | 2.5.1.94 | - | M480C Fireproof Gloves |  | 181 | 201 | 381 | 418
4 | 2.5.1.95 | - | M491A Special Foundations |  | 125 | 217 | 341 | 441
4 | 2.5.1.96 | - | M492 CPT Fixed Points |  | 150 | 419 | 568 | 682
4 | 2.5.1.97 | - | M495 Miscellaneous Supports |  | 150 | 192 | 341 | 441
4 | 2.5.1.98 | - | M502 External Hydrants |  | 150 | 292 | 441 | 418
4 | 2.5.1.99 | - | M503 Type 164 Flow Displays |  | 150 | 292 | 441 | 418
4 | 2.5.1.100 | - | M505 Filters Type 193 |  | 150 | 292 | 441 | 418
4 | 2.5.1.101 | - | M506 RC5 Globe Valves |  | 150 | 292 | 441 | 418
4 | 2.5.1.102 | - | M507 Internal Hydrants |  | 150 | 232 | 381 | 418
4 | 2.5.1.103 | - | M508A Diaphragm Valves |  | 150 | 292 | 441 | 418
4 | 2.5.1.104 | - | M508B Ball Valves |  | 150 | 292 | 441 | 418
4 | 2.5.1.105 | - | M514B Hoses |  | 150 | 292 | 441 | 418
4 | 2.5.1.106 | - | M514C Flexible Metal Pipes |  | 150 | 192 | 341 | 441
4 | 2.5.1.107 | - | M514D Couplings |  | 150 | 171 | 320 | 872
4 | 2.5.1.108 | - | M514E Ball Valves |  | 150 | 171 | 320 | 872
4 | 2.5.1.109 | - | M514F Transition Parts and Coupling. |  | 150 | 171 | 320 | 872
4 | 2.5.1.110 | - | M514H PVC Y Filters |  | 150 | 171 | 320 | 872
4 | 2.5.1.111 | - | M515 Type 356 Diaphragm Valves |  | 150 | 171 | 320 | 872
4 | 2.5.1.112 | - | M516 Vertical Check Valves |  | 150 | 171 | 320 | 872
4 | 2.5.1.113 | - | M517 Solenoid Valves |  | 150 | 171 | 320 | 872
4 | 2.5.1.114 | - | M518A Electric Heaters |  | 150 | 171 | 320 | 872
4 | 2.5.1.115 | - | M518B Building/ Globe Valves |  | 150 | 171 | 320 | 872
4 | 2.5.1.116 | - | M519 Vacuum Breaker Valves |  | 150 | 171 | 320 | 872
4 | 2.5.1.117 | - | M521 Type 288 Flow Restrictor |  | 150 | 171 | 320 | 872
4 | 2.5.1.118 | - | M607A Interconnection Ducts between UKA and UKH |  | 336 | 456 | 791 | 541
4 | 2.5.1.119 | - | M607B Gratings and Diffusers for Nuclear Buildings |  | 197 | 145 | 341 | 441
4 | 2.5.1.120 | - | M607C Metal profiles and sheets for component fixing structure |  | 150 | 192 | 341 | 441
4 | 2.5.1.121 | - | M608A Gratings and Diffusers for Conventional Buildings (except UBA) |  | 150 | 72 | 221 | 441
4 | 2.5.1.122 | - | M608B UBA Building Gratings and Diffusers |  | 150 | 192 | 341 | 441
4 | 2.5.1.123 | - | M613 Manual Fire Extinguishers |  | 367 | 195 | 561 | 418
4 | 2.5.1.126 | - | M620 Oil Separator |  | 184 | 566 | 749 | 182
4 | 2.5.1.127 | - | M626 Embedded Parts 1st. Stage |  | 2 | 152 | 152 | 0
4 | 2.5.1.128 | - | M627 Ducts, Supports, Insulation/Nuclear Area |  | 150 | 10 | 159 | 322
1 | 3 | - | NUCLEAR AREA (UJA/ UJB/ UJE/ UJF / UKA/ UKH ) |  | - | 152 | 1752 | 198
2 | 3.1 | - | Civil Construction |  | - | 152 | 1234 | 716
3 | 3.1.1 | - | Construction of the Reactor Building (UJA) |  | 1084 | 870 | 1234 | 419
4 | 3.1.1.3 | - | Finishing (UJA) |  | 801 | 870 | 1234 | 182
3 | 3.1.2 | - | Construction of the Reactor Building (Annulus) (UJB) |  | 993 | 364 | 1115 | 538
4 | 3.1.2.2 | - | Finishing (UJB) |  | 905 | 559 | 1086 | 567
4 | 3.1.2.3 | - | Steel Structure (UJB) |  | 993 | 364 | 1115 | 538
3 | 3.1.3 | - | Construction of the Reactor Auxiliary Building (UKA) |  | 1026 | 152 | 1177 | 773
4 | 3.1.3.1 | - | Concrete Structure (UKA) |  | 734 | 766 | 885 | 1065
4 | 3.1.3.2 | - | Civil Dependent (UKA) |  | 226 | 542 | - | 822
4 | 3.1.3.3 | - | Finishing (UKA) |  | 1026 | 152 | 1177 | 605
3 | 3.1.4 | - | Construction of the Gas Discharge Chimney (UKH) |  | - | 548 | 1187 | 514
4 | 3.1.4.1 | - | Concrete Structure (UKH) |  | 550 | 548 | 1097 | 514
4 | 3.1.4.2 | - | Finishing (UKH) |  | - | 1098 | 1187 | 514
4 | 3.1.4.3 | - | Steel Structure (UKH) |  | - | 1098 | 1139 | 514
3 | 3.1.5 | - | Construction of the Main Steam and Feedwater Valve Compartment (UJE) |  | 333 | 492 | 674 | 689
4 | 3.1.5.2 | - | Finishing (UJE) |  | 183 | 492 | 674 | 689
3 | 3.1.6 | - | Construction of the Equipment Lock Structure and Gantry (UJF) |  | 679 | 709 | 1199 | 751
4 | 3.1.6.2 | - | Civil Dependent (UJF) |  | 491 | 914 | 1199 | 751
4 | 3.1.6.3 | - | Finishing (UJF) |  | 85 | 709 | 793 | 860
2 | 3.2 | - | Erection of the Steel Envelope of the Containment Sphere and Locks (UJA) |  | 721 | 787 | 1289 | 325
3 | 3.2.8 | CEG1110000 | Erection of the JME Equipment Lock (UJA) | EPC | 150 | 787 | 936 | 678
3 | 3.2.9 | CEG1075000 | Erection of the JMF Personnel Lock (UJA) | EPC | 186 | 792 | 977 | 547
3 | 3.2.10 | CEG1270000 | Erection of the JMG Emergency Lock (UJA) | EPC | 150 | 803 | 952 | 662
3 | 3.2.15 | CEG1263000 | Erection Gate Closing (UJA) | EPC | 90 | 1200 | 1289 | 325
2 | 3.3 | - | Electromechanical Erection in Buildings (UJA/UJB/UJE/UJF/UKA/UKH) |  | - | 152 | 1713 | 237
3 | 3.3.1 | - | Erection in the Reactor Building (UJA) |  | - | 152 | 1713 | 237
4 | 3.3.1.2 | - | Coating of Fuel Pools and Supercompact Racks (UJA) |  | 1279 | 529 | 1430 | 520
4 | 3.3.1.3 | - | Fuel Refilling Device (UJA) |  | 240 | 1230 | 1469 | 67
4 | 3.3.1.4 | - | Nuclear Fuel Storage and Handling (UJA) |  | 210 | 1350 | 1559 | 193
4 | 3.3.1.5 | - | Reactor Protection System (UJA) |  | 120 | 547 | 666 | 987
4 | 3.3.1.6 | - | Containment Penetrations (UJA) |  | 364 | 569 | 932 | 682
4 | 3.3.1.7 | - | Erection of Supports and Isolation of the Reactor Pressure Vessel (UJA) |  | 1165 | 551 | 1324 | 182
4 | 3.3.1.8 | - | Erection of Primary Circuit Supports (UJA) |  | 1493 | 431 | 1713 | 39
4 | 3.3.1.9 | - | Erection of Primary Circuit Components (UJA) |  | 727 | 933 | 1659 | 291
4 | 3.3.1.10 | - | Erection of Primary Circuit Piping (UJA) |  | 614 | 786 | 1399 | 17
4 | 3.3.1.11 | - | Piping Systems (UJA, except Primary Circuit) |  | - | 152 | 1448 | 214
3 | 3.3.2 | - | Erection in the Reactor Building (Annulus) (UJB) |  | - | 152 | 1598 | 124
4 | 3.3.2.1 | - | Mechanical Components (UJB) |  | 440 | 682 | 1121 | 470
4 | 3.3.2.2 | - | Piping Systems (UJB) |  | - | 152 | 1598 | 124
3 | 3.3.3 | - | Erection of Common Systems UJA / UJB / UKA / UJE |  | 1084 | 335 | 1418 | 235
4 | 3.3.3.1 | - | Ventilation Systems (UJA / UJB) |  | 630 | 382 | 1011 | 370
4 | 3.3.3.2 | - | Electrical and I&C Systems and Equipment (UJA/ UJB / UJE) |  | 542 | 877 | 1418 | 235
4 | 3.3.3.3 | - | Temporary Ventilation (UJA / UJB / UKA Controlled Area) |  | 240 | 335 | 574 | 516
3 | 3.3.4 | - | Erection in the Reactor Auxiliary Building (UKA) and Discharge Chimney (UKH) |  | - | 152 | 1418 | 304
4 | 3.3.4.1 | - | Mechanical Components (UKA) |  | 450 | 542 | 991 | 606
4 | 3.3.4.2 | - | Piping Systems (UKA) |  | - | 152 | 1261 | 461
4 | 3.3.4.3 | - | Electrical and I&C Systems and Equipment (UKA) |  | 847 | 572 | 1418 | 235
4 | 3.3.4.4 | - | Ventilation Systems (UKA) |  | 540 | 572 | 1111 | 309
4 | 3.3.4.5 | - | Piping Systems (UKH) |  | 390 | 732 | 1121 | 601
3 | 3.3.5 | - | Erection in the Valve Compartment (UJE) and in the Equipment Lock and Gantry Structure (UJF) |  | 1025 | 479 | 1273 | 449
4 | 3.3.5.1 | - | Piping Systems (UJE) |  | 960 | 489 | 1208 | 514
4 | 3.3.5.2 | - | Piping Systems (UJF) |  | 795 | 479 | 1273 | 449
2 | 3.4 | - | Final Erection and Commissioning Services for Nuclear Area Systems |  | 741 | 1012 | 1752 | 0
3 | 3.4.1 | - | Piping Systems and Mechanical Components |  | 721 | 1032 | 1752 | 0
4 | 3.4.1.1 | CEG2250000 | Final Services of Erection and Commissioning of the Piping Systems and Mechanical Components (UKA/UKH) | EPC | 180 | 1032 | 1211 | 541
4 | 3.4.1.2 | CEG2320000 | Final Services of Erection and Commissioning of the Piping Systems (UJE) | EPC | 130 | 1149 | 1278 | 474
4 | 3.4.1.3 | CEG1900000 | Final Services of Erection and Commissioning of the Piping Systems (UJA, except Primary Circuit) | EPC | 150 | 1449 | 1598 | 124
4 | 3.4.1.4 | CEG1590000 | Final Services of Erection and Commissioning of the Piping Systems (UJB) | EPC | 131 | 1498 | 1628 | 124
4 | 3.4.1.5 | CEG1650000 | Commissioning of FCB Fuel Refilling Machine (UJA) | EPC | 99 | 1654 | 1752 | 0
3 | 3.4.2 | - | Electrical and I&C Systems and Components |  | 481 | 1058 | 1538 | 214
4 | 3.4.2.1 | CEG2790000 | Final Services of Erection and Commissioning of the Electrical and I&C Sys. (UKA / UKH) | EPC | 386 | 1058 | 1443 | 309
4 | 3.4.2.2 | CEG6590000 | Final Services of Erection and Commissioning of the Electrical and I&C Sys. (UJA / UJB / UJE)) | EPC | 450 | 1089 | 1538 | 214
3 | 3.4.3 | - | Ventilation Systems and Components |  | 432 | 1012 | 1443 | 309
4 | 3.4.3.1 | CEG2730000 | Final Services of Erection and Commissioning of the Ventilation Sys. KLB/KLA (UJB/ UJA) | EPC | 371 | 1012 | 1382 | 370
4 | 3.4.3.2 | CEG2810000 | Final Services of Erection and Commissioning of the Ventilation Sys. KLE (UKA / UKH) | EPC | 332 | 1112 | 1443 | 309
1 | 4 | - | ELECTRICAL AREA / DIESEL GENERATORS / TRANSFORMERS (UBA / UBP / ULB / Transformers) |  | - | 152 | 1556 | 226
2 | 4.1 | - | Civil Construction |  | 1156 | 152 | 1261 | 392
3 | 4.1.1 | - | Construction of the Emergency Power Building (ULB) |  | 789 | 152 | 939 | 714
4 | 4.1.1.2 | - | Finishing (ULB) |  | 668 | 272 | 939 | 714
4 | 4.1.1.3 | - | Steel Structure (ULB) |  | 759 | 152 | 909 | 714
3 | 4.1.2 | - | Construction of the Emergency Generators and Chilled Water Building (UBP) |  | 1153 | 152 | 1258 | 395
4 | 4.1.2.1 | - | Concrete Structure (UBP) |  | 424 | 152 | 575 | 482
4 | 4.1.2.2 | - | Finishing (UBP) |  | 1153 | 347 | 1258 | 395
4 | 4.1.2.3 | - | Steel Structure (UBP) |  | 431 | 369 | 558 | 1065
3 | 4.1.3 | - | Construction of Generator Transformer Structures (UBF) |  | 372 | 152 | 523 | 598
4 | 4.1.3.1 | - | Civil Construction / Structures and Finishing (UBF) |  | 372 | 152 | 523 | 598
3 | 4.1.4 | - | Construction of the Control Building (UBA/UBD) |  | 1110 | 500 | 1261 | 392
4 | 4.1.4.2 | - | Finishing (UBA / UBD) |  | 1110 | 500 | 1261 | 392
3 | 4.1.5 | - | Construction of Unit Auxiliary Transformer Structures (UBE) |  | 371 | 180 | 550 | 571
4 | 4.1.5.1 | - | Civil Construction / Structures and Finishing (UBE) |  | 371 | 180 | 550 | 571
3 | 4.1.6 | - | Construction of Structures for External Network Transformer (UBC) |  | 91 | 152 | 242 | 707
4 | 4.1.6.1 | - | Civil Construction / Structures and Finishing (UBC) |  | 91 | 152 | 242 | 707
2 | 4.2 | - | Electromechanical Erection in Buildings (UBA / UBP / ULB / Transformers) |  | - | 152 | 1481 | 301
3 | 4.2.1 | - | Erection in the Control Building (UBA/UBD) |  | - | 152 | 1481 | 271
4 | 4.2.1.1 | - | Servers and Communication Network (I&C) (UBA) |  | 90 | 791 | 880 | 872
4 | 4.2.1.2 | - | Ventilation System (UBA) |  | 666 | 152 | 817 | 438
4 | 4.2.1.3 | - | Temporary Ventilation (I&C, CW and Server Panel Rooms) (UBA) |  | 90 | 397 | 486 | 403
4 | 4.2.1.4 | - | Piping Systems (UBA - QKC) |  | - | 152 | 665 | 1057
4 | 4.2.1.5 | - | Fire Network Piping Systems (UBA) |  | 292 | 322 | 613 | 1109
4 | 4.2.1.6 | - | Lighting Systems and Power Take-offs (UBA) |  | 365 | 272 | 636 | 583
4 | 4.2.1.7 | - | Main Control Room (CW) (UBA) |  | 384 | 558 | 941 | 158
4 | 4.2.1.8 | - | Cable Trays and Cable Launching (Power and I&C) (UBA) |  | 1204 | 392 | 1203 | 188
4 | 4.2.1.9 | - | Low Voltage Transformers (UBA/UBD) |  | 60 | 216 | 275 | 404
4 | 4.2.1.10 | - | Distribution Panels (BT, MT, CC and Package Systems) (UBA) |  | 528 | 380 | 907 | 402
4 | 4.2.1.11 | - | Electronic Panels (I&C) (UBA) |  | 394 | 487 | 880 | 872
4 | 4.2.1.12 | - | Installation of I&C Equipment (UBA) |  | 180 | 522 | 701 | 495
4 | 4.2.1.13 | - | I&C Commissioning (UBA) |  | 1206 | 276 | 1481 | 124
4 | 4.2.1.14 | - | Physical Protection Systems (UBA) |  | 240 | 976 | 1215 | 438
3 | 4.2.2 | - | Erection of Emergency Generators and Chilled Water (UBP) in the Building |  | - | 204 | 1418 | 304
4 | 4.2.2.1 | - | Emergency Diesel Generating Sets 1 (UBP) |  | 390 | 583 | 972 | 482
4 | 4.2.2.2 | - | Electrical and I&C Systems and Equipment (UBP) |  | 826 | 593 | 1418 | 235
4 | 4.2.2.3 | - | Chilled Water System (UBP) |  | 420 | 745 | 1164 | 196
4 | 4.2.2.4 | - | Ventilation Systems (UBP) |  | 420 | 745 | 1164 | 196
4 | 4.2.2.5 | - | Piping Systems (UBP) |  | - | 204 | 1334 | 388
3 | 4.2.3 | - | Erection in the Emergency Power Building (ULB) |  | - | 239 | 1418 | 334
4 | 4.2.3.1 | - | Redundancy Tanks (ULB) |  | 390 | 652 | 1041 | 342
4 | 4.2.3.2 | - | Emergency Diesel Generating Sets 2 (ULB) |  | 390 | 652 | 1041 | 342
4 | 4.2.3.3 | - | Cable Trays and Cable Launching (Power and I&C) (ULB) |  | 794 | 482 | 1275 | 317
4 | 4.2.3.4 | - | Local Control Panels and Stations (ULB) |  | 390 | 652 | 1041 | 711
4 | 4.2.3.5 | - | Physical Protection Systems (ULB) |  | 120 | 1299 | 1418 | 235
4 | 4.2.3.6 | - | Piping Systems (ULB) |  | - | 239 | 951 | 771
4 | 4.2.3.7 | - | Ventilation Systems (ULB) |  | 510 | 482 | 991 | 331
4 | 4.2.3.8 | - | Temporary Ventilation (I&C Panel Rooms) (ULB) |  | 61 | 623 | 683 | 354
3 | 4.2.4 | - | Erection in the Transformer Structures Area |  | - | 206 | 969 | 813
4 | 4.2.4.1 | - | 138 kV External Network Transformer (BCT01) |  | 60 | 333 | 392 | 707
4 | 4.2.4.2 | - | Unit Auxiliary Transformers (BBT01/02) |  | 270 | 551 | 820 | 608
4 | 4.2.4.3 | - | Generator Transformers (BAT01/02/03) |  | 332 | 524 | 855 | 633
4 | 4.2.4.4 | - | Shielded Busbars (BAA) / Generator Circuit Breaker (BAC) |  | 419 | 551 | 969 | 571
4 | 4.2.4.5 | - | Piping Systems (UBC/ UBE/ UBF) |  | - | 206 | 730 | 1052
2 | 4.3 | - | Final Erection and Commissioning Services for Central Area Systems |  | 1164 | 393 | 1556 | 196
3 | 4.3.1 | - | Piping Systems and Mechanical Components |  | 693 | 712 | 1404 | 348
4 | 4.3.1.1 | CEG6270000 | Final Erection and Commissioning Services of the Piping System (ULB) | EPC | 310 | 712 | 1021 | 731
4 | 4.3.1.2 | CEG2900000 | Final Erection and Commissioning Services of Emergency Diesel Generating Sets 1/2/3/4XJ (UBP) | EPC | 300 | 900 | 1199 | 405
4 | 4.3.1.3 | CEG3500000 | Final Erection and Commissioning Services of the Emergency Feeding Pumps 5/6/7/8XJ (ULB) | EPC | 270 | 1042 | 1311 | 342
4 | 4.3.1.4 | CEG4320000 | Final Erection Services and Preparatory Tests of the Cold Water Sys. QK (UBP) | EPC | 210 | 1165 | 1374 | 249
4 | 4.3.1.5 | CEG4290000 | Completion of the UBP System Commissioning | EPC | - | - | 1200 | 405
4 | 4.3.1.6 | CEG2960000 | Commissioning of the QK Cold Water System (UBP) | EPC | 100 | 1305 | 1404 | 249
3 | 4.3.2 | - | Electrical and I&C Systems and Components |  | 1043 | 393 | 1435 | 317
4 | 4.3.2.1 | CEG4110000 | Commissioning of the BCT01 External Network Transformer (UBC) | EPC | 90 | 393 | 482 | 797
4 | 4.3.2.2 | CEG5710000 | Complementary Erection of I&C (UBA) (Reactor Protection TXS Cabinets CF: L/M1/M2/L-UBA/N) | EPC | 90 | 791 | 880 | 872
4 | 4.3.2.3 | CEG4115000 | Interconnection line with the External Network (138 kV) ready and commissioned (BCT) | EPC | - | - | 820 | 459
4 | 4.3.2.4 | CEG4160000 | Commissioning of Auxiliary Transformers of Unit BBT01/02 (UBE) | EPC | 210 | 821 | 1030 | 608
4 | 4.3.2.5 | CEG4220000 | Commissioning of Generator Transformers BAT01/02/03 (UBF) | EPC | 150 | 856 | 1005 | 633
4 | 4.3.2.6 | CEG6260000 | Final Erection and Comissioning Services of the Electrical and I&C Systems (UBP) | EPC | 270 | 930 | 1199 | 406
4 | 4.3.2.7 | CEG4710000 | Commissioning of Energy Supply System for Auxiliaries Unit Sys. (S1) | EPC | 450 | 942 | 1391 | 158
4 | 4.3.2.8 | CEG3717000 | Final Erection and Comissioning Services of the Electrical and I&C Systems (ULB) | EPC | 480 | 956 | 1435 | 317
4 | 4.3.2.9 | CEG4250000 | Commissioning of BAA Shielded Busbars and BAC Generator Circuit Breaker (UMA) | EPC | 65 | 970 | 1034 | 571
4 | 4.3.2.10 | CEG6280000 | Final Erection and Comissioning Services of the Local Control Panels and Stations (ULB) | EPC | 385 | 1042 | 1426 | 326
3 | 4.3.3 | - | Ventilation Systems and Components |  | 793 | 764 | 1556 | 196
4 | 4.3.3.1 | CEG3525000 | Final Erection and Comissioning Services of the Ventilation System SAC (UBA) | EPC | 500 | 764 | 1263 | 438
4 | 4.3.3.2 | CEG4060000 | Commissioning of the SAL Ventilation System (ULB) | EPC | 430 | 992 | 1421 | 331
4 | 4.3.3.3 | CEG2980000 | Final Erection and Comissioning Services of the Ventilation (UBP) | EPC | 392 | 1165 | 1556 | 196
1 | 5 | - | CONVENTIONAL AND EXTERNAL AREAS (ONE / Other Buildings) |  | - | 152 | 1513 | 269
2 | 5.1 | - | Civil Construction |  | 1362 | 152 | 1513 | 140
3 | 5.1.1 | - | Civil Construction - Discharge Channels (UGZ / UQT / UQN) |  | 1170 | 152 | 1321 | 209
4 | 5.1.1.1 | CEG3361000 | Concrete Structure (UGZ and UQT) | EPC | 612 | 152 | 763 | 767
4 | 5.1.1.2 | CEG3371000 | Concrete Structure (UQN / UQT - Connection with Angra 2) | EPC | 570 | 752 | 1321 | 124
3 | 5.1.2 | - | Civil Construction - Protection Jetty and Beach Line (UZS / UZP) |  | 720 | 572 | 1291 | 124
4 | 5.1.2.1 | CEG3381000 | Containment Structure Design - Itaorna Beach Line (UZP) | EPC | 180 | 572 | 751 | 124
4 | 5.1.2.2 | CEG3383000 | UQX Structure Protection Jetty Design (UZS) | EPC | 180 | 572 | 751 | 124
4 | 5.1.2.3 | CEG3382000 | Containment Structure - Itaorna Beach Line (UZP) | EPC | 540 | 752 | 1291 | 124
4 | 5.1.2.4 | CEG3384000 | Structure of the UQX Structure Protection Jetty (UZS) | EPC | 540 | 752 | 1291 | 124
3 | 5.1.3 | - | Construction of Water Intake Structures (UPC / UQB) |  | 1362 | 632 | 1513 | 140
4 | 5.1.3.1 | - | Concrete Structure (UPC/UQB) |  | 600 | 632 | 751 | 124
4 | 5.1.3.2 | - | Finishing (UPC/UQB) |  | 762 | 752 | 1513 | 140
3 | 5.1.4 | - | Construction of the Turbine Building (UMA) |  | 520 | 152 | 671 | 982
4 | 5.1.4.1 | - | Concrete Structure (UMA) |  | 180 | 492 | 671 | 409
4 | 5.1.4.2 | - | Steel Structure (UMA) |  | 457 | 152 | 608 | 1045
3 | 5.1.5 | - | Construction of Water Discharge Structures (UQJ / UQM) |  | 61 | 152 | 212 | 473
4 | 5.1.5.1 | - | Concrete Structure (UQJ/UQM) |  | 61 | 152 | 212 | 473
2 | 5.2 | - | Electromechanical Erection in Buildings (ONE and Other Buildings) |  | - | 152 | 1491 | 291
3 | 5.2.1 | - | Erection in the Turbine Building ( UMA ) |  | - | 152 | 1202 | 580
4 | 5.2.1.2 | - | Turbogenerator and Auxiliary Set (MA / MK) (UMA) |  | 390 | 737 | 1126 | 409
4 | 5.2.1.3 | - | Ventilation System (UMA) |  | 546 | 335 | 880 | 452
4 | 5.2.1.4 | - | Pre-Heaters (A1/A2) and Condensers (MAG10/20/30) (UMA) |  | 980 | 152 | 1131 | 441
4 | 5.2.1.5 | - | Water-Steam Circuit Systems (UMA) |  | - | 152 | 1202 | 400
4 | 5.2.1.6 | - | Piping Systems (UMA) |  | - | 152 | 1161 | 621
4 | 5.2.1.7 | - | Electrical and I&C Systems and Equipment (UMA) |  | 552 | 331 | 882 | 536
3 | 5.2.2 | - | Water Intake Mechanical Systems and Components (UPC / UQB) |  | 756 | 722 | 1236 | 159
4 | 5.2.2.5 | CEG3253400 | Mobilization of Supervision Service Team of Erection of the Water Inlet Mechanic Equip. (UPC/ UQB) - M201 | EPC | 120 | 722 | 841 | 159
4 | 5.2.2.6 | CEG3255000 | Mobilization of Supervision Service Team of Erection of the Water Intake Gantry (M315) | EPC | 120 | 722 | 841 | 159
4 | 5.2.2.7 | CEG3260000 | Erection of Mechanical Water Intake Equipment (UPC/UQB) | EPC | 395 | 842 | 1236 | 159
3 | 5.2.3 | - | Electrical and I&C Systems and Equipment (UPC / UQB) |  | 515 | 872 | 1386 | 159
4 | 5.2.3.1 | CEG3270000 | Erection of Electrical and I&C Equipment and Systems (UPC/ UQB) | EPC | 515 | 872 | 1386 | 159
3 | 5.2.4 | - | PEB Piping Systems (1/ 2/ 3/ 4/ 5 and 6 UPX) |  | 810 | 152 | 961 | 692
4 | 5.2.4.1 | CEG4470000 | Piping - Prefabricated, Erection, Pressure Tests, clogged piping before Erection (PEB) | EPC | 450 | 152 | 601 | 988
4 | 5.2.4.2 | CEG3330000 | Piping - Tubular Erection. of the Coolant System of Security Service (PEB) | EPC | 450 | 512 | 961 | 692
3 | 5.2.5 | - | Electromechanical Erection in Water Discharge Structures (UQJ / UQM) |  | 285 | 1207 | 1491 | 231
4 | 5.2.5.1 | CEG6100000 | Piping - Engineering Phase 1 (Workbook) (UQJ/UQM) | EPC | 80 | 1207 | 1286 | 241
4 | 5.2.5.2 | CEG6110000 | Piping - Prefabrication (UQJ/UQM) | EPC | 80 | 1267 | 1346 | 241
4 | 5.2.5.3 | CEG6120000 | Piping - Erection QJ/QM001 (UQJ/UQM) | EPC | 75 | 1357 | 1431 | 231
4 | 5.2.5.4 | CEG6130000 | Pipes - Cleaning, Hydrostatic Test, Painting Phase 2 (UQJ/UQM) | EPC | 50 | 1412 | 1461 | 231
4 | 5.2.5.5 | CEG6140000 | Piping - Engineering Phase 2 (Documentation Closing) (UQJ/UQM) | EPC | 50 | 1442 | 1491 | 231
2 | 5.3 | - | Other Buildings / Structures / Galleries |  | - | 152 | 1291 | 431
3 | 5.3.1 | - | Plant Area (UZT) and Pipe and Cable Galleries |  | - | 152 | 1152 | 570
4 | 5.3.1.1 | - | Galleries / Cable and Piping Ducts |  | 567 | 152 | 718 | 935
4 | 5.3.1.2 | - | Miscellaneous Structures |  | 718 | 152 | 869 | 733
4 | 5.3.1.3 | - | Plant Area Piping and Piping Galleries |  | - | 152 | 1152 | 570
3 | 5.3.2 | - | Condensate Purification Building (ULD) |  | - | 152 | 691 | 877
4 | 5.3.2.3 | CEG3760000 | Concrete Structure (1/2GHC) | EPC | 92 | 152 | 243 | 935
4 | 5.3.2.4 | CEG3765000 | Civil Finishing (ULD) | EPC | 275 | 152 | 426 | 877
4 | 5.3.2.5 | CEG3780000 | Electromechanical Erection (GHC/ ULD) | EPC | 390 | 302 | 691 | 877
4 | 5.3.2.6 | CEG3770000 | Erection of 1/2GHC Demineralized Water Tanks | EPC | 140 | 519 | 658 | 880
3 | 5.3.3 | - | Control Gate (UYF) |  | 486 | 422 | 907 | 664
4 | 5.3.3.1 | CEG3540000 | Concrete Structure (UYF) | EPC | 153 | 422 | 574 | 664
4 | 5.3.3.2 | CEG3550000 | Civil Finishing Phase 1 (UYF) | EPC | 90 | 575 | 664 | 664
4 | 5.3.3.3 | CEG3560000 | CZ Electromechanical and Physical Protection Erection (UYF) | EPC | 243 | 665 | 907 | 664
3 | 5.3.4 | - | Administration Building/Refectory/Cold Workshop (UYA/UYB/UST) |  | 574 | 152 | 725 | 817
4 | 5.3.4.1 | CEG3511000 | Concrete Structure (UYA/ UYB/ UST) | EPC | 378 | 152 | 529 | 817
4 | 5.3.4.2 | CEG3520000 | Civil Finishing Phase 1 (UYA/ UYB/ UST) | EPC | 335 | 306 | 640 | 817
4 | 5.3.4.3 | CEG3530000 | Electromechanical Erection (UYA/ UYB/ UST) | EPC | 360 | 366 | 725 | 817
3 | 5.3.5 | - | Gas Cylinder Storage Area (UTG) |  | 454 | 352 | 805 | 767
4 | 5.3.5.1 | CEG3570000 | Concrete Structure (UTG) | EPC | 122 | 352 | 473 | 767
4 | 5.3.5.2 | CEG3580000 | Civil Finishing Phase 1 (UTG) | EPC | 181 | 474 | 654 | 767
4 | 5.3.5.3 | CEG3590000 | Electromechanical Erection (UTG) | EPC | 151 | 655 | 805 | 767
3 | 5.3.6 | - | Interconnections of 138kV and 500kV Lines |  | 1050 | 242 | 1291 | 347
4 | 5.3.6.1 | CEGPA42000 | Mobilization of the Contractor - Interconnections of the 138/500 kV Lines | EPC | 90 | 242 | 331 | 278
4 | 5.3.6.2 | CEG4910401 | Contractor's Preliminary Activities - 138/500 kV Lines | EPC | 120 | 332 | 451 | 278
4 | 5.3.6.3 | - | SE-138 kV - Output Gap 138 kV - SE Furnas |  | 550 | 452 | 1001 | 278
4 | 5.3.6.4 | - | SE-138 kV - BCT |  | 510 | 452 | 961 | 288
4 | 5.3.6.5 | - | LT 138 kV - Interconnection of SE Furnas - SE BCT |  | 510 | 452 | 961 | 288
4 | 5.3.6.6 | - | SE 500 kV - Entrance Gap - SE Furnas |  | 630 | 572 | 1201 | 347
4 | 5.3.6.7 | - | LT 500 kV - Interconnection of BAT's Trafos - SE Furnas |  | 630 | 662 | 1291 | 347
2 | 5.4 | - | Final Erection and Commissioning Services for Conventional and External Area Systems |  | 790 | 692 | 1481 | 271
3 | 5.4.1 | CEG6320000 | Final Erection and Comissioning Services of Components and Systems (GHC/ ULD) | EPC | 180 | 692 | 871 | 881
3 | 5.4.2 | CEG6290000 | Final Erection and Comissioning Services of Components and Systems (UYA / UYB / UST) | EPC | 210 | 726 | 935 | 817
3 | 5.4.3 | CEG6310000 | Final Erection and Comissioning Services of Components and Systems (UTG) | EPC | 180 | 806 | 985 | 767
3 | 5.4.4 | CEG3190000 | Final Erection and Comissioning Services of the LA Water-Steam Circuit (UMA) | EPC | 341 | 832 | 1172 | 400
3 | 5.4.5 | CEG3230000 | Ventilation System Commissioning (UMA) | EPC | 420 | 881 | 1300 | 452
3 | 5.4.6 | CEG3210000 | Final Erection and Comissioning Services of Electrical and I&C Systems(UMA) | EPC | 334 | 883 | 1216 | 536
3 | 5.4.7 | CEG6300000 | Final Erection and Comissioning Services of Components and Systems (UYF) | EPC | 181 | 908 | 1088 | 664
3 | 5.4.8 | CEG6330000 | Final Erection and Comissioning Services of the Plant Area (UZT) and Galleries | EPC | 200 | 1013 | 1212 | 540
3 | 5.4.9 | CEG6360000 | Final Erection and Comissioning Services of the Turbogenerator and Auxiliaries Set (UMA) | EPC | 217 | 1127 | 1343 | 409
3 | 5.4.10 | CEG1272000 | Start of Commissioning of the CF H - Turbogenerator | EPC | - | 1277 | - | 476
3 | 5.4.11 | CEG3280000 | Final Erection and Comissioning Services of Components and Systems (UPC / UQB) | EPC | 190 | 1292 | 1481 | 124
3 | 5.4.12 | CEG1273000 | Completion of CF H Commissioning - Turbogenerator | EPC | - | - | 1343 | 409
1 | 6 | - | FINAL TESTS AND STARTUP |  | 1621 | 330 | 1950 | 0
2 | 6.1 | CEG1520000 | Start of Preparatory Activities for Commissioning Recommended by FRAMATOME | EPC | - | 330 | - | 935
2 | 6.2 | CEG0916180 | Equipment Testing and Testing Operations | EPC | 214 | 1366 | 1579 | 26
2 | 6.3 | CEG1470000 | Primary Circuit Pressure Test (UJA) | EPC | 35 | 1580 | 1614 | 0
2 | 6.4 | CEG1302000 | Secondary Circuit Pressure Test (UMA) (Phase A) | EPC | 35 | 1580 | 1614 | 23
2 | 6.5 | CEG0916220 | First Inspection of Primary Circuit Main Equipment | EPC | 20 | 1615 | 1634 | 23
2 | 6.6 | CEG1300000 | JMA Containment Ball Pressure Test - TPC (UJA) (Phase A) | EPC | 35 | 1615 | 1649 | 0
2 | 6.7 | CEG1311000 | First Hot Operation (Phase B) | EPC | 45 | 1654 | 1698 | 4
2 | 6.8 | CEG0916240 | Second Inspection of Reactor Main Equipment | EPC | 50 | 1699 | 1748 | 4
2 | 6.9 | CEG1320000 | Core Loading (Phase C) | EPC | 29 | 1754 | 1782 | 0
2 | 6.10 | CEG6560000 | Second Hot Operation (Phase C) | EPC | 28 | 1783 | 1810 | 0
2 | 6.11 | CEG1330000 | Preparation for Power Tests (Phase D) | EPC | 20 | 1811 | 1830 | 0
2 | 6.12 | CEG1337000 | First Criticality and Beginning of Physical Tests (Phase D) | EPC | - | 1831 | - | 0
2 | 6.13 | CEG6490000 | Power Escalation (0% to 30%) (Phase D) | EPC | 30 | 1831 | 1860 | 0
2 | 6.14 | CEG6500000 | Power Escalation (30% to 80%) (Phase D) | EPC | 30 | 1861 | 1890 | 0
2 | 6.15 | CEG6510000 | Power Escalation (80% to 100%) (Phase D) | EPC | 30 | 1891 | 1920 | 0
2 | 6.16 | CEG0916780 | Plant Released for Pilot Operation | EPC | - | - | 1920 | 0
2 | 6.17 | CEG1335000 | Plant Demonstration Tests (Phase D) | EPC | 30 | 1921 | 1950 | 0